## SDA
SEKHUKHUNE DEVELOPMENT AGENCY
DRAFT 2019-2020 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN
SEKHUKHUNE DEVELOPMENT AGENCY
2019-2020 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN
MEASURABLE OBJECTIVE | PROJECT | BASELINE 2018/2019 | INDICATORS | ANNUAL TARGET 2019/2020 | Q3 TARGET | PROGRESS (Achieved/Not achieved) | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTIONS | EVIDENCE | BUDGET 2019/2020
To act as an engine for economic growth by diversifying and expanding local economic base by June 2020 | Mining Input Supplier Park MISP) | MISP report | Number of sessions conducted | 3 sessions conducted with stake holders (LEDET, Glencor and LEDA) | MISP Occupancy report | Not Achieved | MISP Occupancy report received | Lockdown due to Covid 19 pandemic | Meeting to be schedulled after lockdown | Signed Minutes* attedance register *Occupancy report | 0
| Wild-Life Empowerment programmes | Signed MOU | Number of Wild Life partnerships made with Ekim | 1 Wild Life partnership with Ekim | Funding application | Achieved | Funding application | None | None | Copy of Action Plan* Business plan | 0
| Tourism Route | Report | Number of district tourisn route marketed | 3 district tourism route marketed | 1 tourism route marketing workshop conducted | Not Achieved | Session held with Local Municipalities | Lockdown due to Covid 19 pandemic | Workshop to be conducted after Lockdown | *Report *Tourism guide map* Brochure | 0
| Agri-Park | Business Plan | Number of partership with Famers production support unit (FPSU) | 1 FPSU Partnership | 1 engagement with stakeholders (DALRRD) | Achieved | 1 engagement held with stakeholders (DALRRD) | None | None | Attendance register and minutes* Proposal | 0
| Mining Beneficiation | Mining Beneficiation Study | Number of business plan developed | 1 business plan developed | 1 project identified | Achieved | 1 project identified | None | None | Attendance register* Project Report *Business plan | 0
| Digital Economy | MOU with Limpopo Connexion (LCX) | 1 Partnership established | x1 Partnership established by MOU | 1 ICT Digital incubator proposal developed | Achieved | 1 ICT Digital incubator proposal in place | None | None | copy of the draft MOU* Proposal *Funding application | 0
| Cotton Industry Revitilisation Program | Outlook Report on cotton textile Industry in SA | 1 Partnership established | x1 Partnership established by MOU | Draft MOU | Achieved | Draft MOU in place | None | None | Draft MOU* Business plan | 100000
| Youth Entrepreneurship Development and Support | MOU with Youth Entrepreneuship project (YEP) | Number of proposals developed | x 3 proposals developed | Signed MOU 1 proposal on ICT incubation | Achieved | Signed MOUin place and 1 proposal on ICT incubation developed | None | None | Signed MOU *Proposals | 50000
| Limpopo 6000 ( Manufacturing of electrical vehicles) | Draft MOU with EISOWAVE (PTY) LTD | Number of strategic partner | x1 Partnership established by signed MOU | *Signed MOU * Proposal | Achieved | *Signed MOU in place * Proposal developed | None | None | Signed MOU * Business plan | 0
Strategic objective 2: To secure a stable and sustainable financial base for the future of the agency & Support Business Plan funding by June 2020
To secure a stable and sustainable financial base for the future of the agency and support business plan funding by June 2020 | Financial Mobilisation | Contracts with 3 appointed companies | Number of proposals | 3 Proposals Developed | 1 Proposal Developed | Achieved | 1 Proposal in place | None | None | Proposals | 0
| Amaloloo - MOU implimentation | Signed MOU | Number of VIP sanitation Top structure supplied | Supply of 670 Units of VIP top structure supplied | 1 report generated on supply of VIP sanitation top structure and proof of payment provided | Not Achieved | 1 report generated on supply of VIP sanitation top structure and proof of payment provided | Supply of VIP sanitation is put on hold due to negotiations with Service provider | meeting to be schedulled between the service provider, SDA management and SDM MM after lockdown | Proof of payment and report | 0
| Small Business Support | Draft MOU | Number of business supported | 10 SMME’s supported | Application for funding and Technical support to SMME projects | Achieved | Application for funding and Technical support to SMME projects in place | None | None | Signed MOU. List of identified SMME s and report | R 100 00
| Small Business Development Fund | Draft Funding Policy | Number of SMME's & Cooperatives supported financially | 4 SMME's/Cooperatives supported financially | Advert for proposals | Not Achieved | Advert for proposals delayed | Advert for proposal delayed due to lockdown | Advert after lockdown | *Funding Policy * Funding Approval Letters | 320000
| RAL-MOU (Steel Bridge) | Signed MOU | Number of engagements held with RAL & other partners | 2 proposals developed | Engagement with partners | Achieved | Engagement with partners held | None | None | 2 signed proposal reports * Commitment letters | 0
To develop/ ficilitate businesses that create sustainable jobs by June 2020 | BEE Keeping | 1 Informal project | Number of cooperatives supported | 1 cooperative supported | Training for the cooperative | Not Achieved | Training for the cooperative could not heppen due to lockdown | Lockdown due to Covid 19 pandemic | re-schedulled training after lockdown | Registration certificate, attendance registers | 0
| Skills Development | Agri Seta Accredidation Application lodged | Number of accreditation certificates | 1 Agri-SETA accreditation certificate obtained | Application for funding | Achieved | Application for funding in place | None | None | Signed MOU and Application for Funding | 50000
| LED lights manufacturing | Benchmarking exercise | Number of partnership created | 1 LED Lights partnership created | Finilization of MOU | Not Achieved | MOU not finalised due to lockdown | Lockdown due to Covid 19 pandemic | Re-schedulled meeting after lockdown | Draft MOU* Concept Document*Application for Funding | 0
| Aquaculture farming | Feasibility study reports | Number of Aquaculture project implemented | 1 Aquaculture project implemented | Business plan | Achieved | Business plan in place | None | None | Minutes and attendance registers Businedd Plan*Application for Funding | R 100 00
| Solar Energy | Signed SLA | Number of proposals developed | 1 proposal on solar energy | Business plan | Achieved | Business plan in place | None | None | proposal* Business plan* Implementation plan | 0
Strategic Objective 4: To enhance SDA Internal Capacity by June 2022
To enhance SDA Internal Capacity by June 2020 | Marketing and Promotional materials | Investment booklet | Number of marketing material developed | 4 SDA Marketing Material developed (Banners, brochures, folders, business cards) | Develop Communication and Marketing Strategy | Achieved | Communication and Marketing Strategy developed | None | None | SDA Marketing brochure | 180000
| SDA website development & maintenance | Previous website | Number of website developed | *1 functional website developed | Revamped website | Not Achieved | Service provider briefed and content sent to service provider to develop a dummy webside | Lockdown due to Covid 19 pandemic | website to be revamped after lockdown | Appointment letter * Functional website | 130000
| Stakeholder management | 2018/19 AGM Report | Number of public meetings & engagement held | 1 AGM and stakeholder engagement | Stakeholder enegament (SDM Strategic planning Session) | Achieved | Stakeholder enegament (SDM Strategic planning Session) | None | None | AGM Minutes/attedance registers *SDA Presentation