## BTO
DRAFT SDBIP 2021/2022
KPA: FINANCIAL VIABILITY
2021 /2022 ADJUSTED SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN
FINANCIAL VIABILITY
MEASUABLE OBJECTIVES | PROJECT | BASELINE 2020/2021 | INDICATORS | ANNUAL TARGET 2021/2022 | Q3 TARGET | PROGRESS (Achieved/ Not achieved) | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTIONED | POE | BUDGET 2021/2022
Manual GRAP Compliant FAR | Manual GRAP Compliant FAR | 100% accounting of assets | % accounting of assets | 100% accounting of assets | 100% fully functional fixed asset module | Not achieved | 80% fully functional fixed asset module | Unavailability of documents, Fixed asset module not fully fuctional | Further engagements with BCX | GRAP Compliant Fixed Asset Register/ Trial Balance | 4806000
| mSCOA implementation plan | 70% achievement of mSCOA implementation plan | % of activities on mSCOA implementation plan achieved | 100% of activities on mSCOA implementation plan achieved | 100% of all mSCOA modules fully operational by end of 3rd Quarter | Not achieved | 80% fully functional fixed asset module | Unavailability of documents, Fixed asset module not fully fuctional | Further engagements with BCX | Trial Balance/LG Portal Submission Reports | R0.00
To provide sound financial management | Functional budget steering committee | Credible budget prepared | Number of credible annual budgets prepared and implemented. | 2 Credible Annual Budgets prepared and implemented. | Credible 2021/22 Adjusted Annual Budget and 2022/23 Draft Budget. | Achieved | Credible 2021/22 Adjusted Annual Budget and 2022/23 Draft Budget in place | None | None | Council resolutions/Draft Budget Documents | R0.00
| Procurement plan | 2020/2021 procurement plan in place | Number of procurement plan developed | 1 procurement plan developed | Monitoring implementation of the plan | Achieved | Monitoring implementation of the plan done | Delays in initiating the required procurement processes. | Follow up with bid committees | Signed procurement plan | R0.00
| Irregular expenditure in the 2020/21 | Section 32 expenditure amount reported. | % Compliance with management of MFMA section 32 | 100% Compliance with management of MFMA section 32 | 3rd Quarter reporting of UIF through Section 52 reports (Annexure A) | Achieved | 3rd Quarter reporting of UIF through Section 52 reports done | Lack of understanding on the required SCM processes accros all departments | SCM to set new dates for the training | Section 52 Report | 50000
| AFS preparations | Submission of AFS and APR to the AG within the legislated time frame | Compile AFS and APR within the legislated time frame | Compile AFS and APR within the legislated time frame | N/A | No activity | n/a | n/a |  | Signed AFS and APR/ Ackonwledgement of receipt by AGSA | R1 650 000
| Identification of potential areas to be billed | *Collections and Capturing of consumer Data from 5 areas identified for potential biling. *Billing of 5 identified areas for potential revenue | Number of areas with revenue potential to be billed | Collection of data and billing of 5 areas with revenue potential | Billing of 2 area with revenue potential | Not achieved | Billing of 0 area with revenue potential | Revenue enhancement strategy not yet implemented | Implementation of the Revenue enhancement strategy and credit collection policy | Data Collection report and Summary of billing reports | R5,000 000
| Meter reading | 74%% Verification and reading of 13100 customers' meters | % of customer's meters valitated and read | 75% Validation and reading of customers meters | 70% Validation and reading of customers meters | Not achieved | 30% Validation and reading of customers meters | Non-payment of long outstanding debts | Implementation of the Revenue enhancement strategy and credit collection policy | Meter reading report | R7,500 000
| Billing of Customers | Billing of 80 % of 41133 customers | % of customers billed | 90% of 41200 customers to be billed | 90% of 41133 Customers to be billed | Achieved | 90% of 41133 Customers were billed | Less meters were read, some meters were faulty, access to some meters was denied by community members | 1) Fixing of faulty meter 2) Community participation | Billing report | 1500000
| Improve collection rate | Improve the collection rate to 75% | % improvement of collection rate | 75% of revenue collected against the billing | improvement of collection rate to 75% | Achieved | improvement of collection rate reported 95% | Non-payment of long outstanding debts | Implementation of the Revenue enhancement strategy and credit collection policy | Collection rate report | 4500000
|  | R241m. debt book | % Reduction of debt book | 2% reduction of debt book | 1,5%reduction debt book | Not achieved | 4% increase in debt book | Slow spending on conditional grants, stagnat capital projects. | Exceleration of spending on conditional grants, completion of slow moving infrastructure projects. | Own revenue reports/Debtors age analysis report | R0.00
| Free basic services | Indigent register for 2020/2021 | % of indigent customers | 10% increase in indigent customers | 8%Collection of customers'indigent registration data | Not achieved | 0% Collection of customers'indigent registration data | The process for appointment of the verification system is in progress | All indigent registration need to be validated before implementation | Indigent register for 2021/2022 | 3000000
| Payment of creditors | 80% of valid, complete and received invoices paid ( 7 days before lapse of 30 days) | % of creditors paid within 30 days against all invoices | 100% payment of valid and complete received invoices | 100% payment of valid and complete received invoices | Achieved | 100% payment of valid invoices received in March 2022 | None | None | Monthly Payment Report
| Personnel budget | 2020/2021 salaries paid by 25th and 3rd party payment paid on/before the 7th. | % payment of salaries 25th and 3rd party payment paid on/before the 7th. | 100% payment of salaries 25th and 3rd party payment paid on/before the 7th. | 100% payment of salaries 25th and 3rd party payment paid on/before the 7th. | Achieved | 100% payment of employee salaries by 31st March 2023 | None | None | Salaries Payment Vouchers
| Travel claims | 100% Travel claims paid by the 15th | % Travel claims to be paid by the 15th | 100% Travel claims to be paid by the 15th | 100% Travel claims to be paid by the 15th | Achieved | 100% valid travelling claims were processed by the 15th of March 2022. | None | None | Payment Vouchers