## Sheet1
2021/2022 QUARTER 4 REPORT
GOOD GOVERNANCE AND PUBLIC PARTICIPATION
OBJECTIVES | PROJECT | BASELINE 2020/2021 | INDICATORS | ANNUAL TARGET 2021/2022 | Q4 ACTIVITIES | PROGRESS ACHIEVED/NOT ACHIEVED | PROGRESS | CHALLENGE | REMEDIAL | POE | BUDGET 2021-2022 | EXPENDITURE
INTERNAL AUDIT
To ensure improved internal controls and clean governance in the municipality by June 2022 | Development of the Three(3) Years rolling Plan | Development of 2020-2021 Three Year Internal audit rolling plan | Number of (SDM & SDA) 3 years rolling plans developed | 2 (SDM & SDA) 3 years rolling plans developed | No activity | N/A | N/A | N/A | N/A | Approved 3 Years and Annual Internal Audit rolling Plan for SDM and SDA by Audit Committee-Audit Committee Minutes | R0.00
| Conduct Regularity audit | 22 regularity audits conducted | Number of regularity audit conducted | 20 Regularity Audits conducted | 6 regularity audits Conducted | Not Achieved | 6 regularity audit conducted however not finalised | Lack of human resource.Late appointment of service providers due to lack of budget.Unavailability of process owners | CAE position be filled. Fastrack the audit projects to be completed by end of July 2022 | Signed Regularity Audit Reports | R4734850.00 | R1442659.35
| Conduct Ad hoc Audits | Conduct Ad Hoc Audits | Percentage Ad Hoc audits conducted | 100% Management requests/ investigations conducted as and when required | 100% Management requests/ investigations conducted as and when required | Achieved | 100% Management requests/ investigations conducted as and when required | None | None | Signed Management /Investigation reports | R0.00
| To conduct ICT Audits | 4 ICT Audits reports conducted | Number of ICT Audits conducted | 4 ICT Audit reports conducted | 1 ICTAudits conducted | Achieved | 1 ICTAudits conducted | None | None | Signed ICT Audits Reports | R0.00
| To conduct Audits of Performance Information | 4 Audit of Performance information conducted | Number of Audit of Performance Information conducted | 4 Audit of Performance Information conducted | 1 AOPI conducted | Achieved | 1 AOPI conducted | None | None | Signed AOPI Reports | R0.00
| Monitoring of implementation of auditor general activities | 100% monitoring of implementation of AG activities | Percentage monitoring of External Audit implementation plan | 100%monitoring of external Audit Implementation plan | 100% monitoring of implementation of AG activities | Achieved | 100% monitoring of implementation of AG activities | None | None | Audit Action plan,Signed Minutes,proof of payments | R0.00 | R1 575 193.43
| Monitoring of Internal Audit Implementation plan | 100% monitoring of Internal Audit Implementation plan | Percentage monitoring of Internal Audit implementation plan | 100%monitoring of Internal Audit Implementation plan | 100%monitoring of Internal Audit Implementation plan | Achieved | 100%monitoring of Internal Audit Implementation plan | None | None | Internal Audit Implementation plan | R0.00
| Coordination of Audit Committee and Performance Audit Committee | 7 (4 ordinary) and (3 special ) meetings of audit and performance committees coordinated | Number of meetings of audit and performance committees coordinated | 7 (4 ordinary) and ( 3 special ) meetings of audit and performance committees coordinated | 2 meetings of audit and performance committees coordinated | Achieved | 4 meetings of audit and performance committees coordinated (19th April,12 May,26th May &27th June) | None | None | Signed Minutes/Agenda/Signed AC Reports | 670500 | R113407.44
| Monitoring implementation of the operation clean audit strategy | 100% monitoring of the operation clean audit strategy | Percentage monitoring of the operation clean audit strategy | 100%monitoring of the operation clean audit strategy | Implementation of the operation clean Audit Strategy | Not Achieved | Operation clean Audit Strategy not implemented | Operation Clean Audit Strategy not presented to council for approval | Operation Clean Audit Strategy to be workshopped to Members of Mayoral committee before submssion for approval council | Approved operation clean Audit Strategy/Minutes of OPCA meetings/Quarterly Reports | R0.00
| Conducting external assessment review | None | Number of external quality assessment performed | 1 external quality assessment performed | Conduct external assessment review | Not Achieved | 1 external quality assessment not performed | Lack of capacity (Human Resources) in the Internal Audit | Request Human resource to provide two Interns and fill in the vacant position including the position of the CAE | External Assessment Review Report | R300 000.00
RISK MANAGEMENT
To assess, identify, and manage risks and uncertainty to safeguards assets, enhance productivity, and build resilience into the operations by June 2022 | Conduct Strategic Risk Assessment and review risk register | Strategic Risk Register in /place | Number of Strategic Risk Assessment conducted, and Strategic Risk Registers reviewed | *1 Strategic Risk Assessment conducted * 4 Strategic Risk Registers reviewed | 1.Monitor & review Risk Register 2.Strategic Risk Assessment for 2022/2023 conducted | Achieved | 1.Monitored & reviewed Risk Registers 2.Strategic Risk Assessment for 2022/2023 conducted | None | None | Strategic Risk Register report | R0.00
| Conduct Operational Risk Assessment and review risk register | Operational Risk Registers in place | Number of Operational Risk Assessment Conducted and Operational Risk Registers reviewed | *1 Operational Risk Assessment Conducted *4 Operational Risk Registers reviewed | 1.Monitor & review Risk Register 2.Operational Risk Assessment for 2022/2023 conducted | Achieved | 1.Monitored & reviewed Risk Registers 2.Operational Risk Assessment for 2022/2023 conducted | None | None | Operational Risk Registers report | R0.00
| Facilitate insurance coverage for municipal assets | 1 x Assets Insurance Policy contract entered into. | Number of insurance coverage for municipal assets facilitated | All insurance coverage for municipal assets facilitated | 1. Insurance coverage for municipal assets for 2022/2023FY facilitated 2.Update insurance policy for additions and deletions | Achieved | 1. Insurance coverage for municipal assets for 2022/2023FY facilitated 2 Insurance policy for additions and deletions done | None | None | Assets Insurance Policy contract | R6 131 490. 00
| Facilitate Assets Insurance Claims and payments | Insurance claims report facilitated | Percentage processing and facilitation of insurance claims and payments | 100% insurance claims processing, and payments of repairs, losses and excess facilitated | 100% insurance claims processing and payments facilitated | Achieved | 100% insurance claims processing and payments facilitated | None | None | Insurance Claims report | R 968 851,00
| Manage Security operations and SLA | All incidents occurred reported | Number of incidents occurred, and SLA managed | All occurred incidents and SLA managed | 4 x Security cluster operations and contracts managed | Achieved | 4 x Security cluster operations and contracts managed | None | None | Quarterly Security Report | R30 000 000. 00
| Conduct Security Operational Sites Assessments | Security operational Sites Assessment conducted | Number of Security Operational sites assessments conducted | Forty (40) Security Operational sites assessments conducted | Ten (10) Security Operational sites assessments conducted | Achieved | Seventeen (17) Security Operational sites assessments conducted | None | None | Quarterly Security Operational Sites Report produced/compiled | R0.00
| Facilitate the establishment of an Anti-Fraud & Corruption hotline | Fraud and Corruption cases reported and investigated | Number of fraud and corruption allegation cases reported for referral and investigations facilitated | All fraud and corruption allegation cases reported for referral and investigations facilitated | All fraud and corruption allegation cases reported for referral and investigations | N/A | N/A | No known incident reported | N/A | Fraud and Corruption Cases report | R0. 00
To assist the Accounting Officer/Authority in addressing its oversight requirements of risk management and evaluating and monitoring the municipality’s performance with regards to risk management | Facilitate Risk Management Committee (RMC) meetings | One (01) Risk Management Committee held | Number of Risk Management Committee (RMC)meetings facilitated | 4 x Risk Management Committee (RMC) meetings facilitated | 1 x Risk Management Committee (RMC) meetings facilitated | Not Achieved | 1 x Audit Committee (AC) meeting facilitated NB. Risk Management items were tabled at the said AC meeting | None | None | Risk Management Committee report | R80 000
Two (02) Audit Committee meetings held to consider Risk Management Committee report
PUBLIC PARTICIPATION, MPAC SUPPORT; SECRETARIAT AND SUPPORT
Provide secretarial support to 10 council structures to ensure accountability by June 2022 | FORA | 16 Fora facilitated | Number of fora facilitated | 16 Fora facilitated | 1 Speakers' Forum, 1 Chief Whips' Forum, 1 Public participation Forum, 1 MPAC forum 1 Secretariat Forum facilatated. | Not achieved | 2 Speakers' Forum - 08 & 22/06/2022, 1 Chief Whips' Forum - 23/06/2022, 1 Public participation Forum - 11/05/2022, 1 MPAC forum not facilitated, 1 Secretariat forum - 23/06/2022, facilatated. | Conflicting schedules | MPAC forum meeting rescheduled for 1st quarter | Notice & Attendance registers | R75 000.00
| Public participation sessions. | 15 public participation sessions facilitated | Number of public consultation meetings facilitated | 15 public participation facilitated | 7 public consultation meetings on the IDP/Budget, 1 District Ward Committee Conference facilitated. | Achieved | Egagement with stakeholders on Draft IDP/Budget facilitated. 7 public consultatiion meetings facilitated *District ward committee conference facilitated on 30/06/2022 | None | None | Attendance registers and exit reports | R750 000.00
| SODA & Budget Day | 1 SODA , 1 Budget Day facilitated | Number of SODA and Budget days facilitated | 1 SODA , 1 Budget Day facilitated | 1 Extra Special Council Meeting (Budget Speech) Facilitated. | Achieved | 1 Extra Special Council meeting (Budget Speech) facilitated on 25/05/2022 | None | None | Notice and attendance registers | R0.00
| Council and portfolio committee meetings | 22 Council and portfolio committee meetings facilitated | Number Council and portfolio committee meetings facilitated | 24 Council and portfolio committee meetings facilitated | 1 Ordinary Council Meetings and 5 Portfolio Committee Meetings facilitated. | Achieved | 1 Ordinary Council Meeting facilitated on 28/04/2022. 4 Special Council meetings facilitated on 08,13,14,19/04/2022, 30/05/2022 and 5 Portfolio Committee Meetings facilitated | None | None | Notice and attendance registers | R500 000.00
| Study group | 4 study groups facilitated | Number of study groups facilitated | 4 study groups facilitated | 1 Study Group Facilitated. | Achieved | 1 study group facilitated on 26/04/2022 | None | None | Notice and attendance registers | R65 000.00
| Public hearings | 2 public hearings facilitated | Number of public hearings facilitated | 2 public hearings facilitated | 1 MPAC Public Hearing Facilitated. | Achieved | 1 MPAC Public hearing facilitated on 13/06/2022 | None | None | Notice and attendance registers | R200 000.00
| Strategic planning sessions for Section 79 Portfolio Committees & MPAC | 2 strategic planning sessions facilitated | Number of strategic planning session facilitated | 2 strategic planning sessions facilitated | 1 Section 79 Portfolio Committees Strategic planning Session facilitated. | Achieved | 1 Section 79 Portfolio Committees Strategic planning Session facilitated on 08 - 10/06/2022 | None | None | Notice and attendance registers | R350 000.00
| Capacity building workshops | 2x workshops facilitated | Number of workshops facilitated | 2x workshops facilitated | 1 capacity building Workshop on Income tax facilitated. | Achieved | 2 capacity building workshop on Income Tax facilitated during the induction workshop for Cllrs on 28-29/01/2022 | None | None | Notice and attendance registers | R300 000.00
| Training and development of Cllrs | 2x councillors trained | Number of councillors trained | 10x Councillors trained | No activity | N/A | N/A | N/A | N/A | Exit report | R600 000.00
| Queries and assistance of travel claims | 100% resolution of Cllrs queries facilitated | Percentage resolution of Cllrs queries facilitated | 100% resolution of Cllrs queries facilitated | 100% resolution of Cllrs queries facilitated. | Achieved | 100% resolution of cllrs queries facilitated | None | None | Exit report | R0.00
| Resolution registers for Council implementation. | 4 Council Resolution registers compiled and coordinated | Number of Council Resolution registers compiled and coordinated | 4 Council Resolution registers compiled and coordinated | 1 council resolution register compiled and coordinated. | Achieved | 1 Council Resolution register compiled and coordinated | None | None | Council resolution register | R0.00
| Council whippery meetings facilitated | 4 meetings held | Number of meetings facilitated | 4 Council Whippery meeting Facilitated. | 1 Council Whippery meeting Facilitated. | Achieved | 1 council whippery meeting facilitated 06/04/2022 | None | None | Notice and attendance registers | R20 000.00
| Working sessions for Cllrs. | 8 MPAC Working sessions for Cllrs facilitated | Number of MPAC working sessions for Cllrs facilitated | 8 MPAC working sessions for Cllr facilitated. | 2 MPAC working sessions for Cllr facilitated. | Achieved | 7 MPAC working sessions for Cllr facilitated on 11 - 12/05/2022, 19 - 20/05/2022, 24/05/2022, 14 - 15/06/2022 | None | None | Notice and attendance registers | R180 000.00
COMMUNICATIONS; ADVOCACY; SOCIAL FACILITATION; SPECIAL PROGRAMMES AND ARTS & CULTURE
To facilitate stakeholder & sectorial engagement by June 2022 | Mayoral Outreaches and Sectorial Engagements | 12 Programmes facilitated | Number of community & sectorial engagements facilitated | 8 stakeholder & sectorial engagements facilitated | 2 stakeholder & sectoral engagement facilitated | Achieved | 4 Stakeholder and Sectoral Engagement facilitated. 13 April 2022 -SODA, 25 May 2022 (Budget Speech, 30 June 2022 Ward Committee Launching at Moses Mabotha Civic Hall and 30 June 2022 (Youth Job Summit. | None | None | Attendace Register & Exit report | R800 000,00 | 42008
To provide support to Mayoral Committee by June 2022 | Executive Support to Mayoral Committee | 12 Mayoral Committee meetings supported | Number of Mayoral Committee meetings supported | 12 Mayoral Committee meetings supported | 3 Mayoral Committee meetings supported | Achieved | 4 Mayoral Committee Meetings supported. Mayoral committee meeting held 12 April 2022 at the council chamber,13 and 19 May 2022 at the council chamber and 10 June 2022 at Lekgotla Boardroom. | None | None | Attendace Registers | R0.00 | 0
To produce newsletters by June 2022 | Newsletter & Publications | 16 Programmes produced | Number of newsletters produced | 8 newsletters produced. | 1 external and 1 internal newsletters produced | Achieved | 1 Internal and 1 External Newsletters Produced. | None | None | Newsletters | R500 000,00 | 335620
To market and brand events by June 2022 | Media Relations and Marketing | 12 Events Branded | Number of events Marketed and branded | 12 Events marketed and branded | 3 events marketed and branded | Achieved | 3 Events Marketed and Branded. Draft Annual Report,Handover Manoke Tribal Office Project, Inauguration of Ward Committees,Youth Economic Summit | None | None | Exit reports, pictures\publications | R100 000,00 | 0
To undertake website updates by June 2022 | Website Management | 20 Updates undertaken | Number of Website Updates undertaken | 12 Website Updates undertaken | 3 Website Updates undertaken | Achieved | 3 Websites updates undertaken | None | N/A | Screenshots | R150 000,00 | 0
To facilitate meetings for Traditional Leaders by June 2022 | Executive Support and Traditional Leadership Affairs | 2 SPLUMA meetings supported | Number of Traditional Leadership meetings facilitated | 3 Traditional Leadership meetings facilitated | 1 meeting facilitated | Achieved | 2 Traditional leadership meetings facilitated. 1 held at Fetakgomo Tubatse Chamber Ga-Nkoana 11 June 2022, and the 2nd one on the 23 June 2022 respectively. | None | N/A | Attendance registers and exit reports | R0. 00 | 0
To facilitate strategic events by June 2022 | Special Mayoral strategic Events | 5 strategic events Facilitated | Number of Strategic Events facilitated | 5 strategic events facilitated | 2 strategic events facilitated | Achieved | 2 strategic events facilitated.Kgoshi Mampuru and Kgoshi Nyabela Commemorations held Dec 2021 at Mapogo Heritage Site and Jan 2022 at Mamone Sport Ground | None | None | Attendance registers and exit reports | R500 000,00 | 156110
To facilitate Moral Regeneration Movement committee programmes by June 2022 | Strengthening of Moral Regeneration Movement Committee | MRM committee established | Number of programmes for MRM committee facilitated | 2 MRM committee programme facilitated | 1 MRM activity facilitated | Achieved | 1 MRM activity facilitated.Zoom Meetings held on the 15 June 2022 - Microsoft Team | None | None | Attendance registers and exit reports | R100 000,00 | 0
To generate Customer Care reports by June 2022 | Customer Care Services | 24 reports generated | Number of reports generated | 24 queries/ complains reports on customer care generated | 6 customer care reports generated | Achieved | 6 customer care reports genetated | None | None | Exit reports | R0.00 | 0
To revamp the Call Centre by June 2022 | Call Centre Revamping & Maintenance | 24 hour outdated call centre system | Number of call centre revamped | 1 call centre revamped | No activity | N/A | N/A | N/A | N/A | Report | R600 000,00 | 0
To conduct Batho Pele programmes by June 2022 | Batho Pele | 6 Programmes conducted | Number of Batho Pele Programmes conducted | 4 Batho Pele Programmes conducted | 1 Batho Pele Programmes conducted | Achieved | 3 Batho pele programme conducted.Activities held 03 May 2022 Batho Pele Forum Meeting at Makhuduthamaga Chamber, Visual Launching Batho Pele Forum and 31 May 2022 Workshop Ga-Nkoana).Batho Pele Workshop held 01 - 02 June 2022 Fetakgomo Tubatse Council Chamber (Ga-Nkoana) | None | None | Reports | R100 000,00 | 29942
To co-ordinate SODA by June 2022 | SODA | 2020/2021 SODA held | Number of SODA coordinated | 1 SODA coordinated | No activity | N/A | SODA event that was supposed to be in quarter 3 was held on 13 April 2022 at Ga-Masemola Stadium | None | None | Attendance registers and exit reports | R450 000,00 | 391065.24
To facilitate campaigns for the elderly by June 2022 | Aged care | 2 aged care programmes facilitated | Number of Aged Care campaigns facilitated | 2 Aged Care campaigns facilitated | No activity | N/A | N/A | N/A | N/A | Attendance registers and exit reports | R200 000,00 | 12970
To facilitate campaigns for the children by June 2022 | Children’s Care | 2 children’s activities facilitated | Number of children's campaigns facilitated | 2 children's campaigns facilitated | 1 children programme facilitated | Achieved | 1 children programme facilitated.Take a girl child to work held. | None | None | Attendance registers and exit reports | R100 000,00 | 0
To facilitate campaigns for women by June 2022 | Woman Development Initiative | 4 Women Programmes facilitated | Number of woman development initiatives facilitated | 3 woman development initiatives facilitated | 1 programme for women facilitated | Achieved | 1 programme for women facilitated | None | None | Attendance registers and exit reports | R300 000,00 | 104450
To facilitate Awareness campaigns for people with disability by June 2022 | People with disability | 3 Programmes facilitated | Number of awareness campaigns for people with disability facilitated | 2 awareness campaigns for people with disability facilitated | No activity | N/A | N/A | N/A | N/A | Attendance registers and exit reports | R200 000,00 | 71500
To facilitate art and culture programmes by June 2022 | Cultural Heritage Celebrations and Language Promotions | 2 Programmes facilitated | Number of Heritage and promotions of indigenous languages and theatre workshop facilitated | 1 Heritage day and 2 promotions of indigenous languages and Theatre workshop facilitated | No activity | N/A | N/A | N/A | N/A | Attendance registers and exit reports | R500 000,00 | 0
To coordinate health calendar days activities by June 2022 | Coordination of health calendar days activities | 3 health calendar days activities conducted | Number of health calendar days activities coordinated | 3 Health calendar days activities coordinated | 1 heath calendar day co-ordinated | Not Achieved | 1 heath calendar day not held | Unavailability of major stakeholders | Event planned for 2022/23 financial year | Attendance registers and exit reports | R200 000,00 | 0
To coordinate district AIDS Council activities by June 2022 | Coordination of District AIDS Council activities | 4 District Aids Council activities coordinated | Number of district AIDS Council activities coordinated | 3 district AIDS Council activities coordinated | 1 district AIDS Council activities coordinated | Not Achieved | District AIDS Council meeting not coordinated. | Disrict Aids Council activity not coordinated due to tight programme | AIDS Council meeting rescheduled for 2022/23 financial year | Attendance registers and exit reports |  | 0
To facilitate Youth development programmes by June 2022 | Youth Opportunities Expo | 3 Programmes facilitated | Number of Youth development programmes facilitated | 3 Youth development programmes facilitated | 1 Youth development programme facilitated | Achieved | 1 youth development programme facuilitated.Youth Job Summit held 30 June 2022 at Boiketlong Lodge | None | None | Attendance registers and exit reports | R900 000 00 | 128600
To facilitate Mayor’s forum activities by June 2022 | Facilitation of Mayor’s forum | 4 Mayor’s forum facilitated | Number of Mayor’s forum facilitated | 4 Mayor’s forum facilitated | 1 Mayor’s forum facilitated | Not Achieved | Mayor's Forum not facilitaed. | Forum meeting not held due to tight schedule. | Forum meetings rescheduled for 2022/23 | Attendance registers and exit reports | R0.00 | 0
To facilitate Mayoral sports activities by June 2022 | Facilitation of Mayoral Sports activities | 2 Mayoral Sport activities facilitated | Number of Mayoral Sport activities facilitated | 1 Mayoral Sport activities facilitated | 1 Mayoral sport activity facilitated | Achieved | 1 Mayoral sport activity (2022 Executive Mayor's Cup) held 29 June 2022 at G/dal Rugby Stadium | None | None | Attendance registers and exit reports | R500 000,00 | 386000 | R6,200,000.00
[11 empty] | R55,299,378.15 | 2962889.14