## Sheet1
BASIC SERVICE DELIVERY
2021/2022 SDBIP
OBJECTIVES | PROJECT | BASELINE 2020/2021 | INDICATORS | ANNUAL TARGET 2021/2022 | Q1 TARGET | PROGRESS (Achieved/ Not achieved) | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTIONS | POE | BUDGET 2021-2022
INFRASTRUCTURE AND WATER SERVICES
OPERATION AND MAINTENANCE (O&M)
To resolve registered sanitation incidents within 14 days. | Sanitation incidents | 700 registered sanitation incidents resolved within 14 days | Number of registered sanitation incidents resolved within 14 days | 700 registered sanitation incidents resolved within 14 days | 175 registered sanitation incidents resolved within 14 days | Achieved | 209 registered sanitation incidents resolved within 14 days | None | None | Incident Report | 52,048,895,51
To resolve registered water incidents within 14 days. | Water incidents | 5000 registered water incidents resolved within 14 days | Number of registered water incidents resolved within 14 days | 4500 registered water incidents resolved within 14 days | 1125 registered water incidents resolved within 14 days | Achieved | 1461 registered water incidents resolved within 14 days | None | None | Incident Report
To purchase Bulk water by June 2022 | Bulk Water Purchases | 16 500Mℓ of water purchased | Number of Mℓ water purchased | 16 500Mℓ of water purchased | 4125Mℓ of water purchased | Achieved | 4284Mℓ of water purchased | None | None | Summary Meter readings report. | 135, 330,000
To develop water sources in areas that does not have infrastructure and replace dried boreholes by June 2022 | Ground Water Development | New Program | Number of ground water source developed | 20 Ground water source developed (boreholes) | Procurement of Geo-Hydrologist | Achieved | 08 Procurement of Geo-Hydrologist | None | None | Progress Reports | 10757256.78
To purchase electricity by June 2022 | Electricity Usage | 1200 KWH of Electricity used | Number of KWH electricty used | 10 000 000 KWH of Electricity used | 2,5 000 000KWH of Electricity used | Achieved | 8,333 333KWH of Electricity used | None | None | Summary Electrical Meter readings report. | 40000000
RURAL ROADS ASSET MANAGEMENT SYSTEM (RRAMS)
To Develop 80% of Road Asset Management System by June 2022 | Development of Rural Roads Asset Management System | Desk top studies and the first rounds of Visual Conditions Assessments | Number of kilometres of Roads assessed | 500 kilometres of Roads assessed | 0 kilometres of Roads assessed | N/A | N/A | N/A | N/A | Progress report | 2, 437, 000. 00
|  |  | Number of traffic counting stations completed. | 200 traffic counting stations completed | 0 traffic counting stations completed | N/A | N/A | N/A | N/A
REGIONAL BULK INFRASTRUCTURE GRANT (RBIG)
To reduce water services backlog with 90% by June 2022 | Mooihoek bulk water supply phase 4F1 | 1 Kilometers of bulk water pipeline and concrete reservoirs constructed | Number of km of bulk pipeline tested and commissioned | 1km of bulk pipeline tested and commissioned | 1km of bulk pipeline tested and commissioned | Achieved | 1km of bulk pipeline tested and commissioned | None | None | Progress report | R94 645 000. 00
To reduce water services backlog with 90% by June 2022 | Construction of Mooihoek bulk water supply phase G1.1 | 1 X 5 Ml concrete reservoir completed Phase 4BA | Number of km of bulk pipeline and package plant constructed | Construction of 3 Kilometres of bulk water supply pipeline. Construction of 1 package plant type clarifier | Contractor appointed. Done with contractual obligations and site establishments | Achieved | Contractor appointed. Done with contractual obligations and site establishments | None | None | Progress report
To reduce water services backlog with 90% by June 2022 | Construction of Mooihoek bulk water supply phase G1.2 | 1 X 5 Ml concrete reservoir completed Phase 4BA | Number of km of bulk pipeline constructed | Construction of 4.7 Kilometers of bulk water supply pipeline. | Contractor appointed. Done with contractual obligations and site establishments | Achieved | Contractor appointed. Done with contractual obligations and site establishments | None | None | Progress report
To reduce water services backlog with 90% by June 2022 | Construction of Mooihoek bulk water supply phase G2 | 17km of bulk water supply pipeline completed | Number of km of bulk pipeline and KL of reinforced concrete rserviour constructed | Construction of 4.9 Kilometres of bulk water supply pipeline. Construction of 500KL Reinforced Concrete Reservoir | 0,5 Kilometers of bulk water supply pipeline constructed | Not achieved | 0,1 Kilometers of bulk water supply pipeline constructed | Delays in non-payment of contractor | Revised implimentation programme | Progress report
To reduce water services backlog with 90% by June 2022 | Construction of Mooihoek Reservoirs phase 4H1 | 12Ml/day Mooihoek Water Treatment Works | Number of Reservoir constructed | 1 Reservoir constructed | No activity | N/A | N/A | N/A | N/A | Progress report
To reduce water services backlog with 90% by June 2022 | Construction of Mooihoek Reservoirs phase 4H2 | 12Ml/day Mooihoek Water Treatment Works | Number of Reservoir constructed | 1 Reservoir constructed | No activity | N/A | N/A | N/A | N/A | Progress report
To reduce water services backlog with 90% by June 2022 | Nebo BWS Commission Jane Furse Pipeline | Nebo Phase1A completed and not commissioned | Number of Kilometers of bulk water supply pipeline tested and commissioned | 18 Kilometers of bulk water supply pipeline tested and commissioned | Test valve chambers | Not achieved | None | Outstanding fees since September 2018. Contractually SDM is required to close the contracts with both PSP in order to appoint new PSP | SDM entered into settlement agreement. Appointment of PSP on turnkey | Progress report | R50, 000, 000. 00
To reduce water services backlog with 90% by June 2022 | Nebo BWS Jane Furse to Lobethal Bulk Water Supply | 18km's of bulk water supply pipe line phase two from Jane Furse to Lobethal completed | Number of km's of bulk water supply pipeline assessed | 18km of bulk water supply pipeline assessed | No activity | N/A | N/A | N/A | N/A | Progress report
To reduce water services backlog with 90% by June 2022 | Nebo BWS Makgeru to Schoonoord BWS | 18.2 Km of Schoonoord bulk water supply pipeline in Makgeru. 10ML Command Concrete Reservoir in Schoonoord constructed | Number of Km of bulk water supply pipelines constructed | 6.4Km of bulk water supply pipeline constructed | 2.5 Km of bulk water supply pipeline constructed | N/A | N/A | Insufficient professional fees to complete the project Insufficient funds of about R22 million for contractor to fund remaining portion of sub-contracting and extension of time | SDM to follow SCM processes and National Treasury regulations for the successful completion of the project SDM to follow SCM processes and National Treasury regulations for the successful completion of the project | Progress report
To reduce water services backlog with 90% by June 2022 | Moutse BWS Project 13 & 14 | 1 WTW in Groblersdal extended in Project 1 and 1 pump station constructed in Project 6 | Number of mechanical and Electrical (M & E) components installed for the extensions to the Groblersdal Water Treatment Works and pump station | 2 mechanical and Electrical (M & E) components installed for the extensions to the Groblersdal Water Treatment Works and pump station | 2 mechanical and Electrical (M & E) components installed | Not achieved | None | Project stopped by affected stakeholder’s interference (business forum) Stakeholders demand that remedial work be performed under turnkey contract | Office of the executive mayor engaged all role players in a meeting and recommendations on action plans to achieve agreement were outlined with follow up on action plan DWS approved WSIG funding to complete the remedial works. | Progress report | R80, 000, 000. 00
| Moutse BWS Project (7 to 12) | 30 Kilometre of bulk water supply pipeline constructed | Number of Kilometres of bulk water supply pipeline installed and tested | 20Kilometre of bulk water supply pipeline installed and tested | 10Kilometre of bulk water supply pipeline installed and tested | Not achieved | None | Project stopped by affected stakeholder’s interference (business forum) Stakeholders demand that remedial work be performed under turnkey contract | Office of the executive mayor engaged all role players in a meeting and recommendations on action plans to achieve agreement were outlined with follow up on action plan DWS approved WSIG funding to complete the remedial works. CFO has been requested to advice on the turnkey contract processes | Progress report
| Moutse BWS construction bulk water pipeline project(2-4) | 19km of bulk water supply pipeline constructed | Number of km of bulk water supply pipelines assessed and refurbished | 14 km of bulk water supply pipelines assessed and refurbished | No activity | N/A | N/A | N/A | N/A | Progress Report
WATER SERVICES INFRASTRUCTURE GRANT (WSIG)
To reduce water services backlog with 90% by June 2022 | Maebe Drilling and Equipping of Borehole | Three (3) drilled and equipped boreholes and bulk pipeline. | Number of pump station constructed, package plant and storage tank installed | 1 Pump station constructed and 1 Reverse Osmosis Water Treatment Package Plant and 1 storage tank installed | 1 Pump station constructed | Not Achived | Design stage | Delays in non-payment of contractor due to non-approval of roll over. | Meeting scheduled for 14 October with DWS to expedite roll over approval. | Progress Report / Completion Certificate | R13, 000, 000. 00
| Tukakgomo RDP Section Borehole | 3.75 Km of water distribution network constructed and 1 raw water abstraction point upgraded | Number of kilometres of network constructed and water meters installed | 7 Km of water distribution network constructed and 735 water meters installed | Construction of 3km distribution network | Not Achived | Design and Procurement | Delays in non-payment of contractor due to non-approval of roll over. | Meeting scheduled for 14 October with DWS to expedite roll over approval. | Progress Report / Completion Certificate | R9, 000, 000. 00
| Nkosini Water Supply & Package Plant | 1 scoping report and business plans | Number of kilometres of pipeline constructed and protection of abstraction point and sealing of the reservoir | 3.5km of pipeline constructed and 1 protection of abstraction and sealing of 1 reservoir | Construction of 3.5km of a pipeline | Not Achived | Design and Procurement | Delays in non-payment of contractor due to non-approval of roll over. | Meeting scheduled for 14 October with DWS to expedite roll over approval. | Progress Report / Completion Certificate | R8, 000, 000. 00
| Laersdrift Water Supply Intervention | 1 Scoping Report and Business Plan | Number of kilometres of network constructed and stand pipes and storage tank installed | 8 km reticulation network constructed, 22 communal stand pipes and 1 storage tank installed | Construction of 5km network | Not Achived | Design and Procurement | Delays in non-payment of contractor due to non-approval of roll over. | Meeting scheduled for 14 October with DWS to expedite roll over approval. | Progress Report / Completion Certificate | R9, 000, 000. 00
| Phokwane/Brooklyn Water Supply | Drilling, testing and equipping of 1 and rising main and 1 storage tank. | Number of kilometres of rising main and storage tank installed | 3km of rising main and 1 elevated tank | Construction of 1.5km of rising main | Not Achived | Site establishment and procure of material | Delays in non-payment of contractor due to non-approval of roll over. | Meeting scheduled for 14 October with DWS to expedite roll over approval. | Progress Report / Completion Certificate | R4, 000, 000. 00
| Legolaneng VDIP | 410 VDIP Toilets | Number of VDIP completed | 440 VDIP completed | 150 VDIP completed | Not Achived | Design and Procurement | Delays in non-payment of contractor due to non-approval of roll over. | Meeting scheduled for 14 October with DWS to expedite roll over approval. | Progress Report / Completion Certificate | R7, 000, 000. 00
MUNICIPAL INFRASTRUCTURE GRANT(MIG)
To reduce water services backlog with 90% by June 2022 | Fetakgomo VIP Backlog Programme (Phase 2,3) | 15330 VIP units constructed | Number of VIP units constructed | 154 VIP units to be constructed | 20 VIP units to be constructed | Not Achieved | 0 VIP units constructed | No PSP panel | Expedite procurement of PSP | Progress report | R2, 000, 000. 00
To reduce water services backlog with 90% by June 2022 | Ephraim Mogale VIP Backlog Programme (Phase2,3 ) | 15730 VIP units constructed | Number of VIP units constructed | 1308 VIP units to be constructed | 60 VIP units to be constructed | Not Achieved | 0 VIP units constructed | No PSP panel | Expedite procurement of PSP | Progress report | R17, 000, 000. 00
To reduce water services backlog with 90% by June 2022 | Makhuduthamaga VIP Backlog Programme | 16096 VIP units constructed | Number VIP sanitation units to be constructed | 1308 VIP sanitation units to be constructed | 60 VIP units to be constructed | Not Achieved | 0 VIP units constructed | No PSP panel | Expedite procurement of PSP | Progress report | R17, 000, 000. 00
To reduce water services backlog with 90% by June 2022 | Upgrading of De Hoop Water Treatment Works | Ga-Malekana 12Ml Water Treatment Works | Number of WTW registered. | 01 WTW registered. | Registration | Not Achieved | Overall progress = 0%. | 5 Year Reliability Plan Outstanding to motivate registration with MIG. | Finalize and approve 5 Year Reliability Plan. | Progress report | R60, 505, 976. 00
To reduce water services backlog with 90% by June 2022 | De Hoop/Nebo Plateau/Schoonoord Water Scheme Villages:Ga –Mogashoa (Senkapudi) and Ga- Mogashoa (Manamane) | 94,6 kilometres of water pipeline constructed | Number of water reticulation pipeline constructed | 11Kilometers of water reticulation pipeline constructed | 5 Kilometers of water reticulation pipeline constructed | Not Achieved | 0 Kilometers of water reticulation pipeline constructed | Project behind schedule due limited material on site | Contractors instructed to procure outstanding material in order to accelerate the progress on site | Progress report | R4, 762, 404. 00
To reduce water services backlog with 90% by June 2022 | NSD07 Regional Water Scheme Construction of Concrete Reservoirs | 3km of bulk pipeline constructed 1 Reservoir completed | Kilometres of bulk pipeline constructed Number of reservoir completed | 13 Kilometres of bulk pipeline constructed, 3 reservoirs completed | 2 Kilometres of bulk pipeline constructed, 0 reservoirs completed | Not Achieved | 0 Kilometres of bulk pipeline constructed, 0 reservoirs completed | Project behind schedule due to stoppages relating to non-payments of sub-contractors and other related services and also due to limited material on site | Contractor has submitted an acceleration plan and was instructed to improve progress in order to complete in resonable time. Also contractor submitted a commitment letter to make outstanding payments | Progress report | R28, 686, 829. 00
To reduce water services backlog with 90% by June 2022 | De Hoop/Nebo Plateau/Schoonoord Water Scheme Villages: Makgeru, Ga Ratau & Matekane | 6 Kilometres of bulk pipeline constructed. 98 km of water reticulation pipeline 2435 metered stand pipes Equipping of two boreholes | Number of Kilometres of bulk pipeline constructed. Number of kilometers of Reticulation. Number of Standpipes constructed. Number of Water Meters Installed Number of boreholes equiped. | 6 Kilometres of bulk pipeline constructed. 42 kilometers of Reticulation. 850 Standpipes constructed. 850 Water Meters Installed Equipping of two boreholes. | 2 Kilometres of bulk pipeline constructed. 10 kilometers of Reticulation. 0 Standpipes constructed. 0 Water Meters Installed. | Achieved | 2 Kilometres of bulk pipeline constructed. 10 kilometers of Reticulation. 0 Standpipes constructed. 0 Water Meters Installed. | None | None | Progress report | R85, 472 953. 08
To reduce water services backlog with 90% by June 2022 | Elias Motsoaledi VIP Backlog Programme (Phase 2,3) | 16862 VIP units constructed | Number of VIP sanitation units to be constructed | 1308 VIP sanitation units to be constructed | 60 VIP units to be constructed | Not Achieved | 0 VIP units constructed | No PSP panel | Expedite procurement of PSP | Progress report | R17, 000, 000. 00
To reduce water services backlog with 90% by June 2022 | Carbonitites to Zaaiplaas PH4(Dindela Reservoir) | Dindela Pump Station, Gravity Main and Rising Main. | Number of reservoirs constructed | 1 Reservoir Constructed | No activity | N/A | None | Contractors terminated, no activity on site | MISA together with our planning enginners have been requested to assess the works and material on site and prepare a status quo which will then map a wayforward | Progress report | R8, 000, 000. 00
To reduce water services backlog with 90% by June 2022 | Tubatse VIP Backlog Programme (Phase 2,3) | 16830 VIP units constructed | Number of VIP sanitation units constructed | 1308 VIP sanitation units to be constructed | 60 VIP units to be constructed | Not Achieved | 0 VIP units constructed | No PSP panel | Expedite procurement of PSP | Progress report | R17, 000, 000. 00
To reduce water services backlog with 90% by June 2022 | Motlailana, Makgemeng Water Supply | 2,57 km of bulk pipeline constructed. 5,66 km of reticulation water pipeline constructed. 1x 100kl elevated tank erected. | Kilometers of bulk line constructed Kilometers of reticulation constructed Number of steel tanks erected. Number of concrete reservoirs constructed. Number of pumphouses constructed. Number of boreholes refurbished. | 5,16 Kilometers for bulk line constructed 36,87Kilometers of reticulation constructed 1 steel tank erected 2 concrete reservoirs constructed. 4 pumphouses constructed. 4 boreholes refurbished. | 2 Kilometers for bulk line constructed 5Kilometers of reticulation constructed 1 steel tank erected 0 concrete reservoirs constructed. 2 pumphouses constructed. 2 boreholes refurbished. | Not Achieved | 2 Kilometers for bulk line constructed,0 pumphouses constructed. 0 boreholes refurbished. Installation of concrete ring chambers and fittings | Steel Tank Order delayed for Motlailane. | contractor instructed to accelerate the work to ensure it is completed within the contractual time frame. | Progress report | R29 409 971.00
To reduce water services backlog with 90% by June 2022 | Malekana Regional Water Scheme | Ga-Malekana 12Ml Water Treatment Works | Kilometers of water pipeline constructed and number of reservior completed | 14 kilometres of water pipeline and 4 reservoirs completed | 6 kilometres of water pipeline and 0 reservoirs completed | Not Achieved | 1 kilometre of water pipeline and 0 reservoirs completed | Rate of production is slow | Contractor instructed to accelerate the work to ensure it is completed within the contractual time frame. | Progress report | R60 973 427.00
To reduce water services backlog with 90% by June 2022 | Lebalelo South connector pipes and reticulations | 100km of connector pipes and reticulation pipelines constructed and 3 steel tanks completed | Number of steel tanks erected | 11 steel tanks erected | 6 steel tanks erected | Not Achieved | 0 steel tanks erected | Continuous stoppage by the subcontractors due to non payment | Cessions signed between main contractors and sub contractors for the municipality to pay directly to subcontractors. | Progress report | R32, 748, 439. 30
To reduce water services backlog with 90% by June 2022 | Lebalelo South: Phase 3 (Ga- Maroga and Motlolo Bulk and Reticulation Infrastructure | 12,6 kilometres of bulk line constructed. 23,4km reticulation pipeline constructed. 8 reservoirs constructed. 1 package plant constructed. 6 boreholes refurbished. | Kilometers of bulk line constructed. Kilometers reticulation pipeline constructed. Number of WTW Constructed. | 10 Kilometers of bulk line constructed. 46Kilometers reticulation pipeline constructed. 1 WTW Constructed. | 3 Kilometers of bulk line constructed. 10Kilometers reticulation pipeline constructed. 0 WTW Constructed. | Not Achieved | 0 Kilometres of bulk line constructed, 0 km of reticulation completed,0 WTW Constructed.0 boreholes refurbished | 1.The contractor for reservior project has not resumed with works after withdrawal of his termination due to non-payment of local labourers and appointed sub-contractors and non-submission of contractual documents . 2.Slow progress and late delivery of steel pipes | 1, The contractor is given extention of time up to 04/10/2021 to submit all contract documents and pay all outstanding payments . 2. The contractor was requested to submit an accceleration plan , and instructed to fast track the progress on site . | Progress report | R63, 000, 000. 00
To reduce water services backlog with 90% by June 2022 | Mampuru Bulk Water Scheme | Ga-Malekana 12Ml Water Treatment Works | Kilometres of bulk line constructed. Number of reservoirs constructed. Number of booster pumpstations constructed. Number boreholes drilled. | 68,26 Kilometers of bulk line constructed. 10 reservoirs constructed. 3 booster pumpstations constructed. 8 boreholes drilled. | Registration | Not Achieved | Overall progress = 0%. | 5 Year Reliability Plan Outstanding to motivate registration with MIG. | Finalize and approve 5 Year Reliability Plan. | Progress report | R40,000,000.00
MUNICIPAL HEALTH SERICES
To Have an improved, clean, healthy and sustainable environment through municipal health services package by June 2022 | Environmental Pollution Prevention | 24 Awareness Campaigns on Air Quality conducted | Number of Awareness Campaigns on Air Quality conducted | 24 Awareness Campaigns on Air Quality conducted | 6 Awareness Campaigns on Air Quality conducted | Achieved | 6 Awareness Campaigns on Air Quality conducted | None | None | Report and Attendance register | R208,200.00
| Water quality monitoring | 300 Water quality samples collected | Number of Water quality samples collected | 300 Water quality samples collected | 75 Water quality samples collected | Achieved | 75 Water quality samples collected | None | None | Water Quality samples Reports | R89,507.26
| Food Safety control | 1500 Food Premises evaluated | Number of Food Premises evaluated | 1500 Food Premises evaluated | 375 Food Premises evaluated | Achieved | 384 Food Premises evaluated | None | None | Signed Assessment forms including the agent signature | R57,932.69
| Waste Management | 100 Health care risk waste monitored | Number of Health care risk waste monitored | 100 Health care risk waste monitored | 25 Health care risk waste monitored | Achieved | 26 Health care risk waste monitored | None | None | Signed Assessment forms including the agent signature | R208,200.00
| Health Surveillance of premises | 1500 premises evaluated | Number of premises evaluated | 1500 premises evaluated | 375 premises evaluated | Achieved | 382 premises evaluated | None | None | Signed Assessment forms including the agent signature | R0.00
| Surveillance and prevention of communicable diseases | 100 awareness campaigns on Communicable diseases held | Number of awareness campaigns on Communicable diseases held | 100 awareness campaigns on Communicable diseases held | 25 awareness campaigns on Communicable diseases held | Achieved | 30 awareness campaigns on Communicable diseases held | None | None | Report and attendance register | R20,820.00
| Communicable diseases outbreak control | 127 communicable diseases investigated and controlled | Number of Communicable disease outbreaks traced | All reported Communicable disease outbreaks traced | All reported Communicable disease outbreaks traced | Achieved | No Communicable disease cases reported | None | None | Reports | R2,528,423.48
| Vector Control | 1500 inspections on Vector Control on premises conducted | Number of inspections on Vector Control on premises conducted | 1500 inspections on Vector Control on premises conducted | 375 inspections on Vector Control on premises conducted | Achieved | 380 inspections on Vector Control on premises conducted | None | None | Signed Assessment forms including the agent signature | R 43,661.62
| Disposal of the dead | 100 evaluations on Disposal of the Dead facilities conducted | Number of evaluations on Disposal of the Dead facilities conducted | 100 evaluations on Disposal of the Dead facilities conducted | 25 evaluations on Disposal of the Dead facilities conducted | Achieved | 27 evaluations on Disposal of the Dead facilities conducted | None | None | Signed Assessment forms including the agent signature | R0.00
| Chemical Safety | 369 evaluations on safety to chemical handling premises conducted | Number of evaluations on safety to chemical handling premises conducted | 300 evaluations on safety to chemical handling premises conducted | 75 evaluations on safety to chemical handling premises conducted | Achieved | 108 evaluations on safety to chemical handling premises conducted | None | None | Signed Assessment forms including the agent signature | R0.00
EMERGENCY MANAGEMENT SERVICES
To protect loss of life, damage to property and environment by June 2022 | Fire and Rescue Operations | 332 reported emergency incidents attended | Number of reported emergency incidents attended | All reported emergency incidents attended | All reported emergency incidents attended | Achieved | 176 reported Emergency Services incidents attended | None | None | Call Register and Report | R0.00
| Emergency Management Services Training Academy | 3 firefighting courses facilitated | Number of firefighting courses facilitated | 3 firefighting courses facilitated | 1 firefighting course facilitated | Achieved | 1 firefighting course facilitated | None | None | Attendance Register and Report | R223 671,00
| Fire Prevention and Safety | 369 fire prevention and safety services provided | Number of fire prevention and safety services provided | All Fire prevention and safety services provided | All Fire prevention and safety services provided | Achieved | 146 fire safety and prevention services provided | None | None | Call Register and Report | R0.00
DISASTER MANAGEMNET SERVICES
To protect loss of life, damage to property and environment by June 2022 | Disaster risk assessment | 198 disaster risk incidents assessed | Number of all reported disaster incidents attended | All reported disaster Management incidents | All reported disaster management incidents attended | Achieved | 26 reported disaster management incidents attended | None | None | Register of disaster incidents | R291 480, 00
| Disaster risk reduction | 42 disaster risk reduction awareness campaigns conducted | Number of disaster risk awareness campaigns conducted | 24 disaster risk awareness campaigns conducted | 6 disaster risk reduction awareness campaigns conducted | Achieved | 09 disaster risk awareness campaigns conducted | None | None | Attendance registers
| Response and recovery | 198 disaster incidents responded | Number of all reported disaster response and recovery attended to | All reported disaster response and recovery attended to | All reported disaster response and recovery operations attented to | Achieved | 137 blankets and 61 sponges provided to all reported disaster response and recovery operations attended to | None | None | Report
| Disaster Management plan and framework review | Disaster management plan and framework in place | Number of disaster management plan and framework reviewed | 1 disaster management plan and framework reviewed | Stakeholder consultation | Achieved | Risk assessment process put on hold due to COVID 19, and to resume in Q2 | None | None | Reviewed disaster management plan and framework
| Special operations on high density days | 3 special operations on high density days campaigns coordinated | Number of special operations on high density days campaigns coordinated | 3 special operations on high density days campaigns coordinated | 1 special operations high density campaigns coordinated | Achieved | 01 Special operations on High Density Days campaigns coordinated | None | None | Operational plan and attendance register