## IWS
2022/2023 QUARTER 4 PERFORMANCE REPORT
BASIC SERVICES DELIVERY
OBJECTIVES | PROJECT | BASELINE 2021/2022 | INDICATORS | ANNUAL TARGET 2022/2023 | Q1 | Q2 | Q4 | ACHIEVED/ NOT ACHIEVED | PROGRESS | CHALLENGES | REMEDIAL ACTION | POE | BUDGET 2022-2023
OPERATIONS AND MAINTANANCE (O&M)
To resolve registered sanitation incidents within 14 days | Sanitation incidents | 800 registered sanitation incidents resolved within 14 days | Number of registered sanitation incidents resolved within 14 days | 800 registered sanitation incidents resolved within 14 days | 200 registered sanitation incidents resolved within 14 days | 200 registered sanitation incidents resolved within 14 days | 200 registered sanitation incidents resolved within 14 days | Achieved | 255 registered sanitation incidents resolved within 14 days | None | None | Incidents report | R70 160 850.80
To resolve registered water incidents within 14 days | Water incidents | 5500 registered water incidents resolved within 14 days | Number of registered water incidents resolved within 14 days | 4500 registered water incidents resolved within 14 days | 1375 registered water incidents resolved within 14 days | 1375 registered water incidents resolved within 14 days | 875 registered water incidents resolved within 14 days | Not achieved | 695 registered water incidents resolved within 14 days | delay in procurement of Material | fastrack appointment of service providers on terms contract | Incidents report
To purchase bulk water by June 2023 | Bulk Water Purchases | 2515,5Mℓ of water purchased | Number of Mℓ water purchased | 2515,5Mℓ of water purchased | 628, 875Mℓ of water purchased | 628, 875Mℓ of water purchased | 628, 875Mℓ of water purchased | Achieved | 628, 875Mℓ of water purchased | None | None | Summary meter readings report | 140743200
To purchase electricity by June 2023 | Electricity Usage | 950 MW of electricity used | Number of MW electricity used | 246 399,312 KWH of electricity used | 237 MW of electricity used | 237 MW of electricity used | 61 599,828 KWH of electricity used | Achieved | 118 577,485 KWH of electricity used | None | None | Summary meter readings report | R41 600 000.00
To improve water service provisioning by June 2023 | Borehole Development | 25 boreholes developed | Number of boreholes developed | 20 boreholes developed | 5 boreholes developed | 5 boreholes developed | 5 boreholes developed | Achieved | 8 boreholes developed | None | None | Signed report | R10 187 547.28
| Provision of water through water tankers | 157 680 kl of water provided through water tankers | Number of Kilolitres of water provided throgh water tankers | 315 360 kl of water provided through water tankers | 105 120 kl of water provided through water tankers | 105 120 kl of water provided through water tankers | 52 560 kl of water provided through water tankers | Not achieved | 37 452 kl of water provided through water tankers | loadshedding affects and delays process of supplying water through tankers | Municipality to explore alternative energy sources. | Signed report | R5 200 000.00 | 4 over 6
BULK OPERATIONS
To Improved water quality compliance by June 2023 | Refurbishment of Groblersdal WTW | Dilapidated WTW | Number of WTW refurbished | 1 WTW (Groblersdal) refurbished | No activity | No activity | 1 WTW (Groblersdal) refurbished | Not Achieved | None | TOR rejected in the spec Committee - duplication of scope with DWS Contruction | Arrage a meeting with Design committee & DWS to resolve | Signed report | R3935 990.08
| Refurbishment of Praktiseer WTW | Dilapidated WTW | Number of WTW refurbished | 1 WTW (Praktiseer) refurbished | No activity | No activity | 1 WTW (Praktiseer) refurbished | Not Achieved | None | Awaiting for Appointment of PSP - Panel of consultant | Procure individually | Signed report | R4 000 000.00 | 0 over 2
PLANNING WATER SERVICE DEVELOPMENT PLAN
To develop feasibility study and technical report by June 2023 | Feasibility studies and technical reports - Praktiseer | New project | Number of feasibility studies and Technical reports developed | 1 feasibility study & 1 Technical report developed | Development of TOR & BID document | Advertisement & Appointment of PSP | 1 feasibility study & 1 Technical report developed | Not Achieved | None | Awaiting for Appointment of PSP - Panel of consultant | Urgently Appoint Professional Service Providers | Feasibility study & Technical report | 250000
| Feasibility studies and technical reports - Leeuwfontein | New project | Number of feasibility studies and Technical reports developed | 1 feasibility study & 1 Technical report developed | Development of TOR & BID document | Advertisement & Appointment of PSP | 1 feasibility study & 1 Technical report developed | Not Achieved | None | Awaiting for Appointment of PSP - Panel of consultant | Urgently Appoint Professional Service Providers | Feasibility study & Technical report | 250000
| Feasibility studies and technical reports - Monsterlus | New project | Number of feasibility studies and Technical reports developed | 1 feasibility study & 1 Technical report developed | Development of TOR & BID document | Advertisement & Appointment of PSP | 1 feasibility study & 1 Technical report developed | Not Achieved | None | Awaiting for Appointment of PSP - Panel of consultant | Urgently Appoint Professional Service Providers | Feasibility study & Technical report | 250000
| Feasibility studies and technical reports - Mapodile | New project | Number of feasibility studies & Technical reports developed | 1 feasibility study & 1 Technical report developed | Development of TOR & BID document | Advertisement & Appointment of PSP | 1 feasibility study & 1 Technical report developed | Not Achieved | None | Awaiting for Appointment of PSP - Panel of consultant | Urgently Appoint Professional Service Providers | Feasibility study & Technical report | 250000
| Feasibility studies and technical reports - Waalkraal RDP | New project | Number of feasibility studies & Technical reports developed | 1 feasibility study & 1 Technical report developed | Development of TOR & BID document | Advertisement & Appointment of PSP | 1 feasibility study & 1 Technical report developed | Not Achieved | None | Awaiting for Appointment of PSP - Panel of consultant | Urgently Appoint Professional Service Providers | Feasibility study & Technical report | 250000
| Feasibility studies and technical reports - Motetema | New project | Number of feasibility studies & Technical reports developed | 1 feasibility study & 1 Technical report developed | Development of TOR & BID document | Advertisement & Appointment of PSP | 1 feasibility study & 1 Technical report developed | Not Achieved | None | Awaiting for Appointment of PSP - Panel of consultant | Urgently Appoint Professional Service Providers | Feasibility study & Technical report | 250000 | 0 over 6
REGULATIONS & COMPLIANCE
To improve water service provisioning by June 2023 | Registration of servitutes | Water Services Infrustructure | Number of servitutes registered | 2 servitutes registered | Development of TOR & BID document | Advertisement & Appointment of PSP | 2 servitudes registered | Not Achieved | None | Awaiting for Appointment of PSP - Panel of consultant | Procure individually | Proof of registration | 2000000
To comply with regulations by June 2023 | AWARENESS CAMPAIGNS | New project | Number of awareness campains conducted | 8 awareness campains conducted | 2 awareness campains conducted | 2 awareness campains conducted | 2 awareness campains conducted | Not Achieved | None | Lack of capacity | Appointment of pease cops & compliance officers | Progress reports | 1500000
To comply with regulations by June 2023 | WATER USE LICENSE | 5 Water Use Licences in place | Number of Water Use Licences applied | 3 Water Use Licences applied | Development of TOR & BID document | Advertisement & Appointment of PSP | 3 Water Use Licences Applied | Not Achieved | None | Awaiting for Appointment of PSP - Panel of consultant | Procure individually | Proof of applications | 2000000
To review WSDP by June 2023 | WATER SERVICES DEVELOPMENT PLAN | Approved WSDP | Number of WSDP Reviewed | 1 WSDP Reviewed | Development of TOR & BID document | Advertisement & Appointment of PSP | Review WSDP | Not Achieved | PSP appointed by DWS for updating WSDP | Reviewing WSDP will take longer due to late appointment of PSP | PSP (Umlimi Consulting) has been appointed by DWS for Sekhukhune District municipality for the development of the 5 year reliability plan and updating WSDP. | Reviewed WSDP | R1 000 000.00 | 0 over 4
RURAL ROADS ASSET MANAGEMENT SYSTEM (RRAMS)
To develop Road Asset Management Plan by June 2023 | Development of Rural Roads Asset Management System | Desk top studies and the first rounds of Visual Conditions Assessments | Number of km of Roads assessed, traffic counting stations completed and Road Asset Management Plan developed. | 1 500km of Roads assessed, 200 traffic counting stations completed and 1 Road Asset Management Plan developed. | No Activity | 1 500km of Roads assessed. 50 traffic counting stations completed. | 200 traffic counting stations completed. 1 Road Asset Management Plan. | NOT ACHIEVED | 0 traffic counting stations completed. 1 Road Asset Management Plan. | Late appointment of service provider | Service provider to expedite implementation of project | Progress Reports | R2 451 000.00 | 0 over 1
REGIONAL BULK INFRASTRUCTURE GRANT (RBIG)
To reduce water services backlog with 90% by June 2024 | Construction of Mooihoek bulk water supply Phase G1.1 | 1 X 5 Ml concrete reservoir completed Phase 4BA | Number of km of bulk water supply pipeline and package plant constructed | 3 km of bulk bulk water supply pipeline and 1 package plant constructed | No Activity | 0,5 km of bulk pipeline constructed | 1,5 km of bulk pipeline and 1 package plant constructed | NOT ACHIEVED | 0 km of bulk pipeline and 0 package plant constructed (Site establishments and delivery of pipes ) | Delayed delivery of material on site.Procurement of nominated sub-contractor for the installations of the Package Plant | expedite construction | Progress Reports | R35 000 000.00
| Construction of Mooihoek bulk water supply Phase G1.2 | 2.4 Kilometers of bulk water supply pipeline constructed | Number of km of bulk pipeline constructed | 2,3 km of bulk water supply pipeline constructed | 1 km of bulk water supply pipeline constructed | 1,3 km of bulk water supply pipeline constructed | No activity | N/A | No activity | N/A | N/A | Progress Reports | R15 509 315.24
| Construction of Mooihoek bulk water supply Phase G2 | 5,3km Bulk pipeline constructed | Number of km of bulk water supply pipeline and 500kl reinfornced concrete reservoir constructed | 4,9 km of bulk water supply pipeline and reinfornced concrete reservoir constructed | 2 km of bulk pipeline constructed | 2,9 km of bulk pipeline and 1 concrete reservoir constructed | No activity | N/A | No activity | N/A | N/A | Progress Reports | R4 500 000.00
| Nebo BWS Commission Malekana to Jane Furse Pipeline | Nebo Phase1A completed and not commissioned | Number of Kilometres of bulk water supply pipeline tested & command resevoirs tested | 31 Kilometers of bulk water supply pipeline inspected 31 Kilometers of bulk water supply pipeline tested 1command resevoir tested | No Activity | No Activity | 31 Kilometres of bulk water supply pipeline tested & 1 command resevoir tested | Not Achieved | 0 Kilometres of bulk water supply pipeline tested & 0 command resevoir tested (Inception Report done) | Approval of the inception report | expedite testing | Progress Reports | 6000000
| Nebo BWS Makgeru to Schoonoord BWS | 18.2 Km of Schoonoord bulk water supply pipeline in Makgeru. 10ML Command Concrete Reservoir in Schoonoord constructed | Number of km of bulk pipeline constructed | 5km of bulk pipeline constructed | 1km of bulk pipeline constructed | 1km of bulk pipeline constructed | 1,5km of bulk pipeline constructed | Achieved | 2km of bulk pipeline constructed | None | None | Progress Reports | 34000000
| Moutse BWS Project (7 to 12) | 30 Kilometres of bulk water supply pipeline constructed and tested | Number of Kilometres of bulk water supply pipeline constrcuted and tested | 4 Kilometres of bulk water supply pipeline constrcuted and tested | 1,5 Kilometres of bulk water supply pipeline constructed and tested | 4 Kilometres of bulk water supply pipeline constructed and tested | 1 Kilometres of bulk water supply pipeline constructed and tested | Not Achieved | 1,4KM Complete | Current disruption from business forum Pipes burst during pressure testing/ funds needed to add more pipe material to replace the damaged or failed pipes | Resolve disputes or concerns by business forum Add amount of money needed to purchase extra pipes | Progress Reports | 55494716.05
| Moutse BWS Project 13 & 14 | 1 WTW in Groblersdal extended in Project 1 and 1 pump station constructed in Project 6 | Number of mechanical and Electrical (M & E) components installed for the extensions to the Groblersdal Water Treatment Works and pump station. Civil works for number of clarifier basin | 1 mechanical and Electrical (M & E) components installed for the extensions to the Groblersdal Water Treatment Works and pump station. Civil works for 1 clarifier basin done. | 1 Clarifier basin | 1 Filter basin | 1 electrical component installed for the extensions to the Groblersdal Water Treatment Works and pump station constructed | Achieved | 1 electrical component installed for the extensions to the Groblersdal Water Treatment Works and pump station. 1/2 Clarifier basin constructed | Current disruption from business forum | Resolve disputes or concerns by business forum | Progress Reports | 22346931 | 2 over 5
WATER SERVICES INFRASTRUCTURE GRANT (WSIG)
To reduce water service backlog with 90% by June 2023 | Tukakgomo Water Intervention Phase V | 3.5 km of pipeline and water abstraction point | Number of Kilometres of pipeline constructed, and number of water metres installed | 2,4 Kilometres of pipeline constructed, and 185 water metres installed | 0,5 km of pipeline constructed | 1,5 km of pipeline constructed | 185 house connections and Odex hole drilling, testing and equipping. | Not Achieved | 0 house connections and 0 Odex hole drilled, tested and equipped. | Validity period has expired for the appointment of the contractor. | Project to be re-advertised. | Progress Reports | R9 080 000.00
| Maebe Water Intervention Project – Phase IV | 4 kilometres of water pipeline and 2 boreholes completed | Number of Reverse Osmosis Plant and Wastage Line to specified discharge point constructed | 1 Reverse Osmosis Plant and 1 Wastage Line to speccified discharge point constructed | No activity | No activity | 1 Wastage Line to speccified discharge point constructed | Not Achieved | 0 Wastage Line constructed | Late appointment of service provider | To expedite work on site. | Progress Reports | R19 379 619.49
| Commissioning of Moutse bulk pipeline | Moutse bulk pipeline | Number of Pipeline Conditional assessed | 1 Pipeline Conditional assessed | No Activity | 1 Condition assessed | 1 conditional assessment | Not Achieved | Currently busy with conditional assesment report | Scoping challenges | Meeting to be arranged with the appointed PSP to resolve the matter. | Progress Reports | 10396729.21
| Phokwane/Brooklyn Water Supply | Business Plan | Number of Boreholes drilled, tested and equipped, and installattion of 80kl elevated seel tank. | 1 Borehole drilled, tested and equipped, installation of 80kl elevated steel tank. |  |  | Installation of 80kl elevated steel tank done | Not Achieved | 0 Installation of 80kl elevated steel tank | Validity period has expired for the appointment of the contractor. | Project to be re-advertised. | Progress Reports | 4471000
| Mabulela Water Supply | Business Plan | Number of Boreholes drilled, tested and equipped, and installattion of two 10kl elevated steel tanks and installation of diesel generator. | 1 Borehole drilled, tested and equipped, installation of two 10kl elevated steel tank and 1 diesel generator. |  |  | Installation of two 10kl elevated steel tank and diesel generator | Not Achieved | 1 Borehole drilled, tested and zero equipped, 0 installation of two 10kl elevated steel tank and 0 diesel generator installed. | Late appointment of the contractor. | To expedite work on site. | Progress Reports | 1625870
| Legolaneng VIDP Sanitation Project | Business Plan | Number of VIDP sanitation units constructed | 440 VIDP sanitation units constructed | 20 VIP sanitation units constructed | 130 VIP sanitation units constructed | 250 VIDP sanitation units constructed | Not Achieved | 206 pit excavation, 43 pit lining and 6 sanitation unit completed. | Late appointment of the contractor. | To expedite work on site. | Progress Reports | R7 500 000.00
| eNkosini Water Supply | Business Plan | Number of water treatment works refurbished, and km of reticulation network repaired. | Refurbishment of 1 package plant and repairing of 2km reticulation network. |  |  | Refurbishment 2km of reticulation network. | Not Achieved | Refurbishment 2km of reticulation network. | Late appointment of the contractor and the delay in finalisation of th PEP for 2023/24 FY | Project to be implemend in 2023/24 FY | Progress Reports | 6000000
| Ga-Marishane Village water supply | 1.1ML Reservoir and Water Treatment Plant | Number of boreholes equipped, and km of pipeline constructed | 2 Boreholes equipped and 3km pipeline constructed | No Activity | 1 Borehole equipped and 1km pipeline constructed | 1 Borehole equipped and 1km pipeline constructed | Not Achieved | None | No appointment of panel of professional service providers panel | Expedite the appointment of panel of service providers | Progress Reports | R4 656 710.32
MUNICIPAL INFRASTRUCTURE GRANT(MIG)
To Implement scope through tender contracting strategy by June 2023 | Motlailana and Makgemeng Water supply | 5,16 Kilometers bulk line constructed | Number of Km of bulk & reticulation pipeline , yard connections and concrete reservoirs constructed. | 16,5 Km of bulk & reticulation pipeline, 1304 yard connections and 2 concrete reservoirs constructed. | 12 Km of bulk & reticulation pipeline constructed. 1000 yard connections constructed. 1 concrete reservoir constructed. | 4,5 Km of bulk & reticulation pipeline constructed. 304 yard connections constructed. 1 concrete reservoir constructed. | 0 yard connections and 1 concrete reservoirs constructed | Not Achieved | 95 yard connections and 0 concrete reservoirs constructed. | Slow progress and poor cashflow management by the Contractor. | Contractor is currently on penalties | Monthly Progress Report | 21749214.05
| NSD07 Regional Water Scheme Construction of reservoirs | 13 Kilometres of bulk pipeline constructed; 3 reservoirs completed | Number of bulk pipelines constructed and concrete reservoirs completed | 3km of bulk pipelines constructed and 2 concrete reservoirs completed | 1km of bulk pipelines constructed and 1 concrete reservoirs completed | 2km of bulk pipelines constructed and 1 concrete reservoirs completed | 1km of bulk pipelines constructed and 2 concrete reservoirs completed | Not Achieved | 0km of bulk pipelines constructed and 0 concrete reservoirs completed | `Delays on the completion of project due to stoppages caused by community including SMMEs and business forums | SDM Senior management had meetings with the contractor and other stakeholders in June 2023 with the aim to unlock the project and recommendations are at advanced stages of approval | Monthly Progress Report | 4693759.56
| De Hoop/Nebo Plateau/Schoonoord Water Scheme Villages:Ga –Mogashoa (Senkapudi) and Ga- Mogashoa (Manamane) | 98,6 kilometres of water pipeline constructed | Number of water reticulation pipeline constructed | 2 kilometres of water pipeline constructed |  |  | 1,5 kilometres of water pipeline constructed | Not Achieved | 0 kilometres of water pipeline constructed | Delays on the completion of project due to insufficient material and stoppages on site caused by delayed payments to SMMEs and labourers | Contractor has since procured the outstanding material and anticipates delivery first week of July 2023. Office of the MMC currently intervening on issues relating to delayed payments and some payments has since been processed | Monthly Progress Report | 2175851.37
| De Hoop/ Nebo Plateau/ Schoonoord Water Scheme Villages: Makgeru, Ga Ratau and Matekane | 6 Kilometres of bulk pipeline constructed. & 60km 0f reticulation pipeline | Number of km of reticulation pipeline constructed, yard connections with water meters installed and borehole equipped | 38 km of reticulation pipeline constructed, 2000 of yard connections with water meters installed & 1 Borehole equipped | 9,5 km of reticulation pipeline constructed, 600 of yard connections with water meters installed | 9,5 km of reticulation pipeline constructed, 600 of yard connections with water meters installed & 1 Borehole equipped | 9,5 km of reticulation pipeline constructed, 200 of yard connections with water meters installed | Not Achieved | 0km of reticulation pipeline constructed,0 of yard connections with water meters installed | Project had stalled due to pending approval of a variation order for additional scope. | Variation orders have been approved. Contractors are back on site. New programme of works to inform the revised final completion date. | Monthly Progress Report | 13554104
| Malekana Regional Water Scheme | 14 kilometres of water pipeline and 4 reservoirs completed | Number of Km of reticulation and bulk pipeline constructed | 84,35 Km of reticulation and bulk pipeline constructed | No Activity | 20Km of reticulation and bulk pipeline constructed | 54.35Km of reticulation and bulk pipeline constructed | Achieved | 66,3Km of reticulation and bulk pipeline constructed | None | None | Monthly Progress Report | 123354717.48
| Lebalelo south connector pipes and Reticulation | 11 Steel tanks erected | Number of Steel tanks erected | 3 Steel tanks erected |  |  | 3 Steel tanks erected | Not Achieved | 0 Steel tanks erected | Steel tank sub contractor not on site. | The matter has been referred to Legal department to institute legal procedings against the sub contractor. | Monthly Progress Report | 8373757.24
| Lebalelo South Phase 3(Ga -Maroga & Motlolo) | 32,7 Kilometers of bulk line constructed & 6 Concrete Resevoir constructed | Number of Km of bulk and Km of reticulation pipeline constructed. Number of WTW constructed, boreholes refurbished & house water meters connected | 24km bulk,& 25,3km reticulation pipeline constructed, 3 refurbishment of boreholes, 1 WTW constructed and 912 house water meters connected | 6km of bulk & 6km reticulated pipeline construction & 155 house water meters connections | 6km of bulk & 2km reticulation pipeline constructed & 200 house water meters connections | 6km of bulk & 7km reticulation pipeline constructed, refurbishment of 1 borehole, 1 WTW and 230 house water meters connections | Not Achieved | 6,231km of bulk & 2,164 km reticulation pipeline constructed, refurbishment of 0 borehole, 1 WTW and 186 house water meters connections | Illegal mining activitiies happening around the area, damaging constructed pipes. There is too much rocks around the area. Under performance by contractors. | The matter has been referred to ISD to resolve together with the political principal for intervertion. Blasting is being carried out, in other areas the pipes is being changed to steel pipe. Close monitoring of contractors required | Monthly Progress Report | 67246488.89
| Upgrading of De Hoop WTW | Ga Malekana 12Ml Water Treatment Works | Number of sludge dams and pumps upgraded | 2 sludge dams, 3 pumps upgraded | No Activity | No Activity | 2 sludge dams and 3 pumps upgraded | Not Achieved | Project was re-advertised | Delayed appointments | Expedite appointment of a contractor | Monthly Progress Report | 82858243.59
| Upgrading of Groblersdal – Luckau Bulk Water Scheme Phase 1 | Groblersdal 12Ml Water Treatment Works | Number of Km of bulk pipeline constructed | 3Km of bulk pipeline constructed | No Activity | No Activity | 3km of bulk pipeline constructed | Not Achieved | 0km of bulk pipeline constructed | Delays in finalising the approval of SANRAL servitude | Decision has been taken to offset the pipeline route from SANRAL servitude and the consultant is currently busy negotiating with the property owners along the new proposed pipeline route. | Monthly progress report | 114702546
| Moutse East and West Water Reticulation | Groblersdal 12Ml Water Treatment Works | Number of Km of reticulation pipeline constructed | 21 Km of reticulation pipeline constructed | No Activity | No Activity | 21 km of reticulation pipeline constructed | Not Achieved | 0km of reticulation pipeline constructed | Project still on advert due to a delay in the submission of detail designs and tender documentation | Expedite the finalisation of detailed design and tender documentation. | Monthly progress report | 27169095.38
| Ga Maphopha Command Reservoir | Incomplete construction of Maphopha 5ML command reservoir | Percentage of Reservoir constructed | 100% Reservoir constructed |  |  | 50% Reservoir constructed | Not Achieved | 0% | Contractor and Consultant failing to provide an approval or an authorisation of claimed additional work. Two claims rejected due to lack of supporting documentation. | Resubmission of the application for approval of additional funds | Monthly progress report
COMMUNITY SERVICES
MUNICIPAL HEALTH SERICES
To conduct awareness campaigns on Environmental Pollution Prevention by June 2023 | Environmental Pollution Prevention | 25 Awareness Campaigns on Air Quality conducted | Number of Awareness Campaigns on Air Quality conducted | 24 Awareness Campaigns on Air Quality conducted | 6 Awareness Campaigns on Air Quality conducted | 6 Awareness Campaigns on Air Quality conducted | 6 Awareness Campaigns on Air Quality conducted | Achieved | 8 Awareness Campaigns on Air Quality conducted | None | None | Report and Attendance register | R424,528.00
To evaluate food premises by June 2023 | Food Safety control | 1567 Food Premises evaluated | Number of Food Premises evaluated | 1500 Food Premises evaluated | 375 Food Premises evaluated | 375 Food Premises evaluated | 375 Food Premises evaluated | Achieved | 375 Food Premises evaluated | None | None | Signed Assessment forms including the agent signature | R0.00
To monitor health care risk waste facilities by June 2023 | Waste Management | 112 Health care risk waste monitored | Number of Health care risk waste monitored | 100 Health care risk waste facilities monitored | 25 Health care risk waste facilities monitored | 25 Health care risk waste facilities monitored | 25 Health care risk waste facilities monitored | Achieved | 25 Health care risk waste monitored | None | None | Signed Assessment forms including the agent signature | R0.00
To evaluate health surveillance at public premises by June 2023 | Health Surveillance of premises | 1523 health surveillance at public premises evaluated | Number of health surveillance at public premises evaluated | 1500 health surveillance at public premises evaluated | 375 health surveillance at public premises evaluated | 375 health surveillance at public premises evaluated | 375 health surveillance at public premises evaluated | Achieved | 375 premises evaluated | None | None | Signed Assessment forms including the agent signature | R216,528.00
To conduct awareness campaigns on communicable diseases by June 2023 | Surveillance and prevention of communicable diseases | 116 awareness campaigns on Communicable diseases conducted | Number of awareness campaigns on Communicable diseases conducted | 100 awareness campaigns on Communicable diseases conducted | 25 awareness campaigns on Communicable diseases conducted | 25 awareness campaigns on Communicable diseases conducted | 25 awareness campaigns on Communicable diseases conducted | Achieved | 25 awareness campaigns on Communicable diseases held | None | None | Report and attendance register | R201 408.76
To investigate and trace all reported communicable disease outbreaks by June 2023 | Communicable diseases outbreak control | 279 communicable diseases outbreaks investigated and traced | Percentage of reported Communicable disease outbreaks investigated and traced | 100% reported Communicable disease outbreaks investigated and traced | 100% reported Communicable disease outbreaks investigated and traced | 100% reported Communicable disease outbreaks investigated and traced | 100% reported Communicable disease outbreaks investigated and traced | Achieved | No communicable disease cases reported | None | None | Reports | R341,559.92
To conduct inspection on vector control on premises by June 2023 | Vector Control | 1791 inspections on Vector Control on premises conducted | Number of inspections on Vector Control on premises conducted | 1500 inspections on Vector Control on premises conducted | 375 inspections on Vector Control on premises conducted | 375 inspections on Vector Control on premises conducted | 375 inspections on Vector Control on premises conducted | Achieved | 375 inspections on Vector Control on premises conducted | None | None | Signed Assessment forms including the agent signature
To inspect disposal of the dead facilities by June 2023 | Disposal of the dead | 107 Disposal of the dead facilities inspected | Number of inspections on Disposal of the Dead facilities conducted | 100 inspections on Disposal of the Dead facilities conducted | 25 inspections on Disposal of the Dead facilities conducted | 25 inspections on Disposal of the Dead facilities conducted | 25 inspections on Disposal of the Dead facilities conducted | Achieved | 25 evaluations on Disposal of the Dead facilities conducted | None | None | Signed Assessment forms including the agent signature
To evaluate chemical handling premises by June 2023 | Chemical safety | 354 chemical handling premises evaluations conducted | Number of evaluations on safety to chemical handling premises conducted | 300 evaluations on safety to chemical handling premises conducted | 75 evaluations on safety to chemical handling premises conducted | 75 evaluations on safety to chemical handling premises conducted | 75 evaluations on safety to chemical handling premises conducted | Achieved | 75 evaluations on safety to chemical handling premises conducted | None | None | Signed Assessment forms including the agent signature | R0.00
EMERGENCY MANAGEMENT SERVICES
To attend to all reported emergency incidents by June 2023 | Fire and Rescue Operations | 641 reported Emergency Services incidents attended | Percentage of reported emergency incidents attended | 100% reported emergency incidents attended | 100% reported emergency incidents attended | 100% reported emergency incidents attended | 100% reported emergency incidents attended | Achieved | 100% of (85) reported emergency incidents attended | None | None | Call Register and Report | R0.00
To facilitate firefighting courses by June 2023 | Emergency Management Services Training Academy | 3 firefighting training facilitated | Number of firefighting courses facilitated | 3 firefighting courses facilitated | 1 firefighting course facilitated | 1 firefighting course facilitated | 0 firefighting course facilitated | Achieved | Training of public students on Firefighter-1 is on course | None | None | Attendance Register and Report | R87,847.76
To provide fire prevention and safety services by June 2023 | Fire Safety and Prevention | 522 fire safety and prevention services provided. | Percentage of reported fire prevention and safety services provided | 100% reported fire prevention and safety services provided | 100% reported fire prevention and safety services provided | 100% reported fire prevention and safety services provided | 100% reported fire prevention and safety services provided | Achieved | 100% of (122) reported fire prevention and safety services provided | None | None | Call Register and Report | R0.00
DISASTER MANAGEMNET SERVICES
To conduct disaster risk management incidents by June 2023 | Disaster risk assessment | 188 reported disaster risk Management incidents conducted | Percentage of reported disaster risk Management incidents conducted | 100% reported disaster risk Management incidents conducted | 100% reported disaster risk Management incidents conducted | 100% reported disaster risk Management incidents conducted | 100% reported disaster risk Management incidents conducted | Achieved | 100% of (45) reported disaster risk managemement incidents conducted | None | None | Register of disaster risks assesssments | R500,000.00
To conduct disater risk reduction awareness campaign by June 2023 | Disaster risk reduction | 61 disaster risk reduction awareness campaigns conducted | Number of Disaster risk reduction awareness campaigns conducted | 24 disaster risk reduction awareness campaigns conducted | 6 disaster risk reduction awareness campaigns conducted | 6 disaster risk reduction awareness campaigns conducted | 6 disaster risk reduction awareness campaigns conducted | Achieved | 14 disaster risk reduction awareness campaigns conducted | None | None | Register of risk reduction awareness campaigns
To provide disaster relief materials to affected disaster victims by June 2023 | Disaster response and recovery | 250 blankets and 120 mattrasses of relief material to all affected disaster victims coordinated. | Percentage of reported disaster relief materials provided to affected disaster victims | 100% reported disaster relief materials provided to affected disaster victims | 100% reported disaster relief materials provided to affected disaster victims | 100% reported disaster relief materials provided to affected disaster victims | 100% reported disaster relief materials provided to affected disaster victims | Achieved | 100%of (45) reported disaster risk managemement incidents conducted | None | None | Register of relief materials provided and report
To review disaster management plan and framework by June 2023 | Disaster management plan and framework review | 1 Disaster management plan and framework reviewed | Number of disaster management plan and framework reviewed | 1 disaster management plan and framework reviewed | Stakeholder consultation | Stakeholder consultation | 1 disaster management plan and framework reviewed and submitted to Council structures for approval | Achieved | Disaster Management Plan and Framework reviewed and submitted to Council Structures | None | None | Reviewed disaster management plan and framework | R23,801.44
To coordinate campaigns on special high density days by June 2023 | Special Operations on High Density Day | 03 special operations on high density days campaigns conducted | Number of special high density days campaigns coordinated | 3 special operations on high density days campaigns coordinated | No Activity | 2 special operations high density campaigns coordinated | 1 special operations high density campaigns coordinated | Achieved | 1 special operations high density campaigns coordinated | None | None | Operational plan and attendance registers | R90,816. 96