## Sheet1
MEASURABLE OBJECTIVES | PROJECT | BASELINE 2015/2016 | INDICATORS | ANNUAL TARGET 2016-2017 | Q4 TARGET | PROGRESS (Achieved/not achieved) | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTIONS | EVIDENCE | BUDGET 2016-2017
PLANNING, REGULATION & GOVERNANCE
To develop 20% O&M Management Plan and Systems developed by June 2017 | Operations and Maintenance Management Plan and Systems | Incomplete GIS data, Assets register, TOR and tender documentation | Percentage of plans and systems developed | 20% O&M Management GIS based Plan and Systems developed | 20% O&M Management GIS based Plan and Systems developed | Not Achieved | Appointment of PSP to develop O & M Plan GIS based | Inadequate budget | Budget be available in 2017/18 financial year | O & M Plan | 200000
To apply for 2X Water Infrastructure Servitudes by June 2017 | Application of Water Infrastructure Servitudes at Moutse bulk water pipeline, Burgersfort reservoir Moooihoek phase 4B | Incomplete GIS data, Assets register, TOR and water services infrastructure | Number of Water Infrastructure Servitudes applied for Moutse bulk water pipeline, Burgersfort reservoir Mooihoek phase 4B | 2x Water Infrastructure Servitudes applied for Moutse bulk water pipeline, Burgersfort reservoir Mooihoek phase 4B | 2x Water Infrastructure Servitudes applied for Moutse bulk water pipeline, Burgersfort reservoir Mooihoek phase 4B | Not Achieved | Methodology and Status quo report on SDM servitude | Inadequate budget | Budget be available in 2017/18 financial year | Inception report, Application Methodology and assessment report | 200000
To develop 10% Integrated water systems by December 2016 , Motetema and Leeuwfontein | Integrated water system plan, Motetema and Leeuwfontein | Availability of water infrastructure & regular Water Supply | Percentage integrated water systems developed for Motetema and Leeuwfontein | 10% ntegrated water system Approved by Council, Motetema and Leeuwfontein | 10% ntegrated water system Approved by Council, Motetema and Leeuwfontein | Achieved | Status quo report and assessment of Leeufontein and Motetema reticulations | No funds to implement engineer recommendations | Technical report to be submitted to DWS for approval for MIG Funds | Status quo development report | 1300000
To review Service level agreements (SLAs) by June 2017 (2x LNW, 1X JS Moroka, 1X Ohrigstad, 1X Burgersfort) | Service level agreements (SLAs) with water service providers WSPs reviewed | Existing & draft SLAs | Number of SLAs reviewed. | 5x SLAs reviewed 2x LNW, 1X JS Moroka, 1X Ohrigstad, 1X Burgersfort) | 4 x reviewed WSP SLAs signed | Not Achieved | 3 x SLAs reviwed and signed | Lack of Co-operation from the Ohrigstad WSP | Legal intervention required | Signed Service Level Agreements | 0
To review 100% Water Services By-Law by June 2017 | Water Services By-Law | Water & Sanitation By-Law | Percentage of By-Law reviewed | 100% Water Services By-Law reviewed | Promulgated reviewed Water Service By-Law | Not Achieved | Draft reviewed Water By-Law approved by Council | Public consultation not finalised | Draft reviewed Water-Law to be taken for consultation | Promulgated by-law | 300000
To develop 100% Water Services Tariff Structure Determination Policy by June 2017 | Water Services Tariff Structure Determination Policy | Tariff structure | Percentage development of Water Services Tariff Determination Policy | 100% development of water services tariff determination policy | 100% development of water services tariff determination policy | Achieved | Draft water tariff determination policy. | Public consultation not finalised | Draft water tariff determination policy. | Council Approved Policy | 200000
To develop x2 Water Safety & Waste Water Abatement plans developed by June 2017 | Water Safety & Waste Water Abatement plans | WTW; WWTW & Bulk Water pipelines | Number of Water Safety & Waste Water Abatement plans developed | 2x Council approved Water Safety & Waste Water Abatement plans | 2x Council approved Water Safety & Waste Water Abatement plans | Achieved | Draft Water Safety Plan and Waste Water Risk Abetement Plan |  |  | Council approved Plans | 450000
To facilitate development of x7 Technical Reports by June 2017 Lebalelo Central, Lebalelo south, Madibong, Ga-Mogashoa, Maloma, Piet Gouws, Gaphaahla-Lobethal-Marishane | Water technical reports | Panel of consultants in place | Number of Technical report approved | 7 x Technical reports facilitated x Lebalelo Central , South south, Madibong, Ga-Mogashoa, Maloma, Piet Gouws, Gaphaahla-Lobethal-Marishane Technical report approved | 7 x Approved Technical reports | Not Achieved | 6 x Approved Technical Report. | Water Source development. Completion of Nebo Plateau BWS ( Commissioning of Ga Malekan to Jane Furse command reservoir bulk pipeline). | Budget for forward planning. Experdite the commissioning of Nebo Plateau BWS | DWS Approval letters | 6000000
To undertake 100% Groblersdal Bulk Sewer study by June 2017 | Groblersdal Bulk Sewer study | PSP appointed from panel of consultants | Percentage study of Groblersdal Bulk Sewer undertaken | 100% study of Groblersdal Bulk Sewer undertaken | 100% studies of Marblehall bulk sewer line | Achieved | Marblehall bulk sewer line study report. | No funds available to implement engineer,s recommendation | Budget to be made available to implement engineer report recommendation. | Study report and preliminary report | 250000
PROJECT MANAGEMENT UNIT (MIG)
To achieve 100% of MIG annual budget spend by 30 June 2017 | Capital Grant Expenditure | 90% MIG expenditure | % MIG expenditure | 100% of MIG Expenditure | 100 % expenditure | Achieved | 100% expenditure | Withdrawal of funds by Treasury Department that led to non payment of service providers for May and June 2017 | All outstanding payments to be paid in July 2017 | MIG reports submitted to Council | 331184000
To construct 15 180 VIP Toilets by 30 June 2017 (Ephraim Mogale= 2700,Elias Motsoaledi = 3000, Makhuduthamaga = 3590, Fetakgomo = 2460, Tubatse = 3430) | VIP backlog eradication Phase 2 | 52504 | Number of VIP Sanitation units constructed | 15180 VIP Sanitation toilets completed (Ephraim Mogale= 2700,Elias Motsoaledi = 3000, Makhuduthamaga = 3590, Fetakgomo = 2460, Tubatse = 3430) | 3 795 VIP Sanitation toilets completed (Ephraim Mogale= 675 ,Elias Motsoaledi = 750, Makhuduthamaga = 898, Fetakgomo = 615, Tubatse = 858) | Achieved | Ephraim Mogale =725, Elias Motsoaledi =1359 , Makhuduthamaga= 615, Fetakgomo =1015, Tubatse =1096 Total= 4810 | Budget reduction of R56million impacted on the financial commitment which the municipality has with PSPs and Cessionary holders for the remainder of 2016/17. | Process all outstanding payments in July 2017 | Progress report | 151972427.41
To finalize 100% construction of Zaaiplass water reticulation by March 2017. | Zaaiplaas Connector pipes from Bulk to villages incl. reservoirs (Khathazweni, Rondebosh,Kosini,Mathula,Khathazweni,Areaganeng,Jeije,Sehlakwane,Elandslaagte and Dindela) | Village reticulation with communal stand pipes below RDP level. | % Construction of Zaaiplass Connector Pipes. | 100% construction of Zaaiplass water reticulation (Construction reservoirs 100%; bulk line 100%). | 0% | Not achieved | Contract B Overall progress to date is at 3%. The 3 reservoirs are 74% complete. Contract A-Overall progress is at 6%. All 4 reservoirs (210, 80, 80 &80 KL) are completed. | Contract B- The community stopped the reservoir contractor because they want the labourers to be hired on a rotational basis.Contract A-The contractor has a delay of the supply of reservoir fittings. | Contract B- The contractor to utilize rotation system of employment to cover the list of employment. Contract A-70% of fittings are delivered and the balance to be delivered by June 2017. | Completion report | 10106514.33
To finalize to 100% construction of Carbonatites to Zaaiplaas BWS by December 2016 | Carbonatites to Zaaiplaas BWS (phase 2) | Bulk line at 95%. Pump Station constructed at 94%; Reservoir constructed at 10%. | % Construction of Reservoir, Pipeline, Pump Station | 100% construction of Dindela Reservoir, 100% construction of bulk pipeline, 100% construction of pump station. | 0% | Not achieved | 3.8Ml Dindela reservoir- Physical progress is at 35 % and contract intention to termination letter sent, waiting for 14 days to lapse before finalizing the termination processes. Pump Station-Notice of intension to amend the contract or agreement in terms section 116 (3) of the MFMA finalized, | 3.8 Mℓ Dindela Reservoir Project to be termination due to poor performance. Pump Station Variation order to be approved by bid committees for amended scope of works. | 3.8 Mℓ Dindela Reservoir Advertise new contract by June 2017 and continue project in 2017/18.Pump Station Variation order to be approved by June 2017 and project to be continued in 2017/18 financial year | Completion report | 269348.82
To construct 100% of Tafelkop Reticulation and Cost Recovery by June 2017 | Tafelkop Reticulation and Cost Recovery | Dysfunctional communal stand pipes; Storage; supply lines that are damaged due to illegal connections. | % Construction of Tafelkop Reticulation and Cost Recovery | 100% Tafelkop Reticulation and Cost Recovery Constructed | 20% Tafelkop Reticulation and Cost Recovery Constructed | Not achieved | Projects overall Progress 5%.Pipe laid 19,9 km of 75mm dia =87%.54,516 km of 110 mm dia = 90% | Lepelle NW was expected to refurbish and commission the bulk line to Nkadimeng and the command Reservoir.Some of the uPVC lines must be converted to Steel pipeline and this will affect the cost of the project. | Meeting with Lepelle Northern Water to be arranged to provide clarity on refurbishment scheme.Apply for budget maintenance with COGSTA. Motivate the utilization of contingencies for items with change of specification | Completion report | 16963767.11
To construct 100% of Sekwati Reticulation upgrade Phase 4 by June 2017 | Sekwati Reticulation upgrade Phase 4 | Boreholes; Pump line; Concrete reservoirs; water distribution line, 32 stand pipes. | % Construction of Sekwati Reticulation upgrade Phase 4 | 100% Construction of Sekwati Reticulation upgrade Phase 4 | 20% Construction of Sekwati Reticulation upgrade Phase 4 | Not achieved | overall progress is 5% | 1. Application for extension of time to 23 July has been submitted. 2. Repetitive vandalism on the completed works, might affect the hand over. | . Approve the extension of time application | Completion report | 10719363
To construct 100% of Ga Moloi Water Supply water supply by June 2017. | Ga Moloi area and surrounding villages water supply (contract B and C) | Inadequate Storage; dysfunctional reticulation network, Communal taps below | % Construction of reticulation lines at Morgenzon and Stad Van Masleroem; Gravity main, installation of street taps. | 100% Construction of reticulation lines at Morgenzon and Stad Van Masleroem; Gravity main, installation of street taps. | 30% Construction of reticulation lines at Morgenzon and Stad Van Masleroem; Gravity main, installation of street taps | achieved | overall progress is 48% | None | None | Progress report | 37168349.53
To finalize 80% Nkadimeng: Phase 9 to 11 (Makhuduthamakga) - Ditlabaneng, Letlhabile,Tshatane, Sebetsane, Kgoalane & MAtsebenge) Phase 11A | Nkadimeng: Phase 9 to 11 (Makhuduthamakga) - Ditlabaneng, Rampelane, Matsebeng, Sebetsane, Kgoalane, Mathibeng, Dinotsi, Matolokwane) | Nkadimeng WTW, Command Reservoir, reticulation and bulk line below RDP level. | % Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 80% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 30% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | Not achieved | 17% overall progress | Social issues that delayed the project for months | requires intervention of MMC | Monthly reports | 7404178.15
To implement 100% Borehole Refurbishment Southern Zone by June 2017 | Olifantspoort Contract 21 : Borehole Refurbishment Southern | Non-functional boreholes | % Completion of boreholes developed and Refurbishment Southern Zone | 100% Implementation of borehole Refurbishment Southern Zone | 30% Implementation of borehole Refurbishment Southern Zone | Not achieved | Overall progress 0% | Cashflow problem and budget reduction | Process all outstanding payments in July 2017 | Monthly Progress Report | 4399518.49
To implement 100% Borehole Refurbishment Nothern Zone by June 2017 | Olifantspoort Contract 22 : Borehole Refurbishment Northern | Non-functional boreholes | % Completion of boreholes developed and Refurbishment Northern Zone | 100% Implementation of borehole Refurbishment Northern Zone | 25% Implementation of borehole Refurbishment Northern Zone | Not achieved | Overall progress 8% | Cashflow problem and budget reduction | Process all outstanding payments in July 2018 | Monthly Progress Report | 3657048.46
To construct 100% and Completion of Reservoir Ga – Nchabeleng 2, Makopa, Ga-Seroka and Sesehu and WDM Structures | Olifantspoort Contract 23 : Completion of Reservoir Ga – Nchabeleng 2, Makopa, Ga-Seroka and Sesehu and WDM Structures | Water supply below RDP level | % Completion of Reservoir ga – Nchabeleng 2, Makopa, Ga seroka and Sesehu and WDM Structures | 100% Completion of Reservoir ga – Nchabeleng 2, Makopa, Ga seroka and Sesehu and WDM Structures | 0% | achieved | Overall progress = 0% | Contractor delayed with finalization of snag list items. | Commissioning will be done in the second week of July 2017 | Monthly Progress Report | 2617579.38
To construct 100% of bulk water reticulation in Mooiplaas and Strydkraal Supplement by June 2017. | Olifantspoort Contract 24 : Bulk (Mooiplaas and Strydkraal Supplement) | Water supply below RDP level | % Completion of bulk water reticulation in Mooiplaas and Strydkraal Supplement | 100% Completion of bulk water reticulation in Mooiplaas and Strydkraal Supplement | 30% Completion of bulk water reticulation in Mooiplaas and Strydkraal Supplement | Not achieved | Overall progress 5% | The Tribal Authority of Strydkraal area is not in favour of the residents settling in their area sitting that they are there illegally and have stopped the project to install supply of electricity by Eskom. In retribution therefore, the Tribal Authority of Mashung/ Nchabeleng area has stopped the Water project in their area as the pipe route passes along their area to the reservoir.” | Contractually the project will be suspended and according to GCC which governs the contract, we have 84 days to resolve the matter before the contractor can go back to site. The matter has been reported to the MMC for urgent intervention | Monthly Progress Report | 6543936.31
To construct 100% Nkadimeng: Phase 9 to 11 Fetakgomo) Ga-Mmela to Mashilavele, Ga-Pahla, Molapong, Ga-Magolego, Mankontu and Masehleng by June 2016. Phase 10 | Nkadimeng: Phase 9 to 11 (Fetakgomo) Ga-Mmela to Mashilavele, Ga-Pahla, Molapong, Ga-Magolego, Mankontu and Masehleng | Nkadimeng WTW, Command Reservoir, reticulation and bulk line below RDP level. | % Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 100% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 0% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | achieved | Overall progress at 17%. | none | none | Monthly reports | 39501606.64
To construct 100% Command Reservoir, pump station and pipelines at GaMaphopha by June 2017. | Ga - Maphopha Command Reservoir | Water supply below RDP level | % completion of Command Reservoir, pump station and pipelines | 100% completion of Command Reservoir, pump station and pipelines | 10% testing and commissionning | Not achieved | overall progress is 2% | budget reduction impacted on the financial commitment which the municipality has with PSPs and Cessionary holders for the remainder of 2016/17. | Process payments in July 2017 | Monthly reports | 10485398.27
To provide 4320 Praktiseer households with Water Reticulation by June 2017. | Praktiseer Water Reticulation | Reticulation, Stand Pipes, Distribution lines(Booster Pump Station, High lift Pump station,WTW to be refurbished) | Number of households provided with water | 4320 households provided with water. | 4320 households provided with water. | Not achieved | Litigation | Litigation | Resolve the letigation | Monthly reports | 699250.87
To construct 100% reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa by June 2017. | Ga-Malekane , Masha upgrade and extended reticulation | Reticulation Network provided below RDP level. | % completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa. | 100% completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa. | 20% completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa. | Not achieved | Overall progress= 5% | Contractor expected to finish outstanding work as soon as the VO is approved. Eskom delaying electrifying the boreholes | Expedite approval of VO by the municipality. Way leave agreement form submitted to electrify at least one of the boreholes in Malekana | Monthly reports | 10452868.75
To finalise 100% Technical report, MIS registration, Designs and Tender documents for Ga-Mashabela water reticulation by June 2017 | Ga Mashabela Water Reticulation | Approved DWS Technical reports | 100% MIS project registration, detailed design and tender tender stage | 100% Technical report, MIS registration, Designs and Tender documents for Ga-Mashabela water reticulation by June 2017 | 100% Technical report, MIS registration, Designs and Tender documents for Ga-Mashabela water reticulation by June 2017 | Achieved | Draft documents presented in the design committee and Bid Specification Committee(BSC) | none | none | Copy of Tender Documents | 811011.68
To finalise 100% Technical report, MIS registration, Designs and Tender documents for Ga-Marishane water reticulation by June 2018 | Ga- Marishane Water Reticulation | Approved DWS Technical reports | 100% MIS project registration, detailed design and tender tender stage | 100% Technical report, MIS registration, Designs and Tender documents for Ga-Marishane water reticulation by June 2018 | 100% Technical report, MIS registration, Designs and Tender documents for Ga-Marishane water reticulation by June 2018 | Achieved | Draft documents presented in the design committee and Bid Specification Committee(BSC) | none | none | Copy of Tender Documents | 0
To finalise 100% Technical report, MIS registration, Designs and Tender documents for Maloma and surrounding villages water reticulation by June 2019 | Maloma and Surrounding Water Reticulation | Approved DWS Technical reports | 100% MIS project registration, detailed design and tender tender stage | 100% Technical report, MIS registration, Designs and Tender documents for Ga-Mashabela water reticulation by June 2019 | 100% Technical report, MIS registration, Designs and Tender documents for Ga-Mashabela water reticulation by June 2019 | Achieved | Tender advertised and closed in March 2017 | addendum issued a day before closure therfore project needs to be readvertised | Finalize the re-advertisement by July 2017 | Copy of Tender Documents | 332174.82
To finalise 100% Technical report, MIS registration, Designs and Tender documents for Lobethal water reticulation by June 2020 | Lobethal Water Supply | Approved DWS Technical reports | 100% MIS project registration, detailed design and tender tender stage | 100% Technical report, MIS registration, Designs and Tender documents for Maloma and surrounding villages water reticulation by June 2020 | 100% Technical report, MIS registration, Designs and Tender documents for Maloma and surrounding villages water reticulation by June 2020 | Achieved | Tender advertised and closing on 13 June 2017. | None | None | Copy of Tender Documents | 369415.94
To finalise 100% Technical report, MIS registration, Designs and Tender documents for Ga-Phaahla water reticulation by June 2021 | Ga- Phaahla water supply | Approved DWS Technical reports | 100% MIS project registration, detailed design and tender tender stage | 100% Technical report, MIS registration, Designs and Tender documents for Ga-Phaahla water reticulation by June 2021 | 100% Technical report, MIS registration, Designs and Tender documents for Ga-Phaahla water reticulation by June 2021 | Achieved | Tender advertised and closing on 13 June 2017. | None | None | Copy of Tender Documents | 634845.85
To finalise 100% Technical report, MIS registration, Designs and Tender documents for Lebalelo South water reticulation by June 2022 | Lebalelo south connector pipes | Approved DWS Technical reports | 100% MIS project registration, detailed design and tender tender stage | 100% Technical report, MIS registration, Designs and Tender documents for Lebalelo South water reticulation by June 2022 | 100% Technical report, MIS registration, Designs and Tender documents for Lebalelo South water reticulation by June 2022 | Achieved | tender to be advertised | None | None | Copy of Tender Documents | 3457656
PROJECT MANAGEMENT UNIT (RBIG & WSIG)
To develop 20% O&M Management Plan and Systems developed by June 2017 | Operations and Maintenance Management Plan and Systems | Incomplete GIS data, Assets register, TOR and tender documentation | Percentage of plans and systems developed | 20% O&M Management GIS based Plan and Systems developed | 5% Development of O & M Management Plan.( Conditional assessment of Elias Motsoaledi WTW and WWTW) plants, Development of inseption report, Development of status quo report) | Not achieved | PSP's has been appointed. | Appointment processess of PSP's took long. | Project to be handed-over to Cluster Managers to run the projects and make inputs. | O & M Plan | 200000
To apply for 2X Water Infrastructure Servitudes by June 2017 | Application of Water Infrastructure Servitudes at Moutse bulk water pipeline, Burgersfort reservoir Moooihoek phase 4B | Incomplete GIS data, Assets register, TOR and water services infrastructure | Number of Water Infrastructure Servitudes applied for Moutse bulk water pipeline, Burgersfort reservoir Mooihoek phase 4B | 2x Water Infrastructure Servitudes applied for Moutse bulk water pipeline, Burgersfort reservoir Mooihoek phase 4B | 0 |  |  |  |  | Application Methodology | 200000
To develop 10% Integrated water systems by December 2016 , Motetema and Leeuwfontein | Integrated water system plan, Motetema and Leeuwfontein | Availability of water infrastructure & regular Water Supply | Percentage integrated water systems developed for Motetema and Leeuwfontein | 10% ntegrated water system Approved by Council, Motetema and Leeuwfontein | 5% integrated water system developed (Status quo development) |  |  |  |  | Status quo development report | 1300000
To review Service level agreements (SLAs) by June 2017 (2x LNW, 1X JS Moroka, 1X Ohrigstad, 1X Burgersfort) | Service level agreements (SLAs) with water service providers WSPs reviewed | Existing & draft SLAs | Number of SLAs reviewed. | 5x SLAs reviewed 2x LNW, 1X JS Moroka, 1X Ohrigstad, 1X Burgersfort) | Review 2x LNW Serice Level Agreement |  |  |  |  | Signed Service Level Agreements | 0
To review 100% Water Services By-Law by June 2017 | Water Services By-Law | Water & Sanitation By-Law | Percentage of By-Law reviewed | 100% Water Services By-Law reviewed | 25% Review of the by-law and promulgation |  |  |  |  | Promulgated by-law | 300000
To develop 100% Water Services Tariff Structure Determination Policy by June 2017 | Water Services Tariff Structure Determination Policy | Tariff structure | Percentage development of Water Services Tariff Determination Policy | 100% development of water services tariff determination policy | 25% development of water services tariff determination policy |  |  |  |  | Approved Policy | 200000
To develop x2 Water Safety & Waste Water Abatement plans developed by June 2017 | Water Safety & Waste Water Abatement plans | WTW; WWTW & Bulk Water pipelines | Number of Water Safety & Waste Water Abatement plans developed | 2x Council approved Water Safety & Waste Water Abatement plans | Status Quo Determination |  |  |  |  | Council approved Plans | 450000
To facilitate development of x7 Technical Reports by June 2017 Lebalelo Central, Lebalelo south, Madibong, Ga-Mogashoa, Maloma, Piet Gouws, Gaphaahla-Lobethal-Marishane | Water technical reports | Panel of consultants in place | Number of Technical report approved | 7 x Technical reports facilitated x Lebalelo Central , South south, Madibong, Ga-Mogashoa, Maloma, Piet Gouws, Gaphaahla-Lobethal-Marishane Technical report approved | 2 x Technical reports facilitated x Marishane, Ga-Maloma, Gaphaahla-Marishane and Lobethal Technical report approved |  |  |  |  | DWS Approval letters | 6000000
To undertake 100% Groblersdal Bulk Sewer study by June 2017 | Groblersdal Bulk Sewer study | PSP appointed from panel of consultants | Percentage study of Groblersdal Bulk Sewer undertaken | 100% study of Groblersdal Bulk Sewer undertaken | 25% Surveying of exsting sewer network | Not achieved | The PSP has submitted the close-out report, waiting for further instructions to start with CCTV survey of the network. | Not enough budget for CCTV survey work | Give instructions to the PSP's to proceed with the survey work. The current budget to be adjusted during the budget adjustment. | Study report and preliminary report | 250000
PROJECT MANAGEMENT UNIT
To achieve 100% of MIG annual budget spend by 30 June 2017 | Capital Grant Expenditure | 90% MIG expenditure | % MIG expenditure | 100% of MIG Expenditure | 25% MIG expenditure |  |  |  |  | MIG reports submitted to Council | 457984000
To construct 15 180 VIP Toilets by 30 June 2017 (Ephraim Mogale= 2700,Elias Motsoaledi = 3000, Makhuduthamaga = 3590, Fetakgomo = 2460, Tubatse = 3430) | VIP backlog eradication Phase 2 | 52504 | Number of VIP Sanitation units constructed | 15180 VIP Sanitation toilets completed (Ephraim Mogale= 2700,Elias Motsoaledi = 3000, Makhuduthamaga = 3590, Fetakgomo = 2460, Tubatse = 3430) | 3 795 VIP Sanitation toilets completed (Ephraim Mogale= 675 ,Elias Motsoaledi = 750, Makhuduthamaga = 897, Fetakgomo = 615, Tubatse = 857) |  |  |  |  | Completion report | 210 444 000
To finalize 100% construction of Zaaiplass water reticulation by March 2017. | Zaaiplaas Connector pipes from Bulk to villages incl. reservoirs (Khathazweni, Rondebosh,Kosini,Mathula,Khathazweni,Areaganeng,Jeije,Sehlakwane,Elandslaagte and Dindela) | Village reticulation with communal stand pipes below RDP level. | % Construction of Zaaiplass Connector Pipes. | 100% construction of Zaaiplass water reticulation (Construction reservoirs 100%; bulk line 100%). | construction at 20% |  |  |  |  | Completion report | 17 713 105
To finalize to 100% construction of Carbonatites to Zaaiplaas BWS by December 2016 | Carbonatites to Zaaiplaas BWS (phase 2) | Bulk line at 95%. Pump Station constructed at 94%; Reservoir constructed at 10%. | % Construction of Reservoir, Pipeline, Pump Station | 100% construction of Dindela Reservoir, 100% construction of bulk pipeline, 100% construction of pump station. | 10%Testing and commissioning |  |  |  |  | Completion report | 5 019 826
To construct 100% of Tafelkop Reticulation and Cost Recovery by June 2017 | Tafelkop Reticulation and Cost Recovery | Dysfunctional communal stand pipes; Storage; supply lines that are damaged due to illegal connections. | % Construction of Tafelkop Reticulation and Cost Recovery | 100% Tafelkop Reticulation and Cost Recovery Constructed | 20% Tafelkop Reticulation and Cost Recovery Constructed |  |  |  |  | Completion report | 23 355 182
To construct 100% of Sekwati Reticulation upgrade Phase 4 by June 2017 | Sekwati Reticulation upgrade Phase 4 | Boreholes; Pump line; Concrete reservoirs; water distribution line, 32 stand pipes. | % Construction of Sekwati Reticulation upgrade Phase 4 | 100% Construction of Sekwati Reticulation upgrade Phase 4 | 10% Construction of Sekwati Reticulation upgrade Phase 6 |  |  |  |  | Completion report | 17 847 059
To construct 100% of Ga Moloi Water Supply water supply by June 2017. | Ga Moloi area and surrounding villages water supply (contract B and C) | Inadequate Storage; dysfunctional reticulation network, Communal taps below | % Construction of reticulation lines at Morgenzon and Stad Van Masleroem; Gravity main, installation of street taps. | 100% Construction of reticulation lines at Morgenzon and Stad Van Masleroem; Gravity main, installation of street taps. | 20% Construction of reticulation lines at Morgenzon and Stad Van Masleroem; Gravity main, installation of street taps. |  |  |  |  | Completion report | 47 000 000
To finalize 80% Nkadimeng: Phase 9 to 11 (Makhuduthamakga) - Ditlabaneng, Letlhabile,Tshatane, Sebetsane, Kgoalane & MAtsebenge) Phase 11A | Nkadimeng: Phase 9 to 11 (Makhuduthamakga) - Ditlabaneng, Rampelane, Matsebeng, Sebetsane, Kgoalane, Mathibeng, Dinotsi, Matolokwane) | Nkadimeng WTW, Command Reservoir, reticulation and bulk line below RDP level. | % Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 80% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 10% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. |  |  |  |  | Monthly reports | 8 822 744
To implement 100% Borehole Refurbishment Southern Zone by June 2017 | Olifantspoort Contract 21 : Borehole Refurbishment Southern | Non-functional boreholes | % Completion of boreholes developed and Refurbishment Southern Zone | 100% Implementation of borehole Refurbishment Southern Zone | 20% Implementation of borehole Refurbishment Southern Zone |  |  |  |  | Monthly Progress Report | 13 000 000
To implement 100% Borehole Refurbishment Nothern Zone by June 2017 | Olifantspoort Contract 22 : Borehole Refurbishment Northern | Non-functional boreholes | % Completion of boreholes developed and Refurbishment Northern Zone | 100% Implementation of borehole Refurbishment Northern Zone | 25% Implementation of borehole Refurbishment Northern Zone |  |  |  |  | Monthly Progress Report | 13000000
To construct 100% and Completion of Reservoir Ga – Nchabeleng 2, Makopa, Ga-Seroka and Sesehu and WDM Structures | Olifantspoort Contract 23 : Completion of Reservoir Ga – Nchabeleng 2, Makopa, Ga-Seroka and Sesehu and WDM Structures | Water supply below RDP level | % Completion of Reservoir ga – Nchabeleng 2, Makopa, Ga seroka and Sesehu and WDM Structures | 100% Completion of Reservoir ga – Nchabeleng 2, Makopa, Ga seroka and Sesehu and WDM Structures | 5% Completion of Reservoir ga – Nchabeleng 2, Makopa, Ga seroka and Sesehu and WDM Structures |  |  |  |  | Monthly Progress Report | 4 000 000
To construct 100% of bulk water reticulation in Mooiplaas and Strydkraal Supplement by June 2017. | Olifantspoort Contract 24 : Bulk (Mooiplaas and Strydkraal Supplement) | Water supply below RDP level | % Completion of bulk water reticulation in Mooiplaas and Strydkraal Supplement | 100% Completion of bulk water reticulation in Mooiplaas and Strydkraal Supplement | 20% Completion of bulk water reticulation in Mooiplaas and Strydkraal Supplement |  |  |  |  | Monthly Progress Report | 6 760 000
To construct 50% of water reticulation in Ga selepe, Monametsi, Mosotsi and Paschas by June 2017. | Olifants Contract 25 Sec Dist (Ga Selepe, Monametsi, Ga Mokg., Ga Manot. Mosotsi & Paschas.) | Water supply below RDP level | %Completion of water reticulation in Ga selepe, Monametsi, Mosotsi and Paschas | 50 % Completion of water reticulation in Ga selepe, Monametsi, Mosotsi and Paschas | 15% completion of water reticulation in Ga-Selepe, Monamedi (Design approval and tender stage completion) |  |  |  |  | Progress Report | 3 770 000
To construct 100% Nkadimeng: Phase 9 to 11 Fetakgomo) Ga-Mmela to Mashilavele, Ga-Pahla, Molapong, Ga-Magolego, Mankontu and Masehleng by June 2016. Phase 10 | Nkadimeng: Phase 9 to 11 (Fetakgomo) Ga-Mmela to Mashilavele, Ga-Pahla, Molapong, Ga-Magolego, Mankontu and Masehleng | Nkadimeng WTW, Command Reservoir, reticulation and bulk line below RDP level. | % Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 100% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 40% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. |  |  |  |  | Monthly reports | 39 900 707
To construct 100% Command Reservoir, pump station and pipelines at GaMaphopha by June 2017. | Ga - Maphopha Command Reservoir | Water supply below RDP level | % completion of Command Reservoir, pump station and pipelines | 100% completion of Command Reservoir, pump station and pipelines | 25% completion of Command Reservoir, pump station and pipelines |  |  |  |  | Monthly reports | 12047266
To provide 4320 Praktiseer households with Water Reticulation by June 2017. | Praktiseer Water Reticulation | Reticulation, Stand Pipes, Distribution lines(Booster Pump Station, High lift Pump station,WTW to be refurbished) | Number of households provided with water | 4320 households provided with water. | 0 households provided with water. |  |  |  |  | Monthly reports | 5 401 785
To construct 100% reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa by June 2017. | Ga-Malekane , Masha upgrade and extended reticulation | Reticulation Network provided below RDP level. | % completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa. | 100% completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa. | 15% completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa. |  |  |  |  | Monthly reports | 14 901 566
To complete 100% of the commissioning of Nebo Phase 1A by June 2017 | Nebo De Hoop Phase 1 A BWS | GaMalekana WTW, Pump Station 1 & 2, Regional Bulk line, 10ML Reservoir | Percentage Completion of commissioning of GaMalekana to Jane Furse Bulk line. | "100% Completion of commissioning of GaMalekana to Jane Furse Bulk line, VO approval, application fee payment, and pumpstation 1&2 upgrade | 40% Completion of commissioning of GaMalekana to Jane Furse Bulk line,rising main and pumpstation 1&2. | Not Achieved | 0% Pumpstation 1& 2 upgrade to 4MWa. VO approved by DWS on 31 March 2017 subject to SDM following their SCM processes | VO was finalized on the 20th June 2017, Letters were sent last week onte 30th June 2017 | Contractor to submit new program to resume with the commissioning | Progress Report | 8000000
To complete 100% of the Extension to Groblersdal WTW Project by June 2017. | Moutse BWS - Extension to Groblersdal WTW Project 1 | 18ML/Day WTW | Percentage completion of Extension to Groblersdal WTW Project 1 | "*100% Completion of Manhole Chambers. * 100% installation of fittings*100% Completion of Raw Water Extraction Chambers. * 100% Completion on floculation channels, Clarifiers & Sand Filters. *100% Completion of Clear Water Pumping Station. Testing and Commissionin | *5% Overall Completion *Completion of Manhole Chambers. * 100% installation of fittings*100% Completion of Raw Water Extraction Chambers. * 100% Completion on floculation channels, Clarifiers & Sand Filters. *100% Completion of Clear Water Pumping Station. * 5*Testing and Commissioning. | Not Achieved | Overall progress : 97%. *Manhole Chambers 100% *Raw water extraction chamber & associated pipe work :100% *Raw water inlet channel : 100% *Flocculation channels, clarifiers & sand filter: 100% *Clear water pumping station : 94% | *Mechanical and Electrical must be completed first. The remaining civil works depends on the M&E components. | *Consultants was requested a recovery plan showing financial implication for both professional fees and construction. | Progress Report | 20038195
To complete 100% of 6, 72 km pipeline with a diameter of 250 mm from Groblersdal West Reservoir to Elandsdroon Reservoir by June 2017. | Moutse BWS - 6, 72 km pipeline with a diameter of 250 mm from Groblersdal West Reservoir to Elandsdroon Reservoir- Project 5 | 6,72 km bulk pipeline constructed. | Percentage Completion of Moutse BWS - 6, 72 km pipeline with a diameter of 250 mm | "*100% Completion of Manhole Chambers. * 100% installation of fittings | *100% Completion of Manhole Chambers. * 20% installation of fittings | Not Achieved | Overall progress : 77% *Manhole Chambers Excavations : 96% *Floor Slabs : 96% *Walls : 95% *Roof Slabs : 53% *Connections and Fittings : 96% *Pressure testing sections (1-5) : 0% *(Manhole Chamber, Connections,Pressure Testing outstanding). | *Pipeline traversing on private land delayed project. * Shortage of skilled personnel. | Consultants was requested a recovery plan showing financial implications for both professional fees and constructor | Progress Report | 24206580
To complete 100% of 60km pipeline with diameters 600mm,400mm and from Mzimdala/Uitspanning to Moutse West by June 2017. | Moutse BWS - Gravity pipeline from Mzimdala/Uitspanning to Moutse West- Project 7 to 12 | 60 km bulk pipeline constructed. | % completion of 60 km Bulk supply line from Mzimdala/Uitspanning to Moutse West | "*100% completion of 60 km Gravity pipeline to Motse west * 100% installation of chambers and fittings * Testing and commissioning | *15% completion of 60 km Gravity pipeline to Motse west * 100% installation of chambers and fittings * Testing and commissioning | Not Achieved | Project 7 : 88% Project 8 : 95% Project 9 : 84% Project 10: 0% Project 11 : 57% Project 12 :52% Overall pipe laying progress : 100% Overall chambers and fittings:62% Overall progress of project 7-12: 74% | *Progress on project 10 delayed by land claims. Farmers extended their boundaries along the pipeline route. Access is minimized. | Consultants was requested a recovery plan showing financial implication for both professional fees and constructor | Completion Certificate | 15109827
To complete 100% of Mechanical & Electrical work for WTW Project 13 by June 2017. | Moutse BWS :Mechanical & Electrical for WTW -Project 13 | Groblersdal WTW | % Completion of installation of M&E for Groblersdal WTW | 100% Installation of pumps and electrical fittings and Testing and Commissioning" | *100% Installation of pumps and electrical fittings. Testing and Commissioning | Not Achieved | Overall progress : 86% *Raw water pump station : 100% *Installation of pumps: 100% *Electrical fittings: 100% *Clear water pump station : 78% *Installation of pumps: 100% *Electrical fittings: 73% Booster pump station : 90% Pump Installation:100% Electrical fittings: 79% | *Suppliers payments delays Impacted on the contractors programme. | Consultants was requested a recovery plan showing financial implecation for both professional fees and constructor | Progress Report | 20588301
[6 empty] | Not Achieved | Overall progress : 86% *Raw water pump station : 100% *Installation of pumps: 100% *Electrical fittings: 100% *Clear water pump station : 78% *Installation of pumps: 100% *Electrical fittings: 73% Booster pump station : 90% Pump Installation:100% Electrical fittings: 79% | *Suppliers payments delays Impacted on the contractors programme. | Consultants was requested a recovery plan showing financial implecation for both professional fees and constructor |  | 32057097
To complete 100% of Mechanical & Electrical work for Groblersdal West Pump Station by June 2017. | Moutse BWS: Mechanical & Electrical for Groblersdal West Pump Station- Project 14 | Groblersdal West Pump Station | % Completion of M&E for Groblersdal West Pump Station | "*100% delivery of pumps and electrical fittings. | *100% Installation of pumps and electrical fittings. Testing and Commissioning | Not Achieved | Overall progress : 86% *Raw water pump station : 100% *Installation of pumps: 100% *Electrical fittings: 100% *Clear water pump station : 78% *Installation of pumps: 100% *Electrical fittings: 73% Booster pump station : 90% Pump Installation:100% Electrical fittings: 79% | *Suppliers payments delays Impacted on the contractors programme. | Consultants was requested a recovery plan showing financial implecation for both professional fees and constructor | Progress Report | 15000000
To Construct 30% of phase 4BA 5 Ml reservoir in Burgersfort by June 2017. | Mooihoek BWS - Phase 4BA 5 Ml reservoir in Burgersfort | Reservoir at 19% | % Completion of 5ML Reservoir | "30% Construction of phase 4BA 5 Ml reservoir in Burgersfort and testing and commissioning | *10% Casting of reservoir wall and Construction of inlet & outlet pipes and fittings. | Achieved | *Overall progress is at 95% *The outstanding works entails inlet & outlet pipelaying @ 88%, manhole chambers @ 73%. *Testing and Commissioning 0% *Completion Date:31 May 2017 | *Instruction was issued for redoing of the work due to poor finishings. | * Contractor was able to source skilled workers to assist.Remedial progressing as per Engineer's instruction. | Progress Report | 92000000
To Construct 80% of 1.1km 650m DIA and 500m of 450 DIA Steel Water Pipeline, 3LPE, Coated and cement Mortar lined | Mooihoek Tubatse BWS Phase 4C1:1,1km 650mm DIA and 500m 0f 450mm DIA Steel Water Pipeline | 2,7km BWS constructed to Burgersfort Phase 4A | % completion of 1.1km 650m DIA and 500m of 450 DIA Steel Water Pipeline% | 80% completion of 1.1km 650m DIA and 500m of 450 DIA Steel Water Pipeline | 80% completion of 1.1km 650m DIA and 500m of 450 DIA Steel Water Pipeline | Achieved | *Overall Progress is 98%. *Pipe laying at 100% 500mm Ø, *750mm Ø at 100% completion. *The manhole chambers at 100% *Fittings at 20%. *Completion Date: 31 May 2017 | None | None | Progress Report | 2069000
To construct 80% of 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe line by June 2017. | Mooihoek Tubatse BWS Phase 4C1.2: 400m 0f 650mm DIA and 900m 0f 450mm DIA Steel Water Pipeline | 2,7km BWS constructed to Burgersfort Phase 4A | % completion of 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe | 80% completion of 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe | *20% completion of 1.1km 650m DIA and 500m of 450 DIA Steel Water Pipeline. *20% Completion of Manhole Chambers and Fittings. | Not Achieved | *Overall completion is 25% *Excavation for pipe laying of 750mmØ 41% * Manhole chambers 65% *Completion Date:15 Oct 2016 | *No Contractor on site. *Safety is a serious concern. * Open excavation barricading stolen. | Terminated | Progress Report | 4000000
To construct 66% Mooihoek Tubatse Phase4C1.3 road crossing using pipe jacking method by June 2017 | Mooihoek Tubatse BWS 4C 1.3: Pipe jacking | 2,7km BWS constructed to Burgersfort Phase 4A | Percentage of road crossings constructed | 66 % Completion of Mooihoek Tubatse BWS Phase4C1.3 Pipe Jacking 1 road crossings on R555, Motageng constructed * Procurement of contractor * Clearing and setting of side * Excavation for jerking and delivery of pipes * Completion and stabilation of loose areas | *15% Overall Completion of Road crossings. * Jacking at Road R555 at Apies. * Jacking at Road R555 at Fire Station. * Jacking at Road R555 to Penge Junction. *Jacking Railways crossin) | Achieved | *Overall Progress is 100% * The remaining crossing is at 80%. *Completion Date:31 May 2017 | None | None | Progress Report | 3500000
To Construct 30% of Mooihoek/ Tubatse Bulk Water Supply Phase 4D: 3500m,650mm DIA and1500, 450mm DIA Steel Water Pipeline by June 2017. | Mooihoek/ Tubatse Bulk Water Supply Phase 4D: 3500m,650mm DIA and1500, 450mm DIA Steel Water Pipeline, 3LPE, Coated and cement Mortar lined | 2,7km BWS constructed to Burgersfort Phase 4A | % Construction of 3500m,650mm DIA and1500, 450mm DIA Steel Water Pipeline | "30% of Mooihoek/ Tubatse Bulk Water Supply Phase 4D: 3500m,650mm DIA and1500, 450mm DIA Steel Water Pipeline, Installation of chambers and fittings | "10% of Mooihoek/ Tubatse Bulk Water Supply Phase 4D: 3500m,650mm DIA and1500, 450mm DIA Steel Water Pipeline, Installation of chambers and fittings | Achieved | *The overall progress is 100% completed. *Completion Date:31 October 2016 | None | None | Monthly Progress Report | 5000000
To Construct 40% of Mooihoek Tubatse 4C2:2700m, 500mm DIA and 2600m,400mm DIA Steel Water Pipeline by June 2017. | Mooihoek Tubatse 4C2 :2700, 500mm DIA and 2600,400mm DIA Steel Water Pipeline, 3LPE, Coated and cement Mortar lined | 2,7km BWS constructed to Burgersfort Phase 4A | % Construction of 2700m, 500mm DIA and 2600, 400mm DIA Steel Water Pipeline. | "40% Construction of Mooihoek Tubatse 4C2:2700, 500mm DIA and 2600, 400mm DIA Steel Water Pipeline, Installation of chambers fittings | *10% Overall Completion (40% Installation of pipe and welding of joints. *20% Construction of Concrete Chambers & Fittings) | Achieved | *The overall progress is 80% completion. *Steel pipe installation & welding joints for 400mm Ø is 91%. *Steel pipe installation & elding joints for 500mm Ø is 83%. *Manhole chambers 58%. *Fittings 20% *Completion Date:31 May 2017 *Manhole chambers 44%. *Completion Date: 31 Oct 2016 | *Slow progress. * Cashflow problems. | * Subcontractor to assist with installation of fittings is appointed. | Progress Report | 3200000
To Complete 20% of 21km of Pipeline from Jane Furse to Lobethal by June 2017. | Jane Furse to Lobethal BWS | 80% completed Bulk water supply line at from Jane Furse to Lobethal | % Completion of Bulk water supply line from Jane Furse to Lobethal. | 20% Completion of Pipeline from Jane Furse to Lobethal,Completion of valve chambers | 5% Completion of Pipeline from Jane Furse to Lobethal,Completion of valve chambers | Not Achieved | *85% of construction completed. *Outstanding Work: 400m of pipeline, 14 scour valves, 2 air valves, 5- take off valves, 1 gate valve and testing. Completion Date: To be confirmed upon approval of the submitted variation order. | *Termination by contractor. *Lack of sufficient funds to complete the project. |  | Progress Report | 3500000
To construct 80% of 5.0km pipeline, 10ML Reservoir for Makgeru to Schoonoord by June 2017. | Makgeru to Schoonoord BWS | Water supply below RDP level | % Completion of Pumping line and reservoir | " 80% construction of 5.0km pump line, 10ML Reservoir for Makgeru to Schoonoord | * 20% construction of reservoir. * Pumpline & Gravity main. | Achieved | *Overall progress is 47%. *Reservoir is at 51% *Pipelne is at 43% | * Social related project delays. *Frequent disruptions and non payment of PSP. | *Plan to recover the lost time to be submitted. | Progress Report | 3500000
To develop 100% Road Asset Management System by June 2017 | Rural Roads Assets Management System | Draft RRMS | % development of Road Asset Management System | 100% Development of Roads Asset Management System | 20% Development of Roads Asset Management System | Not Achieved | 15% Development of Roads Asset Management System | Finalise the budget and envolvement of Local Municipalities | enagage the Department and all Local Municipalities | Progress Report | 2120000
To construct 296 VIDP units at Ga-Moretsele by June 2017 | Ga – Moretsele VIDP project | Sanitation below RDP. | Number of VIDP Sanitation units constructed | 296 VIDP units constructed at Ga-Moretsele | 40 VIDP units constructed | Achieved | *95% Physical Progress on site and 20 unit to be signed off. | *None | *None | Progress Report | 4000000
To construct 100% of 3500m of 75mm diameter reticulation network and 1200m of 90mm diameter rising main with four Jojo Tanks by June 2017 | WSIG - GTLM Thokwane borehole equipping and reticulation | Inadequate water source & Water infrastructure not covering entire area | %, length of 75mm diameter reticulation network, 90mm diameter rising main and four Jojo Tanks installed | 100% of 3500m of 75mm diameter reticulation network and 1200m of 90mm diameter rising main with four Jojo Tanks constructed at Thokwane | 10% Submission of technical report to DWS and approvals.Detail designs and drawings, appointment contractors. | Not Achieved | *At procurement stage | Business Plans and Scoping Report submitted late | To fast tract the appointment of the contractor. | Colse-up report | 3500000
To Install two new pumps and motors, one Chlorine system, Inlet and outlet meters by June 2017 | WSIG-GTLM Praktiseer ext water supply extensions. | Dilapidated infrastructure | Number of new pumps, motors and Chlorine system, Inlet and outlet meters installed | 2 new pumps and motors, one Chlorine system, Inlet and outlet meters installed at Praktiseer WTW. | Procurement of new pumps, motors and Chlorine system, inlets and outlet meters | Not Achieved | *Scope of work was revised and the physical progress is at 50%. | late appointment of the contractor. | To fast tract the construction. | Colse-up report | 5000000
To, construct 100% of 1800m of 75mm diameter reticulation network, 800m of 90mm diameter rising main with four Jojo Tanks by June 2017 | WSIG - ELM Vlakfontein borehole equipping and reticulation | Inadequate water source & Water infrastructure not covering entire area | % water source developed, length of 75mm diameter reticulation network, 90mm diameter rising main and number of Jojo Tanks installed. | 100% of 1800m of 75mm diameter reticulation network, 800m of 90mm diameter rising main with four Jojo Tanks constructed at Vlakfonten | 10% Submission of technical report to DWS and approvals.Detail designs and drawings, appointment contractors. | Not Achieved | *Scoping Report was submitted and there is no source in the area. | There is no source in the area. | To establish alternative source first. | Colse-up report | 3200000
To, construct 100% of 3800m of 75mm diameter reticulation network, 1200m of 90mm diameter rising main and install one 100kl eleveted steel tank by June 2017 | WSIG - ELM Magagamatala borehole equipping and reticulation | Inadequate water source & Water infrastructure not covering entire area | % water source developed, lenth of 75mm diameter reticulation network, 1200m of 90mm diameter rising main and number of 100kl eleveted steel tank installed | 100% of 3800m of 75mm diameter reticulation network, 1200m of 90mm diameter rising main and install one 100kl eleveted steel tank at Magagamatala | 10% Submission of technical report to DWS and approvals.Detail designs and drawings, appointment contractors. | Achieved | *90% physical progress on site. | None | None | Colse-up report | 3500000
To construct 100% of 1200 length of 90mm diameter from the by-pass bulk water from maroteng to matsemela and Install of 150kl elevated steel tank by June 2017 | WSIG - FTLM Ga-Photo bulk water supply | Water infrastructure not covering entire area | % Length of 90mm diameter from the by-pass bulk water from maroteng to matsemela constructed and number of 150kl elevated steel tank installed. | 100% of 1200 length of 90mm diameter from the by-pass bulk water from maroteng to matsemela and Install of 150kl elevated steel tank at Ga-Photo. | 10% Submission of technical report to DWS and approvals.Detail designs and drawings, appointment contractors. | Not Achieved | *33% physical progress on site and the steel stank delivered on site and steel pipes delivered. | Late introduction of the contractor to the community | To fast tract the construction process | Colse-up report | 3 500 000,00
To construct 100% of 3000m of 90mm diameter from the college reservoir to mabopo village by June 2017 | WSIG - FTLM Mabopo village water supply | Water infrastructure not covering entire area | % Length of 90mm diameter from the college reservoir to Mabopo village constructed | 100% of 3000m of 90mm diameter from the college reservoir to Mabopo village constructed at Mabopo | 10% Submission of technical report to DWS and approvals.Detail designs and drawings, appointment contractors. | Achieved | *90 physical progress on site and the contractor is busy with the final touch ups. | *Late submission of scoping report and BP . *Late introduction of the contractor to the community | To fast tract the construction process | Colse-up report | 3800000
To, construct 100% of 3800m of 75mm diameter reticulation network ,1200m of 90mm diameter rising main and install one 100kl elevated steel tank by June 2017 | WSIG - FTLM Phashamakgalanoto borehole equipping and reticulation. | Inadequate water source & Water infrastructure not covering entire area | %, Length of 3800 of 75mm diameter reticulation network, 1 90mm diameter rising main and number 100kl elevated steel tank installed. | 100% of 3800m of 75mm diameter reticulation network ,1200m of 90mm diameter rising main and installa one 100kl elevated steel tank at Phashamagalanoto. | 100% of 3800m of 75mm diameter reticulation network ,1200m of 90mm diameter rising main and installa one 100kl elevated steel tank at Phashamagalanoto. | Not Achieved | *At Procument stage | Late appointment of the contractor. | To fast tract the appointment of the PSP | Colse-up report | 4500000
To construct 40% of 2000m rising main line to existing storage | WSIG - MKLM Thabampshe water supply | Inadequate water source & Water infrastructure not covering entire area | %, Length of 2000m rising main line to existing storage constructed | 40% of 2000m rising main line to existing storage at Phaahla (Mamoshalela) | 40% of 2000m rising main line to existing storage at Phaahla (Mamoshalela) | Not Achieved | * The appointed Consultant quited job and the project is implemented internally and at the procurement stage. | *Late implementation of the Project. | *To fast tract the appointment of the contractor. | Memo for the requisition of the payment of the contractor. | 3700000
To complete Borehole development, construction of 1 800m and 2400m reticulation network. Installation 50kl elevated steel tank. | WSIG - MKLM Ga-Komane village water supply. | Inadequate water source & Water infrastructure not covering entire area | % of Borehole development, construction of 1 800m and 2400m reticulation network. Installation 50kl elevated steel tank. | 40% complete Borehole development, construction of 1 800m and 2400m reticulation network. Installation 50kl elevated steel tank. | 40% complete Borehole development, construction of 1 800m and 2400m reticulation network. Installation 50kl elevated steel tank. | Not Achieved | * The appointed Consultant is busy with the Scoping Report and Geohydrologist went to site for Ground Investigation. | * Late Re-appointment of the Consultant. | *To fast tract the finalising of the Scoping Report. | Monthly Progress Report | 2200000
To construct 100% of 1,2km rising main by June 2017 | WSIG - MKLM MANTHLANYANE BOREHOLE EQUIPPING | Inadequate water source & Water infrastructure not covering entire area | % length 0f 1,2km rising main constructed. | 100% of 1,2km rising main constructed at Manthlanyane. | 10% Construction | Achieved | *95% physical completion on site and the project on the commisioning stage. | None | None | Register for Briefing Csseion | 4000000
To construct 100% of 3000m length of 75mm diameter pipeline and connect to elevated steel tank by June 2017 | WSIG - EMLM Rathoke ext of water reticulation network | Water infrastructure not covering entire area | % Length of 3000m of 75mm diameter pipeline and connect to elevated steel tank constructed | 100% of 3000m length of 75mm diameter pipeline and connect to elevated steel tank constructed at Rathoke | 60% Construction | Not Achieved | *25% physical progress on site. | Delays in the procumenent of the land for the Booster pump station. | To fast tract the construction process | Register for Briefing Csseion | 3500000
To refurbish 100% existing infrastructure and complete abundant water reticulation project by June 2017 | WSIG - EMLM Leeuwfontein water reticulation refurbishment | Dilapidated infrastructure. | % of Existing infrastructure refurbished, abundant reticulation project completed | 100% of Existing infrastructure refurbished, abundant reticulation project completed at Leeufontein | 40% Construction | Achieved | *55% physical progress on site. | none | none | Monthly Progress Report | 4100000
To construct 100% of 2 500m length of 65mm diameter pipeline and installation of steel tank by June 2017 | WSIG - ELM Mzemdala (zaaiplaas) borehole equipping and reticulation | Inadequate water source & Water infrastructure not covering entire area | % of length 2500m of 65mm diameter pipeline and steel tank installed. | 100% of 2 500m length of 65mm diameter pipeline and installation of steel tank at Mzemdala (Zaaiplaas) | 60% Construction | Not Achieved | *18% physical progress and the equipping of the borehole in progress. | Contractor behind in progress | To fast track the construction progress. | Colse-up report | 3500000
To construct 100% of 3800m of 75mm diameter reticulation network ,1200m of 90mm diameter rising main and install four Jojo tank by June 2017 | WSIG - MKLM GA-Moretsele ( new section) water supply | Inadequate water source & Water infrastructure not covering entire area | %, length of 75mm diameter reticulation network , 90mm diameter rising main and number Jojo tank installed | 100% of 3800m of 75mm diameter reticulation network ,1200m of 90mm diameter rising main and install four Jojo tank at Moretsele | 60% Construction | Not Achieved | *At procurement stage | late appointment of the contractor. | To fast track the construction progress. | Register for Briefing Csseion | 3000000
To construct 100% of one 200kl elevated steel tank and the 3000m length of 65mm diameter pipeline June 2017 | WSIG - FTLM Mohlaletsi (maroteng) water supply | Inadequate storage & Water infrastructure not covering entire area | % of 200kl elevated steel tank and length of 65mm diameter pipeline constructed | 100% of 200kl elevated steel tank and the 3000m length of 65mm diameter pipeline at Mohlaletsi | 40% Construction | Not Achieved | *At procurement stage | late appointment of the contractor. | To fast track the appointment of the contractor | Register for Briefing Csseion | 3000000
To construct 100% of 1500mm of 75mm diameter pipe line by June 2017 | WSIG-EMLM Mooihoek Tsimanyane water supply extensions. | infrastructure not covering entire area | % pipe line constructed at Mooihoek Tsimanyane | 100% 1500mm pipe line constructed at Mooihoek Tsimanyane | 40% Construction | Achieved | * 95% Physical Progress on site and to commission the projects few weeks to come. | None | None | Monthly Progress Report | 1500000
OPERATION & MAINTENANCE AND SCIENTIFIC SERVICES
To resolve 90 % registered sanitation incidents within 14 days. | Repairs and maintanance (Turn around time for sanitation incidents response) | 90% registered sanitation incidents | Percentage of incidents resolved within 14 days | 90% registered sanitation incidents resolved within 14 days | 90% registered sanitation incidents resolved within 14 days | Achieved | 100% registered sanitation incidents resolved within 14 days | None | None | Incident Reports | R25 000 000
To resolve 90% registered water incidents within 14 days. | Improve respond time to water incidents | 90% registered water incidents | Percentage of incidents resolved within 14 days | 90% registered incidents resolved within 14 days | 90% registered incidents resolved within 14 days | Achieved | 91% registered incidents resolved within 14 days | Shortage of material | Bulk purchase of material at stores | Incident Reports
To ensure 100% provision of electricity to all SDM water and sanitation connections consistently | Electricity supply for water and sanitation connections (Bulk electricity purchase) | 6 million Kwh | % of 6 million Kwh of annual electricity demand supplied | 100% of 6 million Kwh of annual electricity demand supplied | 100% of 1,5 million Kwh of annual electricity demand supplied | Not Achieved | 41% of 616 962 million Kwh of annual electricity demand supplied | Continuous theft and vandalism; delayed invoice payments leading to cut off by eskom, Delay of readings for capturing | Secure the infrastructure;conduct community awereneses, | Electricity consumption report | R32 000 000
To provide 100% bulk water to consumers consistently by June 2017 | Bulk water supply to reservoirs). | 10 062Mℓ of bulk water supplied. | % of annual water volume supplied | 100% of annual water volume supplied | 25% of 2 515.5Mℓ of annual water volume supplied | Achieved | 114% of annual water volume supplied (2 875 697 Mℓ) |  |  | Monthly meter readings report | R95 160 450
To provide 80 000ℓ diesel consistently to diesel driven machines by June 2017 | Diesel supply | 80 000ℓ of diesel supplied | Litres of diesel supplied annually | 80 000ℓ of diesel supplied annually. | 20 000ℓ of diesel supplied annually. | Not Achieved | 11 517ℓ of diesel supplied annually. | More pumps and motors are converted to electricity | None | Fuel consumption report | R1 879 350
To provide 1200ℓ Petrol consistently to petrol driven machines by June 2017 | Petrol supply | 5000ℓ petrol supplied | Litres petrol supplied annually. | 1200ℓ of petrol supplied annually. | 300ℓ of petrol supplied annually. | Not Achieved | 268ℓ of petrol supplied annually. | More pumps and motors are converted to electricity | None | Fuel consumption report
To provide 720ℓ Oil consistently to diesel and petrol driven machines by June 2017 | Oil supply | 1500ℓ of oil supplied | Litres of oil supplied annually. | 720ℓ of oil supplied annually. | 180ℓ of oil supplied annually. | Achieved | 249.9ℓ of oil supplied annually. | More pumps and motors are converted to electricity | None | Fuel consumption report
To improve water quality status | Undertake Full SANS Water Quality Analysis(Laboratories & Chemicals) | draft CSIR SLA | Number of Full SANS 241 analysis done | 1 Full SANS 241 analysis done | Contract signed by all stakeholders on CSIR SLA | Achieved | Draft contract developed and submitted to both parties for signatures | Awaiting comments from CSIR legal division | Expedite signing of the contract by Oct 2016 | Council approved Fulls SANS 241 report | R13 000 000
| Undertake SANS Compliance Water Quality Analysis | 1000 | No of water samples analysed | 1200 water samples analysed | 300 water samples analysed | Not Achieved | 251 samples analysed | Vacany created in Fetakgomo | Fill vacant water quality officer position in Fetakgomo by October 2016 | Council approved Water Quality Reports
| Water Quality Reports to Council | 10 | No of water quality reports submitted | 12 water quality reports submitted | 3 water quality reports submitted | Achieved | 1 quarterly report submitted | None | None | Council approved Water Quality Reports
To develop 100% sanitation master plan by June 2017 | Sanitation Master Plan | 2007 Sanitation Strategy | % development of sanitation masterplan | 100% development of sanitation master plan | 20% Development of Sanitation Master Plan ( status Quo analysis) | Achieved | Draft 25% Sanitation Master plan developed. | Inadequate budget to develop 100% Sanitation Master Plan. | Budget to be made available to complete sanitation master plan. | Council approved Bulk Sanitation Master Plan | 250000
To generate 100% air quality reports by June 2017 | Air Quality Management | 100% quarterly Air quality reports generated | Percentage reports of air quality generated. | 100% reports on air quality generated | 100% reports on air quality generated | Achieved | 100% reports on air quality generated. | None | None | Reports | 674300 | Clean environment
To undertake 204 water quality samples by June 2017 | Water quality monitoring | None | Number of water quality samples taken | 204 water quality samples taken | 51 water samples taken | Not achieved | No water samples taken | Insufficient budget | Budget to be increased | Reports | 81000 | clean, safe, healthy and sustanable environment
To ensure 100 evaluation of food safety in premises by June 2017 | Food Safety Control | 100 Certificate of Acceptability | Number of food premises evaluated | 100 food premises evaluated | 25 food premises evaluated | Achieved | 26 Food premises evaluated | None | None | close up reports | R64000.00 (World Food Day) | Low prevalence of food related complaints
To undertake health surveillance of 1200 premises by June 2017 | Health surveillance of premises | 500 Health surveillance of premises evaluated | Number of premises surveilled | 1200 premises surveilled (e.g Creches) | 300 premises surveilled | Achieved | 316 premises surveilled | None | None | Reports | R0. 00 | Safe and Health Environment in the Dsitrict
To undertake 100% survaillance and prevention of notifiable communicable diseases by June 2017 | Surveillance and prevention of communicable diseases | 20 Surveillance undertaken for detection of communicable diseases | Percentage surveillance undertaken | 100% surveillance and prevention of communicable disease undertaken | 100% surveillance and prevention of communicable disease undertaken | Achieved | 100% surveillance and prevention of communicable disease undertaken. | None | None | Reports | R0. 00 | Improved stae of communicable diseases
To undertake 1200 vector control evaluation by June 2017 | Vector Control | 20 vector control evaluation undertaken | Number of vector control evaluations undertaken | 1200 vector control evaluation undertaken (e.g Health facilities) | 300 vector control evaluations undertaken | Achieved | 467 Vector control evaluations undertaken | None | None | Reports | R0. 00 | vector free environment
To undertake 408 chemical safety awareness campaigns by June 2017 | Chemical Safety | 20 chemical safety awareness campaigns conducted | Number of chemical safety awareness campaigns conducted | 408 chemical safety awareness campaigns conducted | 102 chemical safety awareness campaigns conducted | Achieved | 156 Chemical safety awareness campaigns conducted. | None | None | Reports | R0. 00 | Improved environmental management in the district
To monitor waste management in 102 health care facilities by June 2017 | Waste management | 20 Monitoring Health Care Risk Waste | Number of waste management in Health Care facilities monitored | 102 waste management in Health Care facilities monitored | 26 waste management in Health Care facilities monitored | Achieved | 32 Waste management in Health Care facilities monitored | None | None | Reports | R0. 00 | Safe and Health Environment in the Dsitrict
To evaluate disposal of the dead on 50 facilities by June 2017 | Disposal of the dead evaluation | 20 evaluations for disposal of the dead conducted | Number evaluations for disposal of the dead conducted | 50 evaluations for disposal of the dead facilities conducted | 13 evaluations for disposal of the dead facilities conducted | Achieved | 31 Evaluations for disposal of the dead facilities conducted. | None | None | Reports | R0. 00 | Safe and Health Environment in the Dsitrict
To conduct 10 environmental awareness campaigns | Environmental Pollution Control | 2 awareness campaigns conducted | Number of awareness campaigns conducted | 10 awareness campaign conducted | 2 awareness campaign conducted | Achieved | 4 Awareness campaign conducted | None | None | Reports | R0. 00 | Safe and Health Environment in the Dsitrict
To respond 100% to all Emergency Management Services (EMS) incidents reported by June 2017 | Fire and Rescue Operations | 103 Structural fire incidents, 172 Motor Vehicle accidents(MVA), 32 Veld fires, 5 vehicle fire, 1 Pedestrian vehicle accident(PVA), 47 special services responded to. | Percentage response to all fire and rescue operations | 100% response to all fire and rescue incidents reported | 100% response to all fire and rescue incidents reported | Achieved | 100% response to all fire and rescue incidents reported. | None | None | Reports | 0 | Improved community safety
To undertake 100% fire safety and prevention activities by June 2017 | Fire Safety and prevention | 77 fire safety meeting with clients, 20 fire safety plans scrutinised | Percentage of fire safety and prevention activities on kinds of facilities and events undertaken | 100% fire safety and prevention | 100% attendance to all received calls reported in terms of the fire brigade service standards and protocols | Achieved | 100% attendance to all received calls reported. | None | None | Reports | R0 00 | Improved community safety
To facilitate 100% maintenance of EMS equipment by June 2017 | EMS Equipment servicing and maintenance | Fire and rescue equipments maintained | Percentage facilitation of EMS equipment maintenance schedule | 100% adherence to EMS equipment maintenance schedule | 100% facilitation of EMS Equipment maintanance | Not applicable | No facilitation of EMS equipment maintanance was required. | None | None | Reports | 145000 | Improved community safety
To undertake 3 firefighting training activities by June 2017 | Training Academy | 2 Firefighter 1, 1 Basic Fire fighting and 2 First Aid level3 classes assessed | Number of firefighter training activities undertaken | 3 firefighting training activities undertaken | 100% undertaking of training academy activities in terms of service standards and protocols | Achieved | 100% undertaking of training activities undertaken. | None | None | Reports | 59132 | Improved Public Confidance
| Disaster management Plan | 100% of Disaster Management Plan reviewed |  | 100% review of Disaster Management Plan *50% community risk assessment * 25% consolidated risk assessment report * 25% submission to management and council structures | 100% Submition to Mayoral Committee and Council for approval | Not Applicable | 100% Submitted to council for approval on the 31 October 2016: OC 14/10/16 | None | None | Report | R0 00
To undertake 100% disaster risk assessment by June 2017 | Disaster Risk Assessment | 33 hazards identified. | Percentage of disaster risk assessment undertaken | 100% disaster risk assessment undertaken | 100% undertaking of disaster risk assessment | Achieved | 100% disaster risk assessment undertaken. (58 disaster incidents assessed). | None | None | Reports | 212000 | Improved public safety confidence
To provide 100% relief material by June 2017 | Provision of relief material | 81 Houses assessed, 57 blankets, 37 mattresses and 02 shacks provided | Percentage of disaster relief material provided | 100% of disaster relief material provided | 100% provision of disaster relief material provided | Achieved | 100% of disaster relief material provided | None | None | Report | 0 | Improved public safety confidence
To coordinate 100% disaster related information by June 2017 | Cordination of disaster information | 100% disaster-related information coordinated | Percentage coordination of disaster related information | 100% coordination of disaster related information | 100% coordination of disaster related information | Achieved | 100% disaster related information coordinated | None | None | Reports | 0 | Improved public safety confidence
To undertake 24 disaster awareness campaigns by June 2017 | Awareness education and research | 24 disaster management awareness campaigns undertaken e.g (high density special operation) | number of disaster awareness campaigns undertaken | 24 disaster awareness campaigns undertaken | 03 disaster management awareness campaigns undertaken | Achieved | 5 disaster awareness campaigns undertaken. | None |  | Report | 30000 | Improved public safety confidence