## Sheet1
2018/2019 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN: FINANCIAL VIABILITY
MEASURABLE OBJECTIVE | STRATEGY | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2017/2018 | INDICATORS | ANNUAL TARGET 2018/2019 | PROGRESS (Achieved/ Not achieved) | ACTUAL PROGRESS | CHALLENGE | REMEDIAL ACTIONS | EVIDENCE | BUDGET 2018-2019
To finalise and implement PPP by June 2019 | By having Private Partnership Partner (Smart Metering) | By undertaking PPP process | Completed study | To have a PPP | Revenue enhancement – Billing and other sources (SMART Metering) | 100% Finalisation of PPP feasibility Study | Percentage Finalisation and implementation of PPP | 100% Finalisation and implementation of PPP | Not Achieved | 25%Finalisation and implementation of PPP(Treasury have approved TVR1 and Draft tender document have been received and SCM is the process of reviewing it) | Delay by National Treasury to approve TVR1 ,and delay by Provider to send a draft PPP tender document for review | SCM have received the draft PPP bid document and is in the process of reviewing it for compluiance | PPP agreement & reports | 2540000
To improve collection rate by June 2019 | By implementing credit control measures | By implementing credit control measures | 80% collection rate | To collect 80% revenue by June 2019 | Revenue enhancement – Billing and other sources | 66% Revenue Collection | Percentage Revenue Collection Rate | 80% Revenue Collected | Not Achieved | Revenue Collection at year end is 61% | New 5 Flag west areas were since added to the billing and never paid,Series protests mainly in Groblersdal and Marblehall refused to pay their accounts and denied access for meter readings and water cut | Stakeholders engagements to bill flat rate have been conducted in 5 Flag West areas.series of engagements , political intervention and payments arrangements have been made with customers from Marblehall and Groblersdal | Billing reports | R7m
To create cash backed reserve fund by June 2019 | By reinvesting interest and portion of VAT refunds | Capital Replacement Reserve fund | Budget 2017/18 (R35m) | Percentage improvement in capital replacement reserve fund | Reserve fund | R10m | Rand Value invested towards CRR | R5m invested towards CRR | Achieved | R9m was invested in 2018/2019 | None | None | Investment certificates | 0
To develop and implement procurement plan and inventory management by June 2019 | By Implementation of forward plans | By implementing SCM regulations. | 2017/18 Procurement Plan developed | Procurement plan developed and implemented. | Logistics and inventory management | IDP/BUDGET | 1. Percentage development and implementation of procurement plans 2. Percentage accounting for inventory | 1.100% development and implementation of 2018/19 procurement plans 2. 100% accounting for inventory | Achieved | 1.100% development and implementation of 2018/19 procurement plans done 2. 100% accounting for inventory accounted for | None | None | Procurement Plan *Stock counting sheet | 0
To comply with statutory returns by June 2019 | To utilise the finance intern as compliance officer | Compliance checklist and Human Resources | Compliance reports prepared and submitted on time | Compliance to legislation and regulations | Compliance reporting | 2016/17 AFS 2016/17 Section 52; 71, 72 and SCM reports | Number of finance compliance reports generated and submitted | 30 finance compliance reports generated and submitted (12x Section 71, 4x Section 52, 12x Supply Chain, 1x Section 72, 1xAFS) | Achieved | 30 finance compliance reports generated and submitted (12x Section 71, 4x Section 52, 12x Supply Chain, 1x Section 72, 1xAFS) | All the lesgilated reports were submitted, Sec. 71 in August 2018 and May 2019 were submitted late. | Stick to timelines as per MFMA | Acknowledgement of receipt of Section 71, 52 and 72 Report by Office of Executive Mayor, Auditor General acknowledgement receipt of AFS | 0
To pay within 30 days | By Centralisation of invoice receipting and monitoring of the payment process by CFO | Payment control sheet | All creditors paid within 30 days | Reduction of fruitless expenditure | Creditors payments | Payment rate at 28 days | Percentage payment of creditors within 30 days of correct invoice receipt-date | 100% creditors paid within 30 days of correct invoice receipt- date. | Not achieved | 85% of the invoices were paid within 30 days. | *Delay in resolving queried invoices by end-user departments *Cash-flow problems | Proper monthly cash flow projections and monitoring of expenditure to avoid lack of funds to be experienced towards year end | Creditors aging report | 0
To comply with section 66 of MFMA by June 2019 | By Centralisation of invoice receipting and monitoring of the payment process by CFO | Human Resources Payment Control | All creditors paid within 30 days | Compliance to BCEA | Salaries and third parties payments | 2017/2018 Salaries paid by 25th & 3rd Parties on or before 7th | Percentage payment of salaries and third parties by 25th & the 7th respectively | 100% payment of salaries and third parties by 25th & the 7th respectively | Achieved | 100% payment of salaries and third parties by 25th & the 7th respectively | None | None | Pay roll variance report and salary recon | 0
To prepare and monitor credible budget by June 2019. | By have a functioning budget steering committee | Budget preparation and implementation | 100% 2017/2018 approved realistic and credible budget | Percentage realistic and credible budget prepared. | Budget preparation, review of budget related policies and monitoring | 100% 2017/2018 approved budget | Percentage credible budget prepared and monitored. | 100% credible budget prepared and monitored ( 10% approved budget timetable) * 10% Roll over application * 30% Mid-year adjustment of budget *10% Review of budget related policies *20% Tabling of budget 20% approval of funded budget) | Not Achieved | 100% Budget approved | Overspending on Budget | Fully funded budget need to be implemented | Fully funded final budget. | 0
To have GRAP compliant Fixed Asset Register by June 2019. | By Sound financial management. | human resource, Asset Management Policy | GRAP compliant asset register | Improved asset management and service delivery | Fixed Asset register | 1. Manual GRAP Compliant Fixed asset register 2. Project register | Percentage accounting of Assets | 100% accounting of assets | Not Achieved | 70% accounting of assets (Records are kept safely. Immovable valuation runned. Assets are kept safe) | Movable Asset Register is not yet updated | *Ensure monthly depreciation calcultions * Unbundling of Assets be done as and when projects are completed * Apply Electronic verification system(Scanner) | 1.Verification reports 2.GRAP Compliant Fixed Asset Register | 2040000
To fully comply with mSCOA implementation by June 2019. | By implementing mSCOA implementation plan | mSCOA Project | Council resolution | 100% compliance to mSCOA requirements | mSCOA implementation | Council resolution 2014/2015 & Treasury circular | Percentage unbundling of assets compliant to mSCOA | 100% unbundling of assets compliant to mSCOA | Not Achieved | 70% unbundling of assets compliant to mSCOA(Immovable Assets depreciation run tests conducted outsite MSCOA system) | mSCOA requirements shortfalls were discovered on fixed asset register(FAR) | To be resolved on monthly basis | mSCOA progress report | 2489200
To achieve unqualified audit opinion without matters by June 2019 | By fully implement the audit action plan. | Human resource | Clean audit outcome | Sound financial management | Clean audit - OPCA | Unqualified audit opinion with matters of emphasis. ( 21 audit findings) | Percentage reduction in matters of emphasis and monitoring of the 17/18 audit process | 100% reduction in matters of emphasis and monitoring of the 17/18 audit process | Achieved | 100% reduction in matters of emphasis and monitoring of the 17/18 audit process | None | Progress report on Audit Action Plan | Progress report on Audit Action Plan | 142800