## Sheet1
2018/2019 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN: FINANCIAL VIABILITY
MEASURABLE OBJECTIVE | STRATEGY | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2017/2018 | INDICATORS | ANNUAL TARGET 2018/2019 | Q1 | Q2 | Q3 | Q4 | ACHIEVED/NOT ACHIEVED | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTION | EVIDENCE | BUDGET 2018-2019
To finalise and implement PPP by June 2019. | By having Private Partnership Partner (Smart Metering) | By undertaking PPP process | Completed study | To have a PPP | Revenue enhancement – Billing and other sources (SMART Metering) | 100% Finalisation of PPP feasibility Study | Percentage Finalisation and implementation of PPP | 100% Finalisation and implementation of PPP | 20% finalisationand implementation of PPP.( decision by National Treasury in respect of TVR I AND TVR: IIA) | 30% finalisation and implementation of PPP (A decision by National Treasury in respect of TVR: IIB | 25% finalisation and implementation of PPP. (Appointment and Implementation of PPP) | 25% Implementation and finalisation of PPP | Not Achieved | The only decision received is with regard to TVR 1 and TVR II a is still outstanding National Treasury takes time issuing decisions regarding PPP application response was received | National Treasurytakes time to respond to PPP issues | To amend SDBIP during adjustment period, as National Treasury PPP unit agreed that our targets are then unrealistic considering the time they take to make decisions for TVRs | PPP agreement & reports and approval letter | 2540000
To improve collection rate by June 2019 | By implementing credit control measures | By implementing credit control measures | 80% collection rate | To collect 80% revenue by June 2019 | Revenue enhancement – Billing and other sources | 66% Revenue Collection | Percentage Revenue Collection Rate | 80% Revenue Collected | Increase by 4% to 70% collection rate | Increase by 4% to 74% collection rate | Increase by 3% to 77% collection rate | Increase by 3% to 80% collection rate | Not Achieved | The total bill for first quarter was R26m and collection was R12,1m. The colletion rate for the quarter is at 47% | 1)Lack of credit control staff. 2) Non delivered mails due to errors and delayed mail. 3)Service provider for collection not yet appointed. 4)Unable to collect due to inconsistence water supply | 1)Appointed 5 learners to assist the department with credit control 2) Non delivered mail are being verified through crosscheck system. 3) TOR for collection has been submitted to SCM for advertising. 4) Continuous maintenance of infrastructure will be done to avoid supply interruption. The municipality is in the process of finalizing O&M Plan to assist in doing preventive maintenance | Billing reports | R7m
To create cash backed reserve fund by June 2019 | By reinvesting interest and portion of VAT refunds | Capital Replacement Reserve fund | Budget 2017/18 (R35m) | Percentage improvement in capital replacement reserve fund | Reserve fund | R10m | Rand Value invested towards CRR | R5m invested towards CRR | R1m | R1m | R2m | R1m | Achieved | Total interest earned for the quarter is R 3 948 478,46 | None | None | Investment certificates | 0
To develop and implement procurement plan and inventory management by June 2019 | By Implementation of forward plans | By implementing SCM regulations. | 2017/18 Procurement Plan developed | Procurement plan developed and implemented. | Logistics and inventory management | IDP/BUDGET | 1. Percentage development and implementation of procurement plans 2. Percentage accounting for inventory | 1.100% development and implementation of 2018/19 procurement plans 2. 100% accounting for inventory | *100% Finalisation of Procurement Plan. *100% accounting for inventory | *100% Monitoring and Implementation of procurement plan *100% accounting for inventory | 100% Monitoring and Implementation *100% accounting for inventory | *100% Monitoring and implementation, *100% Development of 2019/20 Procurement plans. *100% final accounting for inventory | Not Achieved | Only management of stock was done successfully for first quarter. | User departments took long to submit TOR for advertisement and bid committee meetings were rescheduled on numerios occations due to departmental commitments | Expedite the submssions of TOR by user department The bid calender was issued were one meeting is not allowed to be postponed twice,if it does MM intervenes | *Procurement Plan *Stock counting sheet | 0
To comply with statutory returns by June 2019 | To utilise the finance intern as compliance officer | Compliance checklist and Human Resources | Compliance reports prepared and submitted on time | Compliance to legislation and regulations | Compliance reporting | 2016/17 AFS 2016/17 Section 52; 71, 72 and SCM reports | Number of finance compliance reports generated and submitted | 30 finance compliance reports generated and submitted (12x Section 71, 4x Section 52, 12x Supply Chain, 1x Section 72, 1xAFS) | 8 Compliance reports (3 Sec 71, 3 SCM , 1 Sec 52 and 1 AFS) reports | 8 (3 Sec 71, 3 SCM , 1 Sec 72 and 1 Sec 52) reports | 7 (3 Sec 71, 3 SCM and 1 Sec 52) reports | 7 (3 Sec 71, 3 SCM and 1 Sec 52) reports | Not Achieved | AFS submitted to AGSA and other sector departments, 3 SCM reports submitted, | Section 71 Reports for July and August not submitted to the mayor due to overwhelming responsibilities of the AFS preparations and Roll over applications | Submit the oustanding section 71 reports (July and August)to executive Mayor with the quarterly reports | Acknowledgement of receipt of Section 71, 52 and 72 Report by Office of Executive Mayor, Auditor General acknowledgement receipt of AFS | 0
To pay within 30 days | By Centralisation of invoice receipting and monitoring of the payment process by CFO | Payment control sheet | All creditors paid within 30 days | Reduction of fruitless expenditure | Creditors payments | Payment rate at 28 days | Percentage payment of creditors within 30 days of correct invoice receipt-date | 100% creditors paid within 30 days of correct invoice receipt- date. | 100% creditors paid within 30 days of correct invoice receipt- date | 100% creditors paid within 30 days of correct invoice receipt- date | 100% creditors paid within 30 days of correct invoice receipt- date | 100% creditors paid within 30 days of correct invoice receipt- date | Not achieved | 93,9% of creditors were paid within 30 days. | 6,1% of creditors have not been processed due late submission of invoices and delayed process for authorisation of invoices by the user department and also Goods received note(GRN) not being processed. | Expedite GRNs for orders with end users and Supply chain division | Creditors aging report | 0
To comply with section 66 of MFMA by June 2019 | By Centralisation of invoice receipting and monitoring of the payment process by CFO | Human Resources Payment Control | All creditors paid within 30 days | Compliance to BCEA | Salaries and third parties payments | 2017/2018 Salaries paid by 25th & 3rd Parties on or before 7th | Percentage payment of salaries and third parties by 25th & the 7th respectively | 100% payment of salaries and third parties by 25th & the 7th respectively | 100% payment of salaries and third parties by 25th & the 7th respectively | 100% payment of salaries and third parties by 25th & the 7th respectively | 100% payment of salaries and third parties by 25th & the 7th respectively | 100% payment of salaries and third parties by 25th & the 7th respectively | Achieved | Salaries and third party payments were processed on on the 25th and before the 7th respectively | None | None | Pay roll variance report and salary recon | 0
To prepare and monitor credible budget by June 2019. | By have a functioning budget steering committee | Budget preparation and implementation | 100% 2017/2018 approved realistic and credible budget | Percentage realistic and credible budget prepared. | Budget preparation, review of budget related policies and monitoring | 100% 2017/2018 approved budget | % credible budget prepared and monitored. | 100% credible budget prepared and monitored ( 10% approved budget timetable) * 10% Roll over application * 30% Mid-year adjustment of budget *10% Review of budget related policies *20% Tabling of budget 20% approval of funded budget) | 1.10% Approved budget timetable 2. 10% Roll over application 2017/2018 . | No activity | * 30% Mid-year Adjustment of budget . * 10% Review of budget related policies(draft policies). 20% Tabling of Draft Budget. | 20% Fully funded Final budget approved | Achieved | Budget timetable was approved on time as well as application for roll over | None | None | Fully funded final budget. | 0
To have GRAP compliant Fixed Asset Register by June 2019. | By Sound financial management. | human resource, Asset Management Policy | GRAP compliant asset register | Improved asset management and service delivery | Fixed Asset register | 1. Manual GRAP Compliant Fixed asset register 2. Project register | % accounting of Assets | 100% accounting of assets | 100% Accounting for assets 1.Safeguarding assets and verification of assets 2.Valuation (run depreciation, update projects register) 3. Records keeping | 100% Accounting for assets 1.Safeguarding assets and verification of assets 2.Valuation (run depreciation, update projects register) 3. Records keeping | 100% Accounting for assets 1.Safeguarding assets and verification of assets 2.Valuation (run depreciation, update projects register) 3. Records keeping | 100% Accounting for assets 1.Valuation. 2. Records keeping, 3. safe guarding & disposal. 4. Activation of electronic asset Module. Year end verification. 5. Impairment tests. 6. 100% unbundling. 7. Review useful lives & review residual vales. 8. Reconcile FAR to G/L. 9.Prepare notes to AFSs. | Achieved | 1) Assets are safeguarded, 2) Valuation is done, 3) Records are kept safe 4) Updated WIP, Commitment ,Retention and Additions Registers 5) Physical verification was performed | None | None | 1.Verification reports 2.GRAP Compliant Fixed Asset Register | 2040000
To fully comply with mSCOA implementation by June 2019. | By implementing mSCOA implementation plan | mSCOA Project | Council resolution | 100% compliance to mSCOA requirements | mSCOA implementation | Council resolution 2014/2015 & Treasury circular | % unbundling of assets compliant to mSCOA | 100% unbundling of assets compliant to mSCOA | 20% appointment of service provider | 20% unbundling of assets compliant to mSCOA | 30% unbundling of assets compliant to mSCOA | 30% unbundling of assets compliant to mSCOA | Not Achieved | Advert closed at 27 June 2018 | Service provider not appointed | The process is at appointment stage | mSCOA progress report | 2489200
To achieve unqualified audit opinion without matters by June 2019 | By fully implement the audit action plan. | Human resource | Clean audit outcome | Sound financial management | Clean audit - OPCA | Unqualified audit opinion with matters of emphasis. ( 21 audit findings) | % reduction in matters of emphasis and monitoring of the 17/18 audit process | 100% reduction in matters of emphasis and monitoring of the 17/18 audit process | *30% reduction of 16/17 matters of emphasis | 70% reduction in matters of emphasis and 100% monitoring of the 17/18 audit process | 100% development and monitoring of 2017/2018 action plan | 100% monitoring of the 2017/2018 action plan | Achieved | 39 sub issues were resolved and 11 is still in progress | Recurring issues such as water loss and Dispute on disallowed VAT that is still being investigated by the consultant | Ojection has been made with SARS. VAT specialist were appointed to review all disallowed VAT inpu | Progress report on Audit Action Plan | 142800
[9 empty] | 5 | Not achieved |  |  | Achieved
[9 empty] | 6 | Achieved |  |  | Not Achieved
[9 empty] | 11 |  |  |  | Total
[9 empty] | 45% | Performance for September |  |  | Performance for Quarter 1
Compiled by:
Rebotile Makgati
[6 empty] | Acting Deputy Chief Financial Officer | [8 empty] | Date