## OTHER DEPARTMENTS
Name of municipality |  | SEKHUKHUNE DISTRICT MUNICIPALITY
Name of Accounting Officer / Delegated Officer |  | M NTSHUDISANE
Signature of Accounting Officer/Delegated
Telephone Number and e-mail addresss
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 13 |  |  | 14 | 15 | 16 | 17
Ref No. | Description | Vote | Type | Contract Number | No. of Deliverables | Estimated Cost Rv /Budgeted Amount |  |  | Procurement Method | Source of Funding | BSC | Preparation BD/RFP Date (Advertisement date) | Expected Bid Open Date/Proposal Submission Date (closing date) | Bid Evaluation Committee (BEC) | Bid Adjudication Committee(BAC) | Appointment Letter/Contract Sign Date | Contract Completion Date | Progress Achieved/Not Achieved | Remarks
MIG FUNDED PROJECTS
1 | Physical Security Services (Tubatse Security Servivces) | 33052285400EQMRCZZHO | Security | SK8/3/1-04/2019/2020 | CLUSTER 01 = 106 | 53 822 111,04/3 yrs=G8:G12 R17 940 703,68 | 7491000 |  | Open Tender | SDM | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | Achieved | Contract in place
2 | Physical Security Services (Mogola Security & Cleaning) | 33052285400EQMRCZZHO | Security | SK8/3/1-04/2019/2020 | CLUSTER 02 = 74 | 14 050 328 ,25/3yrs = R4 683 442,66 | 7491000 |  | Open Tender | SDM | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | Achieved | Contract in place
3 | Physical Security Services (Tubatse Security Servivces) | 33052285400EQMRCZZHO | Security | SK8/3/1-04/2019/2020 | CLUSTER 0 3 = 60 | 30 407 270,32/3rys= R10 135 756,77 | 7491000 |  | Open Tender | SDM | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | Achieved | Contract in place
4 | Physical Security Services (Sesana Security) | 33052285400EQMRCZZHO | Security | SK8/3/1-04/2019/2020 | CLUSTER 04 = 73 | 34 640 442,87/3yrs = R11 546 814,29 | 7491000 |  | Open Tender | SDM | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | Achieved | Contract in place
5 | Alarm Monitoring and Response | 33052285400EQMRCZZHO | Armed Response | None delineated | Bareki mall = 01 site | 36000 | 36000 |  | Open Tender | SDM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Achieved | Contract in place
6 | Assets Insurance ( Gurardrisk Insurance ) | 33052302460EQMRCZZHO 33052302440EQMRCZZHO | Assets Insurance & Excess | None. Insured direct with Insurance Company | All known Moveable and unmoveable assets | 968 851,00 Excess + 6 131 490,00 premiums = R7 100 341,00 | 7100341 |  | Public Tender | SDM | N/A | 2021-05-01 | 2021-05-10 | 2021-06-15 | 2021-06-25 | 2021-06-30 | 2024-06-01 |  | To be advertised
0
CORPORATE SERVICES
INFORMATION AND COMMUNICATION SERVICES
1 |  |  | Water | TBC | 1 WC/WD Management Strategy | 800000 | 0 | 800000 | Term consultant | SDM |  | 2017-07-10 | 2017-07-24 |  |  | 2017-08-10 | 2018-04-30
2 |  |  | Sewer | TBC | 1x Pump station upgraded | 800000 | 0 | 800000 | Term consultant | SDM |  | 2017-07-10 | 2017-07-24 |  |  | 2017-08-10 | 2018-03-31
3 |  |  | Sewer | TBC | 1x Bulk sewer Feasibility study | 500000 | 0 | 500000 | Term consultant | SDM |  | n/a | n/a |  |  | n/a | 2018-03-31
4 |  |  | Water /Sewer | TBC | 1x Condition assemment and O&M plans developed | 300000 | 0 | 300000 | Term consultant | SDM |  | n/a | n/a |  |  | n/a | 2018-06-30
5 |  |  | Water | TBC | 7 feasibility studies conducted and technical reports developed for Leballo South Villages Phase Two | 5000000 | 0 | 5000000 | Term consultant | SDM |  | n/a | n/a |  |  | n/a | 2017-11-30
[6 empty] | 7400000 | 0 | 7400000
1 |  |  | Water | TBC | 3km bulk pipeline | 30000000 | 30000000 | 0 | Open bid | RBIG |  | 2017-07-02 | 2017-08-01 |  |  | 2017-08-21 | 2018-06-30
2 |  |  | Water | TBC | 1x 5Mℓ reservoir | 18000000 | 18000000 | 0 | Open bid | RBIG |  | 2017-07-09 | 2017-08-08 |  |  | 2017-08-28 | 2018-06-30
3 |  |  | Water | TBC | 4km pipeline | 29000000 | 29000000 | 0 | Open bid | RBIG |  | 2017-07-09 | 2017-08-08 |  |  | 2017-08-28 | 2018-06-30
4 |  |  | Water | TBC | 4km pipeline | 28000000 | 28000000 | 0 | Open bid | RBIG |  | 2017-07-09 | 2017-08-08 |  |  | 2017-08-28 | 2018-06-30
5 |  |  | Water | TBC | 38km rising main tested and commissioned | 12000000 | 12000000 | 0 | N/A | RBIG |  | n/a | n/a |  |  | n/a | 2017-12-20
6 |  |  | Water | TBC | 10Mℓ reservoir and pipeline | 43000000 | 43000000 | 0 | Open bid | RBIG |  | n/a | n/a |  |  | n/a | 2018-06-30
7 |  |  | Water | TBC | 100% M& E components | 60000000 | 60000000 | 0 | Open bid | RBIG |  | n/a | n/a |  |  | n/a | 2018-06-30
8 |  |  | Water | TBC | 100% bulk pipeline and valve chambers |  |  | 0 | Open bid | RBIG |  | n/a | n/a |  |  | n/a | 2018-06-30
[6 empty] | 220000000 | 220000000 | 0
WSIG FUNDED PROJECTS
1 |  |  | Water | TBC | 100% water reticulation network completed | 4500000 | 4500000 | 0 | Term Contractors | WSIG | 2017-11-29 | 2018-01-17 | 2018-01-31 | 2018-02-05 | 2018-02-07 | 2018-02-09 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
2 |  |  | Water | TBC | 5.5km bulk water pipeline constructed | 3000000 | 3000000 | 0 | Term Contractors | WSIG | 2017-11-29 | 2018-01-17 | 2018-01-31 | 2018-02-05 | 2018-02-07 | 2018-02-09 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
3 |  |  | Water | TBC | 100% abstraction point constructed | 3500000 | 3500000 | 0 | Term Contractors | WSIG | 2017-11-29 | 2018-01-17 | 2018-01-31 | 2018-02-05 | 2018-02-07 | 2018-02-09 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
4 |  |  | Water | TBC | 7km pipeline constructed | 2500000 | 2500000 | 0 | Term Contractors | WSIG | 2017-11-29 | 2018-01-17 | 2018-01-31 | 2018-02-05 | 2018-02-07 | 2018-02-09 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
5 |  |  | Water | TBC | 3.5km pipeline constructed | 0 | 0 | 0 | Term Contractors | WSIG | 2017-11-29 | 2017-11-30 | 2017-12-14 | 2017-12-21 | 2017-12-22 | 2018-01-10 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
6 |  |  | Water | TBC | 100% package plant constructed | 3000000 | 3000000 | 0 | Term Contractors | WSIG | 2017-11-29 | 2017-11-30 | 2017-12-14 | 2017-12-21 | 2017-12-22 | 2018-01-10 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
7 |  |  | Water | TBC | 100% package plant constructed | 2700000 | 2700000 | 0 | Term Contractors | WSIG | 2017-11-29 | 2018-01-17 | 2018-01-31 | 2018-02-05 | 2018-02-07 | 2018-02-09 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
8 |  |  | Water | TBC | 7km pipeline constructed | 2000000 | 2000000 | 0 | Term Contractors | WSIG | 2017-12-01 | 2018-01-17 | 2018-01-31 | 2018-02-05 | 2018-02-07 | 2018-02-09 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
9 |  |  | Water | TBC | 2km pipeline constructed | 2000000 | 2000000 | 0 | Term Contractors | WSIG | 2017-12-01 | 2018-01-17 | 2018-01-31 | 2018-02-05 | 2018-02-07 | 2018-02-09 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
10 |  |  | Water | TBC | 33km bulk pipeline tested and commissioned. | 8112800 | 8112800 | 0 | Turnkey | WSIG | 2018-01-17 | 2018-01-19 | 2018-02-02 | 2018-02-06 | 2018-02-08 | 2018-02-10 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
11 |  |  | Water | TBC | 2 water sources developed and technical reports prepared . | 2000000 | 2000000 | 0 | Term Contractors | WSIG | 2018-01-12 | 2018-01-24 | 2018-02-07 | 2018-02-09 | 2018-02-12 | 2018-02-14 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
12 |  |  | Water | TBC | 4 water source developed and no of technical reports prepared. | 1500000 | 1500000 | 0 | Term Contractors | WSIG | 2018-01-17 | 2018-01-23 | 2018-02-06 | 2018-02-08 | 2018-02-09 | 2018-02-12 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
13 |  |  | Water | TBC | 1.7 kilometers of pipeline constructed | 3000000 | 3000000 | 0 | Term Contractors | WSIG | 2017-12-01 | 2018-01-17 | 2018-01-31 | 2018-02-05 | 2018-02-07 | 2018-02-09 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
14 |  |  | Water | TBC | 2.8 kilometers of pipeline constructed | 3000000 | 3000000 | 0 | Term Contractors | WSIG | 2017-12-01 | 2018-01-17 | 2018-01-31 | 2018-02-05 | 2018-02-07 | 2018-02-09 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
15 |  |  | Water | TBC | 2.3 kilometers of pipeline constructed | 2300000 | 2300000 | 0 | Term Contractors | WSIG | 2017-12-01 | 2018-01-17 | 2018-01-31 | 2018-02-05 | 2018-02-07 | 2018-02-09 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
16 |  |  | Water | TBC | 3.2 kilometers of pipeline constructed | 3000000 | 3000000 | 0 | Term Contractors | WSIG | 2018-01-12 | 2018-01-24 | 2018-02-07 | 2018-02-09 | 2018-02-12 | 2018-02-14 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
17 |  |  | Water | TBC | 450 household meters Installed. | 9132786 | 9132786 | 0 | Term Contractors | WSIG | 2018-01-17 | 2018-01-19 | 2018-02-02 | 2018-02-06 | 2018-02-08 | 2018-02-10 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
18 |  |  | Water | TBC | One package plant refurbished in Tjibeng . | 3500000 | 3500000 | 0 | Term Contractors | WSIG | 2017-10-18 | 2017-11-14 | 2017-12-05 | 2018-01-11 | 2018-01-12 | 2018-01-16 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
19 |  |  | Water | TBC | One of water source developed | 3000000 | 3000000 | 0 | Term Contractors | WSIG | 2018-01-17 | 2018-01-23 | 2018-02-06 | 2018-02-08 | 2018-02-09 | 2018-02-12 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
20 |  |  | Sewer | TBC | 334 VIDP Sanitation units constructed | 4500000 | 4500000 | 0 | Open Bid | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Contractor appointed
21 |  |  | Water | TBC | 100% refurbishment of Thabampshe water pump station ( 2 pumps, motors and electrical panel completed and replacement of valves and testing of rising main | 3700000 | 3700000 | 0 | Term Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Contractor is already on site
22 |  |  | Water | TBC |  | 1509362.73 | 1509362.73 |  | Term Contractors | WSIG | 2018-01-17 | 2018-01-23 | 2018-02-06 | 2018-02-08 | 2018-02-09 | 2018-02-12 | 2018-06-15 | Not Achieved
[6 empty] | 71454948.73 | 71454948.73 | 0
WSIG FUNDED PROJECTS (2016/2017)
1 |  |  | Water | TBC | Drilling, testing and equipping of two boreholes, construction of 3800m of 75mm diameter reticulation network with stand pipes,1200m of 90mm diameter rising main, installation of 100kl elevated steel tank | 4045962 | 4045962 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
2 |  |  | Water | TBC | Construction of 200kl elevated steel tank and the 3000m length of 65mm diameter pipeline. | 2684752 | 2684752 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
3 |  |  | Water | TBC | Development water source, testing, equipping of two boreholes, construction 2 500m length of 65mm diameter pipeline and installation of steel tank. | 2685773 | 2685773 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
4 |  |  | Water | TBC | Testing and equipping of existing borehole, construction of ±3500m of 75mm diameter reticulation network with stand pipes, 1200m of 90mm diameter rising main with four Jojo Tanks. | 3174150 | 3174150 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
[6 empty] | 12590637 | 12590637
|  |  | Water | TBC |  | 1265831 | 1265831 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
|  |  | Water | TBC |  | 0 | 0 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
|  |  | Water | TBC |  | 210000 | 210000 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
|  |  | Water | TBC |  | 1242860 | 1242860 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
|  |  | Water | TBC |  | 1075579 | 1075579 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
|  |  | Water | TBC |  | 2318157 | 2318157 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
|  |  | Water | TBC |  | 447933.27 | 447933.27 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
|  |  | Water | TBC |  | 194054 | 194054 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
|  |  | Water | TBC |  | 4200000 | 4200000 | 0 | Terms Contractors | WSIG | 2018-01-17 | 2018-01-23 | 2018-02-06 | 2018-02-08 | 2018-02-09 | 2018-02-12 | 2018-06-15 | Not Achieved | None
[6 empty] | 10954414.27 | 10954414.27 | 0
8 | Wireless Connection(5 Sites) | 39052270400EQMRCZZHO |  | None |  | 969000 |  |  | Quotations |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
9 | Wireless Connection(5 Sites) | 39052270400EQMRCZZHO |  | None |  | 500000 |  |  | Quotations |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10 | ICT Infrastructure Connection | 39052270400EQMRCZZHO | [8 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11 | Implementation of security measures | 39052270400EQMRCZZHO |  | None |  | 400000 |  |  | Quotations |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 | Software License renewal | 39052301790EQMRCZZHO |  | None |  | 3859000 |  |  | Quotations |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
13 | Audio Conference Recording Support | 39052301790EQMRCZZHO |  | None |  | 660000 |  |  | Quotations |  | 2021-05-05 | 2021-05-10 | 2021-06-25 | 2021-06-30 | 2021-07-05 | 2021-07-15 | N/A
14 | CCTV and Biometrics | 39052270400EQMRCZZHO |  | None |  | 660000 |  |  | Quotations |  | 2021-07-01 | 2021-07-10 | 2021-08-25 | 2021-09-29 | 2021-09-30 | 2021-09-30 | N/A
15 | Disaster Recovery Plan Support | 39052270400EQMRCZZHO |  | None |  | 720000 |  |  | Quotations |  | 2021-06-01 | 2021-06-15 | 2021-06-20 | 2021-07-25 | 2021-07-30 | 2021-08-02 | N/A
16 | Consumables | 39052320600EQMRCZZHO |  | None |  | 495000 |  |  | Quotations |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
17 | Computers/Servers | 35106470020CFG84ZZWD |  | None |  | 1000000 |  |  | Quotations |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUXILLARY SERVICES
18 | Purchase of Emergency vehicles | 39052306300EQP76ZZH0 | Lease to purchase (Settlement) | New | 15 | 12000000 | _ | _ | Lease to purchase (Settlement) | SDM | 01/07/2021 | 2021-08-25 | 2021-09-01 | 2021-10-01 | 2021-10-25 | 2021-10-30 | 2021-11-01
19 | Mainatanance of Vehicles | 39052283610EQP74ZZHO | Tender | New | 30 | 2000000 | 2200000 | 2300000 | Tender | SDM | 01/06/2021 | 2021-09-15 | 2021-09-30 | 2021-10-15 | 2021-10-25 | 2021-10-30 | 2024-06-01 |  |  | COMMUNITY SERVICES
20 | Lease of IWS vehicles | 39052306300EQP76ZZH0 | Tender | New | 109 | 27000000 | 29000000 | 32000000 | Tender | SDM | 01/07/2021 | 2021-09-15 | 2021-09-30 | 2021-10-15 | 2021-10-25 | 2021-10-30 | 2024-06-01 |  |  | MUNICIPAL HEALTH
21 | Lease of IWS Ephraim Mogale office | 39052383650EQMRCZZH0 | Tender | New | 1 | 300000 | _ | _ | Tender | SDM | 01/06/2021 | 2021-09-15 | 2021-09-30 | 2021-10-15 | 2021-10-25 | 2021-10-30 | 2024-06-01 |  |  | FOOD SAMPLING
22 | Lease of IWS Makhuduthamaga office | 39052383650EQMRCZZH0 | Tender | New | 1 | 700000 | 720000 | 730000 | Tender | SDM | 01/06/2021 | 2021-09-15 | 2021-09-30 | 2021-10-15 | 2021-10-25 | 2021-10-30 | 2024-06-01 |  |  | VECTOR CONTROL APPARATUS
23 | Moutse West offices | 39052383650EQMRCZZH0 | Tender | New | 1 | 350000 | 370000 | 380000 | Tender | SDM | 01/05/2021 | 2021-05-25 | 2021-06-30 | 2021-07-10 | 2021-07-25 | 2021-07-31 | 2024-06-01 |  |  | ANALYSERS
24 | Cleaning Material | 39052283600EQP72ZZHO | Notice | New | 60 | 300000 | 310000 | 320000 | Tender | SDM | 01/07/2021 | 2021-08-25 | 2021-09-30 | 2021-10-15 | 2021-10-25 | 2021-10-30 | 2022-11-30 |  |  | GASES
25 | Mainatanance of buildings | 39052283600EQP72ZZHO | Notice | New | 9 | 500000 | 520000 | 530000 | Tender | SDM | 01/07/2021 | 2021-09-15 | 2021-09-30 | 2021-10-15 | 2021-10-25 | 2021-10-30 | 2022-11-30 |  |  | UNIFORM
26 | Purchase of 2 offices Ephraim Mogale | New Vote | Purchase from Gov.to Gov | New | 2 | 2200000 | 2400000 | 2400000 | Request offer to purchase | SDM | 01/07/2021 | 2021-09-15 | 2021-09-30 | 2021-10-15 | 2021-10-25 | 2021-10-30 | Once off |  |  | SAMPLING EQUIPMENTS
27 | Lease of photocopier for regional offices | 39052381500EQMRCZZHO | Lease | SK-8/3/1-11/2020/2021 | 5 |  |  |  | Tender | SDM | 2020-11-17 | 2020-11-27 | 2021-01-18 | 2021-01-29 | 2021-02-01 | 2021-02-18 | 2024--2-17 |  |  | WASTE MANAGEMENT TOOLS
COVID 19 UNIT
28 | Materials and Supplies for COVID-19. Face cloth mask 2 layers of fabric . | 39052320600EQ11ZZHO |  | N/A | Number of Face cloth masks procured. 3000 Face cloth masks | 50000 |  |  | Quotations | Own Revenue
29 | Digital Thermometers | 39052320600EQ11ZZHO |  | N/A | Number of temperature scanners for COVID-19. 150 temperature scanners. | 10000 |  |  | Quotations | Own Revenue
30 | Sanitisers and Disinfectants. Sanitizer with not less than 70% alcohol content. Anti- bacterial liquid hand soaps. | 39053330600EQ11ZZHO |  | N/A | Number of Sanitisers and Disinfectants procured. 200 Sanitizers, 200 Surface Disinfectants, 1200 Hand Sanitizers sprays, 50 cleaning cloths. | 500000 |  |  | Tender | Own Revenue | 2021-05-10 | 2021-05-19 | 2021-06-15 | 2021-06-18 | 2021-06-21 | 2021-06-25 | Once off
31 | Perspex Protective Screens for COVID-19 | 39054340600EQ11ZZHO |  | N/A | Number of Perspex Protective Screens COVID-19 . 100 Perspex Protective Screens ( COVID-19) | 110000 |  |  | Quotations | Own Revenue | N/A | N/A | N/A | N/A | N/A | N/A | N/A
32 | Hands free Sanitizing Machine. | 39055350600EQ11ZZHO |  | N/A | Number of hands free Sanitizing Machines. 50 | 60000 |  |  | Quotations | Own Revenue | N/A | N/A | N/A | N/A | N/A | N/A | N/A
33 | COVID-19 information posters | 39056360600EQ11ZZHO |  | N/A | Number of COVID-19 information posters procured. 100 COVID-19 information posters. | 24000 |  |  | Quotations | Own Revenue | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EMPLOYEE ASSISTANCE PROGRAMME & OCCUPATIONAL HEALTH &SAFETY
34 | Substance Abuse programme |  |  | N/A |  | R549, 137.00 (Annual budget)
35 | Employee wellness $ counselling (Stress and Trauma Management, debriefings) |  |  | N/A |  | R100 000 00
36 | Employee wellness $ counselling (Stress and Trauma Management, debriefings) |  |  | N/A |  | R549, 137.00 (Annual budget) |  |  | Quotation |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
37 | Substance Abuse programme |  |  | N/A |  | R100 000 00 |  |  | Bid |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
38 | Employee wellness $ counselling (Stress and Trauma Management, debriefings) |  |  | N/A |  | R249.137 000 00 |  |  | Quotation |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
39 | Empoyees' cases (Referral to specialised care services) |  |  | N/A |  | R100 000 00 |  |  | Quotation |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
40 | Employees' Incapacity Ill health |  |  | N/A |  | R100, 000 00 |  |  | Quotaions |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
41 | Occupational Health and Safety (OHS) |  |  | N/A |  | R8, 016, 894.00 (Annual budget) |  |  | Quotation |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
42 | Personal Protective Equipment (PPE) |  |  | N/A |  | R 6. 866 894 00 |  |  | Bid |  | 2021-05-10 | 2021-05-21 | 2021-06-25 | 2021-07-10 | 2021-07-20 | 2021-08-09 | 2024-10-08
43 | Servicing of Fire Extiquishers |  |  | N/A |  | R150 000 00 |  |  | Bid |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
44 | Medical Surveillance Programme |  |  | N/A |  | R1 000 000 00 |  |  | Quotations |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
4
EMERGENCY SERVICES
45 | OS:Personnel and Labour | 370522644500EQP67ZZWD | P | N/A |  | 223671.34 |  |  | Quotation |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
46 | Maintanance of equipment | 37052283610EQP20ZZHO | P | N/A |  | 63440.62 |  |  | Quotation |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
47 | Uniform | 37052320600EQQ12ZZHO | P | N/A |  | 1000000 |  |  | Quotatiojns |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DISASTER MANAGEMENT
48 | Catering Services | 37052260600EQP36ZZWD |  |  |  | 43661.62 |  |  | Quotations |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
49 | B&N Organisational | 37052270400EQP17ZZHO |  |  |  | 291480 |  |  | Quotations |  |  | N/A | N/A | N/A | N/A | N/A | N/A
OFFICE OF THE EXECUTIVE MAYOR
50 | Mayoral Outreaches and Sectoral Engagement |  |  | SK8/3/1-41/2017/18 |  | 400000 |  |  | Quotations | Event managemen company |  | SDM | N\A | N\A | N\A | N\A | N\A |  | Contract in place
51 | Marketing and branding |  |  | SK8/3/1-41/2017/18 |  | 50000 |  |  | Quotations | Quotation |  | SDM | N\A | N\A | N\A | N\A | N\A |  | Contract in place
52 | Website Management |  |  | SK8/3/1-41/2017/18 |  | 130000 |  |  | Quotations | Quotation |  | SDM | N\A | N\A | N\A | N\A | N\A |  | Contract in place
53 | Newsletter and Publication |  |  | SK8/3/1-41/2017/18 |  | 500000 |  |  | Quotations | Event managemen company |  | SDM | N\A | N\A | N\A | N\A | N\A |  | Contract in place
54 | Traditional Leadership meetings |  |  | SK8/3/1-41/2017/18 |  | 100000 |  |  | Quotations | quotation |  | SDM | N\A | N\A | N\A | N\A | N\A |  | Contract in place
55 | Strategic Events |  |  | SK8/3/1-41/2017/18 |  | 300000 |  |  | Quotations | Event managemen company |  | SDM | N\A | N\A | N\A | N\A | N\A |  | Contract in place
56 | Batho Pele Programmes |  |  | SK8/3/1-41/2017/18 |  | 100000 |  |  | Quotations | quotation |  | SDM | N\A | N\A | N\A | N\A | N\A | N\A | Contract in place
57 | SODA |  |  | SK8/3/1-41/2017/2018 |  | 450000 |  |  | Quotations | Event managemen company |  | SDM | N\A | N\A | N\A | N\A | N\A | N\A | Contract in place
58 | Aged Care Programmes |  |  | SK8/3/1-41/2017/2018 |  | 100000 |  |  | Quotations |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Contract in place
59 | Children Care Prorammes |  |  | SK8/3/1-41/2017/2018 |  | 100000 |  |  | Quotations |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Contract in place
60 | Women Development Programmes |  |  | SK8/3/1-41/2017/2018 |  | 300000 |  |  | Quotations |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Contract in place
61 | Disability Awareness Camoaigns |  |  | SK8/3/1-41/2017/2018 |  | 100000 |  |  | Quotations |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Contract in place
62 | Art and Culture Programmes |  |  | SK8/3/1-41/2017/2018 |  | 350000 |  |  | Quotations |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Contract in place
63 | District Aids Council Activities |  |  | SK8/3/1-41/2017/2018 |  | 100000 |  |  | Quotations |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Contract in place
64 | Youth Development Activities |  |  | SK8/3/1-41/2017/2018 |  | 900000 |  |  | Quotations |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Contract in place
65 | Mayoral Sports Activities |  |  | SK8/3/1-41/2017/2018 |  | 500000 |  |  | Quotations |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Contract in place
66 | Call Centre Revamp |  |  | SK8/3/1-41/2017/2018 |  | 600000 |  |  | Quotations |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Contract in place
67 | Mayor's Forum |  |  | N/A |  | 100000 |  |  | Quotations |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Contract in place
68 | Moral Regeration Movement |  |  | SK8/3/1-41/2017/2018 |  | 50000 |  |  | Quotations |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Contract in place
PLANNING & ECONOMIC DEVELOPMENT
SPATIAL PLANNING: GIS
69 | Integration of GIS with Billing System for a period of 3 years | New project | System Integration | New | N/A | 1000000 | - | - | Open Tender | SDM | 2021-08-01 | 2021-08-08 | 2021-09-15 | 20201-09-30 | 2021-10-05 | 2021-10-10 | 2022-05-31
LOCAL ECONOMIC DEVELOPMENT
70 | Facilitate development of Industrial Development Master Plan for the Special Economic Zone (SEZ) | 36052260600EQQ22ZZWD | Tender | New | 1 | 1500000 |  |  | Tender | SDM | 2021-06-18 | 2021-06-30 | 2021-08-01 | 2021-08-10 | 2021-08-15 | 2021-08-25 | 2022-03-01
71 | Facilitate Enterprise and Supplier Development Programme | 36052260600EQP95ZZHO | Quotations | N/A | 4 | 250000 |  |  | 3 Quotations | SDM | N/A | N/A | N/A | N/A | N/A | N/A | N/A
72 | Support to SMMEs and Co-operatives | 36052260600EQP88ZZWD | 7 days notice | N/A | N/A | 2000000 |  |  | Notice | SDM | 2021-07-09 | 2021-07-20 | 2021-08-22 | 2021-08-31 | 2021-09-05 | 2021-09-15 | 2022-03-01
73 | Facilitate Small Scale Mining Seminars and Workshops | 36052260600EQP89ZZWD | Quotations | N/A | 2 | 100000 |  |  | 3 Quotations | SDM | N/A | N/A | N/A | N/A | N/A | N/A | N/A
74 | Facilitate Economic Development Forums (Mining, Tourism, LED & Agric.) | 36052270400EQP33ZZWD | Quotations | N/A | 4 | 90000 |  |  | 3 Quotations | SDM | N/A | N/A | N/A | N/A | N/A | N/A | N/A
75 | Facilitate review of SDM Tourism Strategy | 36052260600EQQ28ZZWD | Tender | New | 1 | 500000 |  |  | Tender | SDM | 2021-06-18 | 2021-06-30 | 2021-08-01 | 2021-08-10 | 2021-08-15 | 2021-08-25 | 2022-03-01
76 | Facilitate development of SMMEs and Cooperatives development strategy | 36052260600EQP32ZZWD | Tender | New | 1 | 400000 |  |  | Tender | SDM | 2021-06-18 | 2021-06-30 | 2021-08-01 | 2021-08-10 | 2021-08-15 | 2021-08-25 | 2022-03-01
BUDGET AND TREASURY DEPARTMENT
ASSET MANAGEMENT
77 | Asset Management support |  | Tender | SK8/3/1-07/2020/21 |  | 6000000 |  |  | Open tender | SDM | 2021-02-18 | 2020-11-05 | 2020-12-08 | 2021-02-26 | 2021-03-05 | 2021-03-07 | 2024-02-01
78 | Scanners for moveable assets |  | Tender | N/A |  | 300000 |  |  | Open tender | SDM | 2021-06-01 | 2021-06-15 | 2021-06-20 | 2021-07-25 | 2021-08-05 | 2021-08-07 | 2021-06-01
REVENUE
79 | Data collection and Indegent verification |  | Tender | N/A |  | 35000000 |  |  | Open tender | SDM | 2021-06-01 | 2021-06-15 | 2021-06-20 | 2021-07-25 | 2021-08-05 | 2021-08-07 | 2021-06-01
Formulas:
Bid Evaluation Committee (BEC) = [N/A]+5
Bid Adjudication Committee(BAC) = [Bid Evaluation Committee (BEC)]+2
Appointment Letter/Contract Sign Date = [Bid Adjudication Committee(BAC)]+2
N/A = [BSC]+2
N/A = [N/A]+14

## IWS PP 202122
Name of municipality |  | SEKHUKHUNE DISTRICT MUNICIPALITY |  |  | SEKHUKHUNE DISTRICT MUNICIPALITY
Name of Accounting Officer / Delegated Officer |  |  |  |  | M NTSHUDISANE
Signature of Accounting Officer/Delegated
Telephone Number and e-mail addresss |  |  | 132627312
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 13 |  |  | 14 | 15 | 16 | 17
Ref No. | Description | Vote | Type | Contract Number | No. of Deliverables | Estimated Cost Rv /Budgeted Amount |  |  | Procurement Method | Source of Funding | BSC | Preparation BD/RFP Date (Advertisement date) | Expected Bid Open Date/Proposal Submission Date (closing date) | Bid Evaluation Committee (BEC) | Bid Adjudication Committee(BAC) | Appointment Letter/Contract Sign Date | Contract Completion Date | Progress Achieved/Not Achieved | Remarks
RBIG FUNDED PROJECTS
1 | Construction of Mooihoek bulk water supply phase G1.1 |  | Water | TBC | 3 Kilometres of bulk water supply pipeline. Construction of 1 package plant type clarifier | 94645000 |  | 0 | Appointed | RBIG | TBC | TBC | TBC | TBC | TBC | TBC | TBC | N/A | Service provider appointed late 2020/early 2021. All procurement stages achieved
2 | Construction of Mooihoek bulk water supply phase G1.2 |  | Water | TBC | 4.7 Kilometers of bulk water supply pipeline |  |  | 0 | Appointed | RBIG | TBC | TBC | TBC | TBC | TBC | TBC | TBC | N/A | Service provider appointed late 2020/early 2021. All procurement stages achieved
3 | Construction of Mooihoek bulk water supply phase G2 |  | Water | TBC | 4.9 Kilometres of bulk water supply pipeline and construction of 500KL Reinforced Concrete Reservoir |  |  | 0 | Appointed | RBIG | TBC | TBC | TBC | TBC | TBC | 2020-07-23 | 2021-10-23 | N/A | Multiyear project. All procurement stages achieved
4 | Makgeru to Schoonoord BWS |  | Water | TBC | 6.4 Kilometres of bulk water pipeline | 50000000 |  | 0 | Appointed | RBIG | TBC | TBC | TBC | TBC | TBC | 2014-12-01 | 2021-07-02 | N/A | Continuation of project from previous financial years. All procurement stages achieved
5 | Nebo Commission Malekana to Jane Furse bulk Pipeline |  | Water | TBC | 18km of bulk water supply pipeline tested and commissioned |  |  | 0 | Open Tender | RBIG | TBC | TBC | TBC | TBC | TBC | TBC | TBC | N/A | Management to make a decision whether to continue with same previous service providers or restart a process of appointing in order to commission the pipeline
6 | Moutse BWS Project 13 & 14 |  | Water | TBC | 2 mechanical and Electrical (M & E) components installed for the extensions to the Groblersdal Water Treatment Works and Pump station | 80000000 |  |  | Appointed | RBIG | TBC | TBC | TBC | TBC | TBC | 2016-10-12 | 2021-12-31 | N/A | Continuation of project from previous financial years. All procurement stages achieved
7 | Moutse BWS Project ( 7 to 12) |  | Water | TBC | 20 Kilometre of bulk water supply pipeline Tested. |  |  |  | Appointed | RBIG | TBC | TBC | TBC | TBC | TBC | 2013-06-14 | 2021-12-31 | N/A | Continuation of project from previous financial years. All procurement stages achieved
[7 empty] | 0 | 0
WSIG
1 |  |  | Water | TBC | 1 WC/WD Management Strategy | 800000 | 0 | 800000 | Term consultant | SDM |  | 2017-07-10 | 2017-07-24 |  |  | 2017-08-10 | 2018-04-30
2 |  |  | Sewer | TBC | 1x Pump station upgraded | 800000 | 0 | 800000 | Term consultant | SDM |  | 2017-07-10 | 2017-07-24 |  |  | 2017-08-10 | 2018-03-31
3 |  |  | Sewer | TBC | 1x Bulk sewer Feasibility study | 500000 | 0 | 500000 | Term consultant | SDM |  | n/a | n/a |  |  | n/a | 2018-03-31
4 |  |  | Water /Sewer | TBC | 1x Condition assemment and O&M plans developed | 300000 | 0 | 300000 | Term consultant | SDM |  | n/a | n/a |  |  | n/a | 2018-06-30
5 |  |  | Water | TBC | 7 feasibility studies conducted and technical reports developed for Leballo South Villages Phase Two | 5000000 | 0 | 5000000 | Term consultant | SDM |  | n/a | n/a |  |  | n/a | 2017-11-30
[6 empty] | 7400000 | 0 | 7400000
1 |  |  | Water | TBC | 3km bulk pipeline | 30000000 | 30000000 | 0 | Open bid | RBIG |  | 2017-07-02 | 2017-08-01 |  |  | 2017-08-21 | 2018-06-30
2 |  |  | Water | TBC | 1x 5Mℓ reservoir | 18000000 | 18000000 | 0 | Open bid | RBIG |  | 2017-07-09 | 2017-08-08 |  |  | 2017-08-28 | 2018-06-30
3 |  |  | Water | TBC | 4km pipeline | 29000000 | 29000000 | 0 | Open bid | RBIG |  | 2017-07-09 | 2017-08-08 |  |  | 2017-08-28 | 2018-06-30
4 |  |  | Water | TBC | 4km pipeline | 28000000 | 28000000 | 0 | Open bid | RBIG |  | 2017-07-09 | 2017-08-08 |  |  | 2017-08-28 | 2018-06-30
5 |  |  | Water | TBC | 38km rising main tested and commissioned | 12000000 | 12000000 | 0 | N/A | RBIG |  | n/a | n/a |  |  | n/a | 2017-12-20
6 |  |  | Water | TBC | 10Mℓ reservoir and pipeline | 43000000 | 43000000 | 0 | Open bid | RBIG |  | n/a | n/a |  |  | n/a | 2018-06-30
7 |  |  | Water | TBC | 100% M& E components | 60000000 | 60000000 | 0 | Open bid | RBIG |  | n/a | n/a |  |  | n/a | 2018-06-30
8 |  |  | Water | TBC | 100% bulk pipeline and valve chambers |  |  | 0 | Open bid | RBIG |  | n/a | n/a |  |  | n/a | 2018-06-30
[6 empty] | 220000000 | 220000000 | 0
WSIG FUNDED PROJECTS
1 |  |  | Water | TBC | 100% water reticulation network completed | 4500000 | 4500000 | 0 | Term Contractors | WSIG | 2017-11-29 | 2018-01-17 | 2018-01-31 | 2018-02-05 | 2018-02-07 | 2018-02-09 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
2 |  |  | Water | TBC | 5.5km bulk water pipeline constructed | 3000000 | 3000000 | 0 | Term Contractors | WSIG | 2017-11-29 | 2018-01-17 | 2018-01-31 | 2018-02-05 | 2018-02-07 | 2018-02-09 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
3 |  |  | Water | TBC | 100% abstraction point constructed | 3500000 | 3500000 | 0 | Term Contractors | WSIG | 2017-11-29 | 2018-01-17 | 2018-01-31 | 2018-02-05 | 2018-02-07 | 2018-02-09 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
4 |  |  | Water | TBC | 7km pipeline constructed | 2500000 | 2500000 | 0 | Term Contractors | WSIG | 2017-11-29 | 2018-01-17 | 2018-01-31 | 2018-02-05 | 2018-02-07 | 2018-02-09 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
5 |  |  | Water | TBC | 3.5km pipeline constructed | 0 | 0 | 0 | Term Contractors | WSIG | 2017-11-29 | 2017-11-30 | 2017-12-14 | 2017-12-21 | 2017-12-22 | 2018-01-10 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
6 |  |  | Water | TBC | 100% package plant constructed | 3000000 | 3000000 | 0 | Term Contractors | WSIG | 2017-11-29 | 2017-11-30 | 2017-12-14 | 2017-12-21 | 2017-12-22 | 2018-01-10 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
7 |  |  | Water | TBC | 100% package plant constructed | 2700000 | 2700000 | 0 | Term Contractors | WSIG | 2017-11-29 | 2018-01-17 | 2018-01-31 | 2018-02-05 | 2018-02-07 | 2018-02-09 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
8 |  |  | Water | TBC | 7km pipeline constructed | 2000000 | 2000000 | 0 | Term Contractors | WSIG | 2017-12-01 | 2018-01-17 | 2018-01-31 | 2018-02-05 | 2018-02-07 | 2018-02-09 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
9 |  |  | Water | TBC | 2km pipeline constructed | 2000000 | 2000000 | 0 | Term Contractors | WSIG | 2017-12-01 | 2018-01-17 | 2018-01-31 | 2018-02-05 | 2018-02-07 | 2018-02-09 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
10 |  |  | Water | TBC | 33km bulk pipeline tested and commissioned. | 8112800 | 8112800 | 0 | Turnkey | WSIG | 2018-01-17 | 2018-01-19 | 2018-02-02 | 2018-02-06 | 2018-02-08 | 2018-02-10 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
11 |  |  | Water | TBC | 2 water sources developed and technical reports prepared . | 2000000 | 2000000 | 0 | Term Contractors | WSIG | 2018-01-12 | 2018-01-24 | 2018-02-07 | 2018-02-09 | 2018-02-12 | 2018-02-14 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
12 |  |  | Water | TBC | 4 water source developed and no of technical reports prepared. | 1500000 | 1500000 | 0 | Term Contractors | WSIG | 2018-01-17 | 2018-01-23 | 2018-02-06 | 2018-02-08 | 2018-02-09 | 2018-02-12 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
13 |  |  | Water | TBC | 1.7 kilometers of pipeline constructed | 3000000 | 3000000 | 0 | Term Contractors | WSIG | 2017-12-01 | 2018-01-17 | 2018-01-31 | 2018-02-05 | 2018-02-07 | 2018-02-09 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
14 |  |  | Water | TBC | 2.8 kilometers of pipeline constructed | 3000000 | 3000000 | 0 | Term Contractors | WSIG | 2017-12-01 | 2018-01-17 | 2018-01-31 | 2018-02-05 | 2018-02-07 | 2018-02-09 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
15 |  |  | Water | TBC | 2.3 kilometers of pipeline constructed | 2300000 | 2300000 | 0 | Term Contractors | WSIG | 2017-12-01 | 2018-01-17 | 2018-01-31 | 2018-02-05 | 2018-02-07 | 2018-02-09 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
16 |  |  | Water | TBC | 3.2 kilometers of pipeline constructed | 3000000 | 3000000 | 0 | Term Contractors | WSIG | 2018-01-12 | 2018-01-24 | 2018-02-07 | 2018-02-09 | 2018-02-12 | 2018-02-14 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
17 |  |  | Water | TBC | 450 household meters Installed. | 9132786 | 9132786 | 0 | Term Contractors | WSIG | 2018-01-17 | 2018-01-19 | 2018-02-02 | 2018-02-06 | 2018-02-08 | 2018-02-10 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
18 |  |  | Water | TBC | One package plant refurbished in Tjibeng . | 3500000 | 3500000 | 0 | Term Contractors | WSIG | 2017-10-18 | 2017-11-14 | 2017-12-05 | 2018-01-11 | 2018-01-12 | 2018-01-16 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
19 |  |  | Water | TBC | One of water source developed | 3000000 | 3000000 | 0 | Term Contractors | WSIG | 2018-01-17 | 2018-01-23 | 2018-02-06 | 2018-02-08 | 2018-02-09 | 2018-02-12 | 2018-06-15 | Not Achieved | Late Appointments of Consultants
20 |  |  | Sewer | TBC | 334 VIDP Sanitation units constructed | 4500000 | 4500000 | 0 | Open Bid | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Contractor appointed
21 |  |  | Water | TBC | 100% refurbishment of Thabampshe water pump station ( 2 pumps, motors and electrical panel completed and replacement of valves and testing of rising main | 3700000 | 3700000 | 0 | Term Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Contractor is already on site
22 |  |  | Water | TBC |  | 1509362.73 | 1509362.73 |  | Term Contractors | WSIG | 2018-01-17 | 2018-01-23 | 2018-02-06 | 2018-02-08 | 2018-02-09 | 2018-02-12 | 2018-06-15 | Not Achieved
[6 empty] | 71454948.73 | 71454948.73 | 0
WSIG FUNDED PROJECTS (2016/2017)
1 |  |  | Water | TBC | Drilling, testing and equipping of two boreholes, construction of 3800m of 75mm diameter reticulation network with stand pipes,1200m of 90mm diameter rising main, installation of 100kl elevated steel tank | 4045962 | 4045962 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
2 |  |  | Water | TBC | Construction of 200kl elevated steel tank and the 3000m length of 65mm diameter pipeline. | 2684752 | 2684752 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
3 |  |  | Water | TBC | Development water source, testing, equipping of two boreholes, construction 2 500m length of 65mm diameter pipeline and installation of steel tank. | 2685773 | 2685773 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
4 |  |  | Water | TBC | Testing and equipping of existing borehole, construction of ±3500m of 75mm diameter reticulation network with stand pipes, 1200m of 90mm diameter rising main with four Jojo Tanks. | 3174150 | 3174150 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
[6 empty] | 12590637 | 12590637
|  |  | Water | TBC |  | 1265831 | 1265831 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
|  |  | Water | TBC |  | 0 | 0 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
|  |  | Water | TBC |  | 210000 | 210000 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
|  |  | Water | TBC |  | 1242860 | 1242860 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
|  |  | Water | TBC |  | 1075579 | 1075579 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
|  |  | Water | TBC |  | 2318157 | 2318157 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
|  |  | Water | TBC |  | 447933.27 | 447933.27 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
|  |  | Water | TBC |  | 194054 | 194054 | 0 | Terms Contractors | WSIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Contractor on site
|  |  | Water | TBC |  | 4200000 | 4200000 | 0 | Terms Contractors | WSIG | 2018-01-17 | 2018-01-23 | 2018-02-06 | 2018-02-08 | 2018-02-09 | 2018-02-12 | 2018-06-15 | Not Achieved | None
[6 empty] | 10954414.27 | 10954414.27 | 0
8 | Tukakgomo RDP Section Borehole |  | Water | TBC | 7 Km of water distribution network constructed and 735 water meters | R9, 000, 000. 00 |  | 0 | Open Tender | WSIG | 2021-04-28 | 2021-05-09 | 2021-05-28 | 2021-06-03 | 2021-06-21 | 2021-07-02 | 2022-01-17 | N/A | PSP Appointed
9 | Nkosini Water Supply & Package Plant |  | Water | TBC | 3.5km of pipeline and 1 protection of abstraction and sealing of 1 reservoir | R8, 000, 000. 00 |  | 0 | Open Tender | WSIG | 2021-04-28 | 2021-05-09 | 2021-05-28 | 2021-06-03 | 2021-06-21 | 2021-07-02 | 2021-12-10 | N/A | PSP Appointed
10 | Laersdrift Water Supply Intervention |  | Water | TBC | 8 km reticulation network, 22 communal stand pipes and 1 storage tank | R9, 000, 000. 00 |  | 0 | Open Tender | WSIG | 2021-04-28 | 2021-05-09 | 2021-05-28 | 2021-06-03 | 2021-06-21 | 2021-07-02 | 2022-02-24 | N/A | PSP Appointed
11 | Phokwane/Brooklyn Water Supply |  | Water | TBC | 3km of rising main and 1 elevated tank | R4, 000, 000. 00 |  | 0 | Open Tender | WSIG | 2021-05-05 | 2021-05-23 | 2021-06-25 | 2021-07-12 | 2021-07-26 | 2021-08-06 | 2022-02-03 | N/A
12 | Legolaneng VDIP |  | Sanitation | TBC | 440 VDIP | R7, 000, 000. 00 |  | 0 | Open Tender | WSIG | 2021-05-12 | 2021-06-06 | 2021-07-02 | 2021-07-19 | 2021-08-04 | 2021-08-20 | 2022-02-28 | N/A | Project to be implemeted in house
13 | Maebe Drilling and Equipping of Borehole |  | Water | TBC | 1 Pump station constructed and 1 Reverse Osmosis Water Treatment Package Plant and 1 storage tank installed | R13, 000, 000. 00 |  | 0 | Appointed | WSIG | N/A | N/A | N/A | N/A | N/A | 2021-04-15 | 2021-10-20 | N/A | PSP Appointed
MIG
14 | Ephraim Mogale VIP Backlog Programme (Phase2,3 CO ) |  | Sanitation | MIG/LP/1622/W/13/15 |  | 17000000 |  |  | Open Tender | MIG | 2021-05-14 | 2021-05-31 | 2021-06-15 | 2021-06-22 | 2021-06-25 | 2021-06-30 | 2021-11-30
15 | Elias Motswaledi VIP Backlog Programme (Phase 2,3 CO) |  | Sanitation | MIG/LP/1998/S/14/18 |  | 17000000 |  |  | Open Tender | MIG | 14/05/2021 | 2021-05-31 | 2021-06-15 | 2021-06-22 | 2021-06-25 | 2021-06-30 | 2021-11-30
16 | Zaaiplaas Village Reticulation Phase 2 (Vlakfontein, Sovolo and remaining villages) - CO |  | Water | MIG/LP/1449/W/12/14 |  | 14029981 |  |  | Open Tender | MIG | 2021-05-13 | 2021-05-25 | 2021-06-11 | 2021-06-18 | 2021-06-23 | 2021-06-30 | 2022-01-30
17 | Makhuduthamaga VIP Backlog Programme (Phase 2,3 CO) - Incl. Malokela, Motsiri, Schoornoord |  | Sanitation | MIG/LP/1996/S/14/18 |  | 17000000 |  |  | Open Tender | MIG | 2021-05-14 | 2021-05-31 | 2021-06-15 | 2021-06-22 | 2019-04-16 | 2021-06-30 | 2021-11-30
18 | Ga -Mogashoa(Senkapudi) and Ga- Mogashoa(Manamane) | 35106446020MGH04ZZWD | Water | MIG/LP/2264/W/18/20 |  | 4762404.21 |  |  | Open Tender | MIG | 2021-05-14 | 2021-05-31 | 2021-06-15 | 2021-06-22 | 2021-06-25 | 2021-06-30 | 2021-11-30
19 | NSD07 Regional Water Scheme Construction of Concrete Reservoirs | 35106446020MGH05ZZWD | Water | MIG/LP/2265/W/18/21 |  | 28686829 |  |  | Open Tender | MIG | 2021-05-28 | 2021-05-31 | 2021-06-18 | 2021-07-23 | 2021-06-28 | 2021-07-01
20 | De Hoop/Nebo Plateau/Schoonoord Water Scheme Villages: Makgeru, Ga Ratau & Matekane | 35106446020MGH06ZZWD | Water | MIG/LP/2287/W/19/22 |  | 57594084.45 |  |  | Open Tender | MIG |  | 2021-06-01 | 2021-07-19 | 2021-07-23 | 2021-07-29 | 2019-08-06 | 2022-06-30
21 | Fetakgomo VIP Backlog Programme (Phase 2,3 CO) |  | Sanitation | MIG/LP/1619/S/13/15 |  | 2000000 |  |  | Open Tender | MIG |  | 2021-05-31 | 2021-06-15 | 2021-06-22 | 2021-06-25 | 2021-06-30 | 2021-11-30
22 | Tubatse VIP Backlog Programme (Phase 2,3 CO) |  | Sanitation | MIG/LP/1849/W/14/16 |  | 17000000 |  |  | Open Tender | MIG |  | 2021-05-31 | 2021-06-15 | 2021-06-22 | 2021-06-25 | 2021-06-30 | 2021-11-30
23 | Motlailana & Makgemeng Water Supply | 35106446020MGG65ZZWD | Water |  |  | 28455196 |  |  | Open Tender | MIG |  | 2021-05-28 | 2021-06-14 | 2021-06-25 | 2021-06-25 | 2021-06-30 | 2021-10-30
24 | Malekana Regional Water Scheme | 35106446020MGH07ZZWD | Water | MIG/LP/2263/W/18/21 |  | 132807655.2 |  |  | Open Tender | MIG |  | 2021-05-28 | 2021-06-14 | 2021-06-25 | 2021-06-25 | 2021-06-30 | 2022-03-30
25 | Lebalelo South connector pipes and reticulations |  | Water | MIG/LP/2183/W/17/20 |  | 27626648.09 |  |  | Open Tender | MIG |  | 2021-05-31 | 2021-06-15 | 2021-06-22 | 2021-06-25 | 2021-06-30 | 2021-10-29
26 | Lebalelo South: Phase 3 (Ga- Maroga and Motlolo Bulk and Reticulation Infrastructure) | 35106446020MGH08ZZWD | Water | MIG/LP/2262/W/18/21 |  | 119597202.05 |  |  | Open Tender | MIG |  | 2021-05-31 | 2021-06-15 | 2021-06-22 | 2021-06-25 | 2021-06-30 | 2022-03-30
OWN FUNDING
27 | External PMU Support to SDM |  | Water and Sanitation |  |  | 20000000 | Equitable share |  | Open tender | Own funding | 2021-05-31 | 2021-06-01 | 2021-07-19 | 2021-07-23 | 2021-07-29 | 2019-08-06 | 2022-06-30
28 | Integrated Programme \ Project Management System |  | Water and Sanitation |  |  | 4000000 | Equitable share |  | Open tender | Own funding | 2021-05-31 | 2021-06-01 | 2021-07-19 | 2021-07-23 | 2021-07-29 | 2019-08-06 | 2022-06-30
29 | Panel of Consultants for water and sanitation |  | Water and Sanitation |  |  | N/A | Equitable share |  | Open tender | Own funding | 2021-05-31 | 2021-06-01 | 2021-07-19 | 2021-07-23 | 2021-07-29 | 2019-08-06 | 2022-06-30
Formulas:
Bid Evaluation Committee (BEC) = [TBC]+5
Bid Adjudication Committee(BAC) = [Bid Evaluation Committee (BEC)]+2
Appointment Letter/Contract Sign Date = [Bid Adjudication Committee(BAC)]+2
TBC = [BSC]+2
TBC = [TBC]+14
Note on J80: Bongani Mtshali: 8CE Contract if taken as a whole and 5, 6 CE and may be applied if contract is split into 5 village contracts
Note on J81: Bongani Mtshali: 8CE Contract if taken as a whole and 5, 6 CE and may be applied if contract is split into 5 village contracts
Note on J82: Bongani Mtshali: 8CE Contract if taken as a whole and 5, 6 CE and may be applied if contract is split into 5 village contracts
Note on J83: Bongani Mtshali: 8CE Contract if taken as a whole and 5, 6 CE and may be applied if contract is split into 5 village contracts
Note on J84: Bongani Mtshali: 8CE Contract if taken as a whole and 5, 6 CE and may be applied if contract is split into 5 village contracts
Note on J85: Bongani Mtshali: 8CE Contract if taken as a whole and 5, 6 CE and may be applied if contract is split into 5 village contracts
Note on J86: Bongani Mtshali: 8CE Contract if taken as a whole and 5, 6 CE and may be applied if contract is split into 5 village contracts
Note on J87: Bongani Mtshali: 8CE Contract if taken as a whole and 5, 6 CE and may be applied if contract is split into 5 village contracts
Note on J88: Bongani Mtshali: 8CE Contract if taken as a whole and 5, 6 CE and may be applied if contract is split into 5 village contracts
Note on J89: Bongani Mtshali: 8CE Contract if taken as a whole and 5, 6 CE and may be applied if contract is split into 5 village contracts
Note on J90: Bongani Mtshali: 8CE Contract if taken as a whole and 5, 6 CE and may be applied if contract is split into 5 village contracts
Note on J91: Bongani Mtshali: 8CE Contract if taken as a whole and 5, 6 CE and may be applied if contract is split into 5 village contracts
Note on J92: Bongani Mtshali: 8CE Contract if taken as a whole and 5, 6 CE and may be applied if contract is split into 5 village contracts