## Sheet1
MEASURABLE OBJECTIVE | STRATEGY | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2015/2016 | INDICATORS | ANNUAL TARGET 2016/2017 | Q1 | Q2 | Q3 | Q4 | EVIDENCE | BUDGET 2016/2017 | IMPACT
FINANCAL VIABILITY
To ensure sufficient reserve funds to address asset renewal by contributing R35m to CRR by end of June 2017 | Reserve VAT refunds and interest on investments for purposes of CRR |  |  |  | Capital Replacement Reserve fund | R30m | Rand value invested towards CRR | R35m by end June 2017 *Q1=R5m *Q2=R15m *Q3=R25m *Q4=R35m | [5 empty] | 0
To ensure 100% Preparation of a credible 2017/18 budget at 30 May 2017 | To have a functioning budget steering committee |  |  |  | Budget preparation and implementation | 100% 2015/2016 approved budget | Percentage credible budget prepared. | 100% credible budget prepared: 1 budget timetable(10%)2. Roll over 2014/2015 (10%) 2. 3. Functionality of budget steering committee (8%) 4.Amendment of roll overs. (10%).5.Mid-year Adjustment of budget (12%) 5.. Reviewed budget related policies(20%) 6. Draft budget (20%) 7.Cash backed budget(10%) | [5 empty] | 0
To ensure 80% improved audit opinion for 2016/17 financial year. | To fully implement the audit action plan. |  |  |  | Operation Clean Audit | Unqualified audit opinion | Percentage reduction in matters of emphasis | 100% reduction of matters of emphasis *clearance of 14/15 matters of emphasis *monitoring of the 15/16 audit process *clerance of 15/16 matters of emphasis | [5 empty] | 350000
To generate and submit 30 finance compliance reports by June 2017 | To utilise the finance intern as compliance officer |  |  |  | Finance Compliance Reports | 2014/15 AFS 2014/15 Section 52; 71 and 72 reports | Number of finance compliance reports generated and submitted | 30 finance compliance reports generated and submitted (12x Section 71, 4x Section 52, 12x Supply Chain, 1x Section 72, 1xAFS) | [5 empty] | 0
To ensure 100% implementation of SCOA activities in terms of the implementation plan by 30 June 2017 | To have a functioning Mscoa commitee |  |  |  | Municipal Standard Chart of Accounts (mSCOA) | Council resolution 2014/2015 & Treasury circular | Percentage of activities on SCOA implementation plan achieved | 100% achievement of SCOA implementation plan *scoa transaction selection 15%; building of SCOA ledger 15%; align old chart to new SCOA 20%; training and budget inputs from departments 10%; final draft on SCOA submitted to council 10%; final full SCOA release 10%; testing 20% | [5 empty] | R1 200 000
100% accounting of assets and inventory by 30 June 2017 | Sound financial management. |  |  |  | 1. Asset management 2. Asset management plan | Manual GRAP Compliant Fixed asset register | % accounting of assets and inventory | 100% accounting of assets 1) safeguarding movable assets 20%, 2) valuation 30%, 3) records keeping 10%) | Accounting for assets. 1.Safeguarding of assets ( verification of assets) 2. Valuation (run depreciation) 3.Records keeping. | Accounting for assets. 1.Safeguarding of assets ( verification of assets) 2. Valuation (run depreciation), 3.Records keeping. | Accounting for assets. 1.Safeguarding of assets ( verification of assets) 2. Valuation (run depreciation), 3.Records keeping. 4.Migration of data to electronic System. | 100% valuation, records keeping, safe Guarding & disposal 100%-activation of electronic Asset Managent Module Year end veification.Impairment tests.Review usefull lifes. Review residual values. Reconcile FAR to G/L.Update FAR Prepare notes to AFSs | Updated GRAP compliant asset register and reconciliation of PPE | R1 900 000
To achieve 75% revenue collection rate by June 2017 | Cost Recovery | human resource, functional meters, credit control policy | Revenue collection reports | Improved financial viability | Revenue management | 65% of billed customers collected | Percentage revenue collection rate achieved | 75% revenue collection rate achieved | 67% collection rate | 69% collection rate | 72% collection rate | 75% collection rate | 1)Customer payment report | 8400000
To undertake 100% feasibility study of Prepaid meters by June 2017 | By conducting feasibity study, and installation of the meters | Feasibility study report* TVR1 *TVR2 | Prepaid meters installed | Increase in revenue collection through payment received in advance | PPP project (transactional advice) | Council resolution | Percentage feasibility study of Prepaid meters done | 100% feasibility study of Prepaid meters done | 100% Feasibility study*Advert for PPP | 1) Appointment of pre paid meter contractor 2)20% Prepaid (SMART)meters installed | 1) 50% Prepaid (SMART) meters installed | 1) 80% Prepaid (SMART) meters installed | Feasibility report & Pre-paid Meter report | 8500000
To cleanse 100% customer data in the three towns (Burgersfort, Marble Hall & Groblersdal) by June 2017 | By auditing data and doing physical verification.By updating customer information on the biling system | 1. Valuation roll and deeds office report 2. Human and financial resources | 1. Updated customer database. | Improved revenue and reliable customer data | Customer Data cleansing | Current non verifiable customer data | Percentage customer data cleansed | 100% customer data cleansed | 50% customer data cleansed for three towns (Groblersdal, Burgersfort and Marble Hall) | 100% customer data cleansed for three towns (Groblersdal, Burgersfort and Marble Hall) | 1)100% updating of cleansed data on the system 2) Physical verifications done for 50% towns | 100% physical verification done on towns | Cleansed customer data report | 2000000
To ensure that 100% creditors are paid within 30 days by June 2017 | Centralisation of invoice receipting and monitoring of the payment process by CFO |  |  |  | Expenditure management | Payment rate at 43 days | Percentage payment of creditors within 30 days of correct invoice date | 100% creditors paid within 30 days of correct invoice date | [5 empty] | 0
To ensure 100% development and implementation of the procurement plan by 30 June 2017 | Implementation of forward plans |  |  |  | Procurement Plan | IDP/BUDGET | Percentage development and implementation of procurement plans | 1) 100% development and implementation of 2016/17 procurement plan *Development of procurement plan =40% * Implementation of procurement plan = 60% | [5 empty] | 350000
To ensure 100% reduction of UIF expenditure by 30 June 2017 | *Due diligence on all projects *Pool of officials for SCM commitees and training of committee members |  |  |  | Acquisition Management | R300M reported irregular expenditure | Percentage reduction of irregular expenditure from baseline | 100% reduction of irregular expenditure from baseline (adherence to full SCM policies and regulations 100%) | [5 empty] | 500000

## workings
MID TERM 2016/2017 SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN REPORT
BUDGET AND TREASURY
MEASURABLE OBJECTIVE | STRATEGY | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2015/2016 | INDICATORS | ANNUAL TARGET 2016/2017 | MID-TERM TARGET | PROGRESS (Achieved/ not achieved) | ACTUAL PROGRESS | CHALLENGE | REMEDIAL ACTION | EVIDENCE | BUDGET 2016/2017 | IMPACT
2016/2017 SDBIP KPA: FINANCIAL VIABILITY
FINANCAL VIABILITY
To ensure sufficient reserve funds to address asset renewal by contributing R35m to CRR by end of June 2017 | Reserve VAT refunds and interest on investments for purposes of CRR | VAT Refunds and Interest earned on investment | Call account investment | Assured Financial Viability | Capital Replacement Reserve fund | R30m | Rand value invested towards CRR | R35m by end June 2017 *Q1=R5m *Q2=R15m *Q3=R25m *Q4=R35m | R15m invested by end of December 2016 | Achieved | An amount of R22 055 988 was invested during the first six months being Interest received from July to November and VAT amount for September and December | None | None | Investment register/ certificates | 0 | Financial Viability
To ensure 100% Preparation of a credible 2017/18 budget at 31 May 2017 | To have a functioning budget steering committee | Human resource | Credible Budget | Improved Financial Viability for Services delivery | Budget preparation and implementation | 100% 2015/2016 approved budget | Percentage credible budget prepared. | 100% credible budget prepared: 1 budget timetable(10%)2. Roll over 2014/2015 (10%) 2. 3. Functionality of budget steering committee (8%) 4.Amendment of roll overs. (10%).5.Mid-year Adjustment of budget (12%) 5.. Reviewed budget related policies(20%) 6. Draft budget (20%) 7.Cash backed budget(10%) | Approved budget timetable (10% ). Roll over application 2014/2015 (10%). Facilitation of the budget steering committee meetings(6%). (Amendment for roll overs(10%) | Not Achieved | Budget/IDP timetable approved by council and roll over application done. No steering committee meetings were held during the first six months | Competing work schedule (Audit process and Mscoa workshops) made it difficult to have a budget steering committee meetings | Two steering committee meetings will be arranged in February 2017 | Approved budget and council resolutions | 0 | Financial Viability
To ensure 100% improved audit opinion for 2016/17 financial year. | To fully implement the audit action plan. | Audit Action Plan and Human Resources | Improved audit opinion | Good governance and sound financial management | Operation Clean Audit | Unqualified audit opinion | Percentage reduction in matters of emphasis | 100% reduction of matters of emphasis *clearance of 14/15 matters of emphasis *monitoring of the 15/16 audit process *clearance of 15/16 matters of emphasis | 100% reduction of 14/15 emphasis and 100% development of draft audit action plan for 15/16 audit | Achieved | 100% reduction of matters of emphasis. The 14/15 audit process was monitored successfully as unqualified audit report was received. In the process of finalising the action plan for 2015/16 audit | None | None | Audit Action Plan Progress Report | 350000 | Good governance and sound financial management
To generate and submit 30 finance compliance reports by June 2017 | To utilise the finance intern as compliance officer | Compliance checklist and Human Resources | Compliance reports performed and submitted on time | Sound financial management | Finance Compliance Reports | 2014/15 AFS 2014/15 Section 52; 71 and 72 reports | Number of finance compliance reports generated and submitted | 30 finance compliance reports generated and submitted (12x Section 71, 4x Section 52, 12x Supply Chain, 1x Section 72, 1xAFS) | 16 (6 Sec 71, 6 SCM Report, 2 x Sect 52 and 72 Report). 1 X AFS | Achieved | 16 Financial reports prepared (6 Sec 71, 6 SCM Reports, 2 X Section 52 and 72 reports and AFS) | None | None | Financial reports | 0 | Sound Financial Viability
To ensure 100% implementation of SCOA activities in terms of the implementation plan by 30 June 2017 | To implementing Mscoa implementation plan | SCOA implementation plan, Human Resources | SCOA compliance chart of accounts | Successful implementation of SCOA | Municipal Standard Chart of Accounts (mSCOA) | Council resolution 2014/2015 & Treasury circular | Percentage of activities on SCOA implementation plan achieved | 100% achievement of SCOA implementation plan *mSCOA transaction selection 15%; building of SCOA ledger 15%; align old chart to new SCOA 20%; training and budget inputs from departments 10%; final draft on SCOA submitted to council 10%; final full SCOA release 10%; testing 20% | *60% implementation of the mSCOA plan. * MSCOA awareness. * MSCOA transaction selection. upgrading of server . * Align Old chart to new SCOA . *Training and workshops. *Inputs from department . *Building of mSCOA Ledger . | Achieved | 60% implementation of mSCOA plan achieved. (mSCOA awareness held, mSCOA transaction selected, server purchased, alignment of old chard to new chart done ,Inputs from departments sourced through mSCOA sub technical committee and technical committee. mSCOA ledger is being built . Trainings and workshop are being attended) | Time constraints and decision that needs to be taken on continuation or discontinuation of financial system | Fast track the decision making so that the mSCOA processes can unfold without hic-ups | mSCOA implementation plan report | R1 200 000
To account 100% on assets and inventory by 30 June 2017 | Sound financial management. | Asset management | Asset and project register | GRAP compliant asset register 2. Updated Project register | 1. Asset management 2. Asset management plan 3. Capex reconciliation | 1. Manual GRAP Compliant Fixed asset register 2. Project register | % accounting of assets and inventory % Capex accounts reconciled | 100% accounting of assets 1) safeguarding movable assets 20%, 2) valuation 30%, 3) records keeping 10%) 4) Unbundling 20% 5) Physical verification 20% | 50% accounting of assets and inventory, 1) safeguarding movable assets 10%, 2))Unbundled Assets 10%, 3) valuation 10%, 4) records keeping 4%) 5) Physical verification 16% | Achieved | 50% accounting for assets and inventory achieved (1. Movable FAR updated, updated inventory register (purchases, requisitions, and Stock Count). 2. Five projects are completed and unbundling process has started. 3. Valuation is done( Depreciation is calculated. Projects Registers (WIP, Retention, Commitments and Additions) is updated, Capitalisation is up to date) 4. All records are kept safe. 5. Verification is currently in progress) | None | None | Updated GRAP compliant asset register and reconciliation of PPE | R1,900,000 | Sound financial management
To achieve 75% revenue collection rate by June 2017 | Cost Recovery | human resource, functional meters, credit control policy | Revenue collection reports | Improved financial viability | Revenue management | 65% of billed customers collected | Percentage revenue collection rate achieved | 75% revenue collection rate achieved | 69% collection rate | Achieved | Collection rate of 75.30% achieved (Billed R24 342 158.18 and Collected R18 422 841.46. ) | N/A | N/A | 1)Customer payment report | 8400000
To undertake 100% feasibility study and installation of Prepaid meters by June 2017 | By conducting feasibility study, and installation of the meters | Feasibility study report* TVR1 *TVR2 | Prepaid meters installed | Increase in revenue collection through payment received in advance | PPP | Council resolution | Percentage feasibility study and installation of Prepaid meters done | 100% feasibility study and installation of Prepaid meters done | 25% Feasibility study *Advert for PPP1. * Appointment of pre paid meter contractor *25% Prepaid (SMART)meters installed | Not Achieved | 35% feasibility study completed but the study was extended to 1 year completion period instead of the 6 months that was initially planned for. The study will be completed by June 2017,. The appointment of a prepaid contractor will only be done in the next financial year and therefore installation will also be done after appointment of the service provider. | Target dates as per project implementation plan differs from targets as per SDBIP | Change SDBIP in Budget adjustment process | Feasibility report & Pre-paid Meter report | 8500000
To cleanse 100% customer data in the three towns (Burgersfort, Marble Hall & Groblersdal) by June 2017 | By auditing data and doing+D9+8:11+D9+8:11+D9+8:11+D9+8:11+D9+8:11+D9+8:11+D9+8:11+D9+8:11+D9+8:11+D9+8:11+8:11+7:11+6:11+5:11+8:11 | 1. Valuation roll and deeds office report 2. Human and financial resources | 1. Updated customer database. | Improved revenue and reliable customer data | Customer Data cleansing | Current non verifiable customer data | Percentage customer data cleansed | 100% customer data cleansed | 100% customer data cleansed for three towns (Groblersdal, Burgersfort and Marble Hall) | Not Achieved | Cleansing of customer data not yet completed (30% done). The Audit has began and is done for Groblersdal town, two towns are remaining. | Audit is done in-house, customers are reluctant to submit some personal details | Text messages have been sent out to inform the public of the awareness however further communication is required | Cleansed customer data report | 2000000
To ensure that 100% creditors are paid within 30 days by June 2017 | Centralisation of invoice receipting and monitoring of the payment process by CFO | Procedure manual on centralisation of invoice receiving | Monitor the received invoices | Ensure Centralisation of Invoice receiving & monitoring | Centralisation of Invoice receiving & monitoring | Payment rate at 43 days | Percentage payment of creditors within 30 days of correct invoice date | 100% creditors paid within 30 days of correct invoice date | Receiving of invoices in a centralise point ,and ensure that 100%creditors are paid within 30days | Achieved | 100% creditors paid within 30 days of correct invoice date | None | None | Invoice Register and Payment register | 0
To ensure 100% development and implementation of the procurement plan by 30 June 2017 | Implementation of forward plans | Procurement schedules/programmes from End User Departments. | Institutional Procurement Plan developed. | Improved service delivery. Improved Spending. | Procurement Plan | IDP/BUDGET | Percentage development and implementation of procurement plans | 1) 100% development and implementation of 2016/17 procurement plan *Development of procurement plan =40% * Implementation of procurement plan = 60% | 100% developed procurement plan. 100% implementation of activities within the quarter | Achieved | 100% Procurement plan developed and implemented. (The procurement plan was approved by council and all projects for the first six months implemented) | None | None | Procurement plan progress report | 350000
To ensure 100% reduction of UIF expenditure by 30 June 2017 | *Due diligence on all projects *Pool of officials for SCM committees and training of committee members | Monthly UIF report. | Reduction of UIF | 100% reduction of UIF | Acquisition Management | R300M reported irregular expenditure | Percentage reduction of irregular expenditure from baseline | 100% reduction of irregular expenditure from baseline (adherence to full SCM policies and regulations 100%) | 100% reduction of Irregular Expenditure | Achieved | 100% reduction of irregular expenditure as no irregular expenditure was identified as incurred during the first six months | None | None | Monthly reports on UIF | 500000

## work
100% accounting of assets and inventory by 30 June 2017 | Sound financial management. | Asset management | Asset and project register | GRAP compliant asset register 2. Updated Project register | 1. Asset management 2. Asset management plan 3. Capex reconciliation | 1. Manual GRAP Compliant Fixed asset register 2. Project register | % accounting of assets and inventory % Capex accounts reconciled | 100% accounting of assets 1) safeguarding movable assets 20%, 2) valuation 30%, 3) records keeping 10%) | Accounting for assets. 1.Safeguarding of assets ( verification of assets) 2. Valuation (run depreciation, update project registers) 3.Records keeping. | Accounting for assets. 1.Safeguarding of assets ( verification of assets) 2. Valuation (run depreciation, update project registers,), 3.Records keeping. | Accounting for assets. 1.Safeguarding of assets ( verification of assets) 2. Valuation (run depreciation, update project registers), 3.Records keeping. 4.Migration of data to electronic System. | 100% valuation, records keeping, safe Guarding & disposal 100%-activation of electronic Asset Managent Module Year end veification.Impairment tests.Review usefull lifes. Review residual values. Reconcile FAR to G/L.Update FAR Prepare notes to AFSs | Updated GRAP compliant asset register, Updated project register and reconciliation of PPE | R1 900 000