## Sheet1
2016/2017 SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
OBJECTIVE | STRATEGIES | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2015/2016 | INDICATORS | ANNUAL TARGET 2016/2017 | Q1 | Q2 | Q3 | Q4 | EVIDENCE | BUDGET 2016/17 | IMPACT
To develop 100% three (3) year rolling plan by July 2017 | By developing an audit universe. | Human Resources | Three [3] year and Annual Internal Audit Plan | Improved internal controls | 3 Years rolling Plan | Three [3] year rolling Plan | Percentage development of the Three(3) Years rolling Plan | 100% development of the Three(3) Years rolling Plan | 100% development of Three Year rolling Plan | 0% | 0% | 0% | Approved Three Year rolling Plan | R0 | Improved Good Governance and Financial Management
To monitor 100% the implementation of AG findings for 2015/2016 by June 2017 | By developing audit action plans for monitoring by Audit Steering Committee. | Human and Financial Resources | External Audit Report | Improved audit opinion | Operation Clean Audit | 2015/16 AG Implementation report | Percentage monitoring of 2015/2016 AG findings | 100% monitoring of 2015/2016 AG findings | 100% monitoring of 2015/2016 AG findings | 100% monitoring of 2015/2016 AG findings | 100% monitoring of 2015/2016 AG findings | 100% monitoring of 2015/2016 AG findings | Audit Action plan,Agenda/Minutes/Reports | R0
To facilitate 100% payments of auditor general South Africa fees by March 2017 | By facilitating external audit work claims of Auditor General. | Human and Financial Resources | Proof of Payment | Improved turnaround time for payment processed | External Auditor's payments | Payments of AGSA payments done | Percentage payments of auditor general South Africa fees facilitated | 100% payments for external audit fees for 2015/2016 facilitated* 50% development of payment schedule *50% reconciliation of payments | 100% payment facilitation and monitoring of payments of auditor general South Africa | 100% payment facilitation and monitoring of payments of auditor general South Africa | 100% payment facilitation and monitoring of payments of auditor general South Africa | 100% payment facilitation and monitoring of payments of auditor general South Africa | Claim schedule Register/Proof of payments | 800000
To issue four (4) municipal performance information reports by July 2017 | By conducting audit reviews on the adequacy and effectiveness of performance information | Human Resources | Performance Reports | High level of Productivity | Performance Audit | Performance Audit Reports issued | Number of municipal performance information reports issued | 4 municipal performance information reports issued | 1 Performance Audit report | 1 Performance Audit report | 1 Performance Audit report | 1Performance Audit report | Performance Audit Reports | R0
To review 42 internal controls by June 2017 | By conducting audit reviews on the adequacy and effectiveness of internal controls. | Human and Financial Resources | Regularity Audit reports | Improved Internal Controls | Regularity Audit | Regularity Audit reports issued and Risk Assessment report | Number of regularity audit conducted | 38 Regularity audits issued | 8 Regularity audits issued | 8 Regularity audits issued | 16 Regularity audits | 6 Regularity audits issued | Regularity Audit Reports | R800 000.00
|  | Human Resources and Financial Resources | ICT Audit reports | Reliable ICT Environment | ICT Audits | ICT Audit reports issued and Risk assessment report | Number of ICT audits conducted | 4 ICT Audit reports for 2015-2016 issued | 1 ICT Audit report | 1 ICT Audit report | 1 ICT Audit report | 1 ICT Audit report | ICT Audit Reports
To execute 100% Ad Hoc audit by June 2017 | By conducting assignments requested by management and investigation(s) | Human Resources and Financial Resources | Ad Hoc Management Report | Improved Internal Controls | Ad Hoc Audits | Ad Hoc Management Reports | Percentage of Ad Hoc audit executed | 100% Ad Hoc report issued 2015-2016 *50% assignment executed *50%investigation reports executed | 100% Ad hoc report issued | 100% Ad hoc report issued | 100% Ad hoc report issued | 100%Ad hoc report issued | Ad-hoc Reports
To facilitate 100% activities of audit committee on a quarterly basis by June 2017 | By co-ordinating and facilitating Audit Committee activities. | Human Resources and Financial Resources | Reports | Effective Oversight | Audit Committee | Reports | Percentage activities of audit committee facilitated | 100% activities of audit committee facilitated | 100% activities of audit committee facilitated | 100% activities of audit committee facilitated | 100% activities of audit committee facilitated | 100% activities of audit committee facilitated | Minutes/Agenda/AC Reports | R500 000.00
To conduct one (1) institutional strategic risk assessment and 4 risk registers reviewed quarterly by July 2017 | Conduct Risk Assessment | Human Resources | Strategic Risk register | Improved Risk Management | Strategic Risk Assessment | 2014/2015 FY Strategic Risk Registers | Number of strategic risk assessments conducted and reviewed | 1 strategic risk assessments conducted and 4 risk registers reviewed quarterly | 1 strategic risk assessments conductedand 1 risk register reviewed | 1 strategic risk register reviewed | 1 strategic risk register reviewed | 1 strategic risk register reviewed | 1 strategic Risk Register 4 Reviewed Risk registers and quarterly reports | 0
To conduct seven (7) operational risk assessments and review 28 risk registers by July 2017 | Conduct Operational Risk Assessment | Human Resources | Operational risk register | Improved Risk Management | Operational Risk Assessment | 2014/2015 FY Operational Risk Registers | Number of Operational risk assessments conducted and reviewed | 7 Operational risk assessments conducted and 28 risk registers review | 7 Operational risk assessments conducted and 7 risk registers reviewed | 7 risk registers reviewed | 7 Operational risk registers reviewed | 7 Operational risk registers reviewed | 7 New Operational risk registers; 28 Reviewed risk registers and quarterly reports. | 0
To conduct 10 project risk assessments by June 2017 | Conduct Projects Risk Assessment | Human Resources | Project risk assessment report | Improved Risk Management | Project Risk Assessment | 2014/2015 FY Projects Risk assessment Reports | Number of Projects risk assessments conducted | 10 Projects risk assessments conducted | 2 Projects risk assessments conducted | 3 Projects risk assessments conducted | 2 Projects risk assessments conducted | 3 Projects risk assessments conducted | 10 Projects Risk Asessment reports | 0
To facilitate 100% insurance coverage for municipal assets | Appraise the adequacy of the current assets insurance | Human Resources and Financial Resources | Insurance policy contract | Idemnified Loss | Insurance Management | 2015/2016 FY Assets Insurance Policy contract | Percentage coverage of insurable assets | 100% Coverage of Insurable Assets | 100% quarterly updating and addition of new assets | 100% quarterly updating and addition of new assets | 100% quarterly updating and addition of new assets | 100% quarterly updating and addition of new assets | Assets Insurance Policy Contract Insurance policy endorsements | R1,300,000.00
To facilitate 100% finalisation of insurance claims within 30 days by June 2017 | Review Insurance Cover and contract | Human Resources and Finanical Resources | Insurance Claims Report | Loss management | Insurance claims | 2015/2016 insurance claims report | percentage facilitation of insurance claims within 30 days | 100% of insurance claims facilitated within 30 days | 100% facilitaion of insurance claims within 30 days | 100% facilitaion of insurance claims within 30 days | 100% facilitaion of insurance claims within 30 days | 100% facilitaion of insurance claims within 30 days | Quarterly Insurance Claims Report
To facilitate 100% payment of insurance claims excess within five days by June 2017 | Excess Claims | Human Resources and Finanical Resources | Proof of payment | Loss management | Insurance excess | 2015/2016 FY Insurance Excess payment report | Percentage payment facilitation of insurance excess within five days | 100% payment facilitation of insurance excess within five days | 100% payment facilitation of insurance excess within five days | 100% payment facilitation of insurance excess within five days | 100% payment facilitation of insurance excess within five days | 100% payment facilitation of insurance excess within five days | Insurance Claims Excess reports and Files | R300,000.00
To facilitate 100% provision of physical security to municipal assets by June 2017 | Manage and monitor security operations | Human Resources and Finanical Resources | Safeguarded assets, employees and visitors | Improved Security | Security Management | 2015/2016FY Security Contracts | Percentage facilitation of provision of physical security to all municipal assets | 100% facilitation of provision of physical security to all municipal assets | 100% facilitation of provision of physical security to all municipal assets and staff | 100% facilitation of provision of physical security to all municipal assets and staff | 100% facilitation of provision of physical security to all municipal assets and staff | 100% facilitation of provision of physical security to all municipal assets and staff | Signed Security contract Quartely Physical security reports | 19000000
To conduct 8 security Operational sites assessments by June 2017 | Security operations sites assessment | Human Resources | Security sites report | Improved security | Security Operational sites Assessments | 2015/2016 Security Operational sites Assessments | number of security operational sites assessment conducted | 8 security operational sites assessments conducted | 2 security operational sites assessments conducted | 2 security operational sites assessments conducted | 2 security operational sites assessments conducted | 2 security operational sites assessments conducted | 8 Security operational sites assessment reports | 0
To facilitate 100% of fraud reported cases for referral and investigation within five days by June 2017 | Operate and Maintenance Disclosure Hotline | Human Resources and Finanical Resources | Fraud cases reports | Increased awareness | Fraud Management | Anti-fraud and corruption Disclosure Hotline | Percentage facilitation of fraud reported cases | 100% fraud reported cases facilitated | 100% facilitation of fraud reported cases for referrals and investigation within five days | 100% facilitation of fraud reported cases for referrals and investigation within five days | 100% facilitation of fraud reported cases for referrals and investigation within five days | 100% facilitation of fraud reported cases for referrals and investigation within five days | Anti-Fraud(Disclosure hot line)Management report | R50,000.00
To undertake two risk management trainings by June 2017 | Provide Risk Management training | Human Resources | Training module | Capacitated staff & councillors | Risk Management Training | 2015/2016 FY Training conducted for Risk Champions | Number of Risk Management training initiatives undertaken | 2 Risk Management training initiatives undertaken | 0 | 1 Risk Management training initiatives undertaken | 0 | 1 Risk Management training initiatives undertaken | Training report and attendance register | 0
To undertake one management strategic session by 2017 | Strategic Management | Human Resources and Finanical Resources | Strategic plan | Resourced operations | Strategic Management Planning | 2012/2013 Strategic Management session held | Number of Strategic Management Planning sessions held | 1 Strategic Management Planning sessions Undertaken | 0 | 1 Strategic Management Planning sessions Undertaken | 0 | 0 | Strategic Planning report Attendance register | R250,000.00
To conduct 2 campaigns for the elderly by June 2017. | By establishing partnerships with organisations to champions rights of elderly people and observe calendar days | Financial and human resources | Mandela day event | Increased awareness among communities on elderly people's rights | Aged Care | 1 Campaign for the elderly Conducted | Number of campaigns held for the elderly | 2 Campaigns for the elderly conducted | 1 Elderly Campaign conducted | 1 Elderly Campaign conducted | 0 | 0 | Exit Report | 85000 | Improved standard of living and conjusise envronment for elderly persons
To conduct 2 programmes for the children by June 2017. | By establishing partnerships with organisations to champion rights of children and observe days | Financial and human resources | Childen's day event | Increased community awareness on children's rights | Children's Care | 2 Children's programmes conducted | Number of programmes conducted for children | 2 Children's programmes conducted | 0 | 1 Children's programme conducted | 0 | 1 Children's programme conducted | Exit Report | 60000 | Improved enviornment for children development
To conduct 4 activities for people with disability by June 2016. | By establishing partnership with organisations for people with disability and organise activities | Financial and human resources | Integrated programme for people living with disability. |  | People with Disability | 3 activities for people with disability conducted | Number of activities conducted for people with disability | 4 activities conducted for people with disability | 1 activity for people with disability conducted | 2 activity for people with disability conducted | 1 activity for people with disability conducted | 0 | Exit Report | 80000 | Improved environment for people with disability.
To facilitate 3 programmes for development of youth by June 2016. | By establishing strategic partnership with public and private sector to integrate youth in the socio-economic mainstream | Financial and human resources | Integrated Youth Develepment | improved youth development approach | Youth Programmes | 3 programmes for development of youth facilitated | Number of youth programmes facilitated for youth development | 3 youth programmes facilitated for youth development | 1 Youth programme for development of youth conducted | 0 | 1 Youth programme for development of youth conducted | 1 Youth programme for development of youth conducted | Exit Report | 130000 | Youth Intergrated in the socio-economic mainstream of the district
To facilitate 3 Programmes of women in the socio-economic mainstream to fight against gender based violence by June 2017. | By establishing partnerships aimed at socio-economic empowerment of women and using public procurement | Financial and human resources | Event | Integrated approach to women and gender develioment issues | Women’s Development Initiatives | 3 Programmes facilitated for women in the socio-economic mainstream to fight against gender based violence conducted in 2014/15 | Number of Programmes facilitated for women in the socio-economic mainstream to fight against gender based violence | 3 Programmes facilitated for women in the socio-economic mainstream to fight against gender based violence | 1 Programme of women in the socio-economic mainstream and fight against gender based violence conducted | 1 Programme of women in the socio-economic mainstream and fight against gender based violence conducted | 1 Programme of women in the socio-economic mainstream and fight against gender based violence conducted | 0 | Exit Report | 120000 | Reduce poverty and unemployment among women
To facilitate 6 programmes in harmonizing relationship with traditional leaders by June 2017. | By facilitating partnerships and linkages with traditional leadership structures and proving support to official events for traditional leaders | Financial and human resources | Number of magoshi events | Improved relations between Municipality and Magoshi | Traditional Leadership (Executive support) | 8 programmes in harmonizing relationship with traditional leaders facilitated | Number of programmes facilitated in harmonizing relationship with traditional leaders | 6 programmes facilitated in harmonizing relationship with traditional leaders | 0 | 2 programme s in harmonising relationship with traditional leaders conducted | 2 programme s in harmonising relationship with traditional leaders conducted | 2 programme s in harmonising relationship with traditional leaders conducted | Exit Report | 320000 | Poiliticla and governance stability
To provide support to 12 Mayoral Committee meetings by June 2017. | By providing ongoing support to the mayoral committee and lekgotla sittings with logistics and secretariat | Financial and human resources | Number of successful Excutive support meetings and events | Effective and fully functional committee | Executive Support (mayoral committee and lekgotla) | 12 Mayoral Committee meetings conducted | Number of occasions where mayoral committee received executive support | 12 executive support occasions provided to mayoral committee meetings | 3 Mayoral Committee meetings conducted | 3 Mayoral Committee meetings conducted | 3 Mayoral Committee meetings conducted | 3 Mayoral Committee meetings conducted | Calender and Minutes | 0 | Political stability. Ehannced oversight
To organise 1 international relations trip by June 2017 | By identifying 1 international project for best practices. | Financial and human resources | Memorandum of understanding | Improves International Relations | International relations | 0 international relations trip organised. | Number of international relations trip organised. | 1 international relations trip organised *MOU generated *Trip undertaken | 0 | 1 international relations trip organised | 0 | 0 | MOU and confirmation letters from ambassey | 20000 | Enhanced international relations.
To facilitate 3 Moral Regeneration Movement (MRM) activities by June 2017. | By partnering with stakeholders and communities to raise awareness on issues of moral regeneration | Financial and human resources | Number of MRM activities | Improved moral restoration | MRM | 3 MRM activities facilitated | Number of MRM activities facilitated | 3 MRM activities facilitated | 1 MRM activity conducted | 0 | 1 MRM activity conducted | 1 MRM activity conducted | Exit Report | 30000 | Peace and Order
To conduct 10 citizenry engagements through outreaches by June 2017. | By providing ongoing community engagement sessions and stakeholder consultations | Financial and human resources | Number of successful outreach meetings | Improved service delivery | Community & stakeholder engagement | 14 citizenry engagement by outreaches conducted | Number of citizenry engagement conducted | 10 citizenry engagements conducted | 2 citizenry engagement and participatory democracy outreaches conducted | 3 citizentry engagement and participatory democracy outreaches conducted | 3 citizentry engagement and participatory democracy outreaches conducted | 2 citizenry engagement and participatory democracy outreaches conducted | Exit Report | R2 000 000 | Improve service delivery. peace and order
To conduct 5 strategic events to promote social cohesion and national building by June 2017. | By implementing heritage, cultural and contemporary events | Financial and human resources | Number of activities | Cultural preservation elvated | Strategic Events | 5 strategic events to promote social cohesion and national building conducted | Number of strategic events held to promote social cohesion and national building | 5 strategic events to promote social cohesion and national building conducted | 2 strategic events to promote social cohesion and national building conducted | 1 strategic events to promote social cohesion and national building conducted | 1 strategic events to promote social cohesion and national building conducted | 1 strategic events to promote social cohesion and national building conducted | Exit Report | R 1 080 000 | Cultural and traditional preservation. Preserve heritage
To undertake 12 website updates by June 2017 | By revamping website and ensuring regular and compulsory updates | Financial and human resources | Fully functional website | Informed communities and stakeholders | Website management | functional website | Number of website updates undertaken | 12 statutory website updates undertaken | 3 statutory webside updates undertaken | 3 statutory webside updates undertaken | 3 statutory webside updates undertaken | 3 statutory webside updates undertaken | Exit Report | 90000 | Informed communities and stakeholders
To market and brand 12 events by June 2017 | By establishing marketing platforms and branding to profile the district | Financial and human resources | Marketing events | Enhanced brand | Marketing | 100% holistic marketing and branding of the district done | Number of events marketed /branded and quantity of marketing materials procured | 12 events marketed and branded | 3 events marketed and branded | 3 events marketed and branded | 3 events marketed and branded | 3 events marketed and branded | Exit Report | 275000 | Improved coroprate identity and attract investors
To undertake 18 media relations activities by June 2017 | By actively selling SDM products in various media platforms and supporting local media | Financial and human resources | Number of successful media events | Informed communities and stakeholders | Advertising | 12 media relations activities held | Number of media relations activities undertaken | 18 media relations activities undertaken*statements *networking sessions | 5 media relations activities conducted | 5 media relations activities conducted | 4 media relations activities conducted | 4 media relations cativities conducted | Exit Report | 120000 | Enhanced image
To produce 14 internal, external and special news letters by June 2017 | By providing regular internal and external newsletter | Financial and human resources | Printing of qulaity news letters | Informed communities and stakeholders | Newsletter production and publication | 0 Internal, 0 external and 1 special news letter | Number of internal, external and special Newsletters produced | 14 Newsletter produced * 4 external *4 special *6 internal | 1 external, 1 special and 1 internal produced | 1 external, 1 special and 1 internal produced | 1 external, 1 special and 2 internal produced | 1 external, 1 special and 2 internal produced | Exit Report | R1 000 000 | Informed communities and stakeholders
To facilitate 2 Theatre workshops by June 20167 | By implementing drama/performing arts workshops and training | Financial and human resources | Number of workshops | Improved knowledge among partcipants on cultural matters | Theatre promotion | 2 Theatre programmes conducted | Number of theatre workshops facilitated | 2 Theatre workshops facilitated | 0 | 2 Theatre programmes conducted | 0 | 0 | Exit Report | 100000 | Knowledge transfer
To facilitate 3 indigenous languages promotion sessions by June 2017 | By implementing language policy and partnering with stakeholder to promote indigenous language | Financial and human resources | Number of language policy programmes | Langauge promotion and preservation | Indigenous languages promotion | 3 indigenous languages promotion conducted | Number of indigenous languages promotion facilitated | 3 indigenous languages promotion sessions facilitated *Sepedi, Isiswati and Isindebele | 1 indigenous languages promotion conducted | 2 indigenous languages promotion conducted | 0 | 0 | Exit Report | 0 | Preserve langauges
To organise 3 Sport Activities by June 2017 | By organising 3 Sport Activities *Executive Mayor's Marathon *Executive Mayor's Cup *Indigenous Games to promote Athletics in the District | Financial and human resources | Healthy lifestyle | Improves Healthy Lifestyle | Sport activities | 3 Sport Activities organised | # of Sport activities facilitated | 3 Sport Activities organised *Executive Mayor's Marathon *Executive Mayor's Cup *Indigenous Games | 2 Sport Activity organised | 0 | 0 | 1 Sport Activity organised | Exit Report | 180000 | Healthy lifestyle
To organise 4 Batho Pele activities by June 2017 | By upholding the Batho Pele Principles and promoting culture of service delivery | Financial and human resources | Number of batho pele activities | Enhanced brand and positive perception about SDM | Batho-Pele | 4 Batho pele activities organised | Number of batho pele activities organised | 4 Batho pele activities organised in all five local municipalities | 1 Batho pele activity organised | 1 Batho pele activity organised | 1 Batho pele activity organised | 1 Batho pele activity organised | Exit Report | 50000 | Informed communities and stakeholders
To generate 24 reports on customer care by June 2017 | By providing 24 hour service call centre system | Financial and human resources | 24 hour functional call centre | Imporved accessibility and changed perceptions | Customer Care Management | 100% provision of professional customer care centre maintained | Number of reports on customer care generated | 24 Reports on customer care generated *X12 Presidential/Premier reports *x12 SDM Call centre reports*Procurement of call centre system | 6 customer care reports generated | 6 customer care reports generated | 6 customer care reports generated | 6 customer care reports generated | Exit Report | 50000 | informed communities and stakeholders
To facilitate 8 Fora in relation to IGR framework by June 2017 | By securing of venue, issuing of notices and agendas, and recording of proceedings | Human and financial resources | Coordinated IGR Forums | Improved intergovernmental relations | Speakers’ and Chief Whips’ Fora | 08 Fora | Number of fora facilitated | 8 Fora facilitated | 2 - One Speakers' Forum and One Chief Whips' Forum | 2 - One Speakers' Forum and One Chief Whips' Forum | 2 - One Speakers' Forum and One Chief Whips' Forum | 2 - One Speakers' Forum and One Chief Whips' Forum | Signed minutes and attendance registers | R10,000.00 | Improved governance
To facilitate 13 public consultation meetings on IDP by end of April 2017 | By securing of venues, issuing of notices, transport logistics and record proceedings | Human and financial resources | Involvement of the public on matters of governance in the District | Enhanced participatory democracy | Consultation on 2017/18 IDP | 13 public participation sessions on IDP | Number of public consultation meetings facilitated | 13 Public consultation meetings facilitated | 0 | 0 | 0 | 13 Public consultation meetings facilitated | Attendance registers | 0 | Public accounctability
To facilitate 8 Public consultation meetings on the 2015/2016 Annual report by February 2017 | By securing of venues, issuing of notices, transport logistics and record proceedings | Human and financial resources | Involvement of the public on matters of governance in the District | Enhanced accountability | Public participation on 2015/16 draft annual report | 08 public participation sessions on Annual Report | Number of public consultation meetings facilitated | 8 Public consultation meetings facilitated | 0 | 0 | 8 Public consultations facilitated | 0 | attendance registers and exit report | 400000 | Public accounctability
To facilitate 1 GNC workshop by October 2016 | By securing venue, Preparation of materials, issuing of notices and recording of proceedings | Human and financial resources | Knowledge sharing | Enriched knowledge on GNC processes | Public awareness on geographical name change | 06 GNC Meetings facilitated | Number of GNC workshop facilitated | 1 GNC workshop facilitated | 0 | 1 GNC workshop facilitated | 0 | 0 | attendance registers and exit report | 50000 | Improved governance
To facilitate one District ward committee conference by June 2017 | By securing venue, Preparation of materials, issuing of notices and recording of proceedings | Human and financial resources | Conference held | Enhanced governance | Ward Committee Conference | 01 district ward committee conference facilitated | Number of district Ward Committee conference facilitated | 1 District ward committee conference facilitated | 0 | 0 | 0 | 1 District ward committee conference facilitated | attendance registers and exit report | 100000 | Public accounctability
To facilitate 3 workshops for Councillors on Compliance by March 2017 | By booking venue, prepare material, issue notices, record proceedings | Human resources | Workshop facilitated | Improved compliance | Capacity building for Cllrs | 3x capacity building workshops held | Number of workshops facilitated | 3 Workshops facilitated. (2 Income Tax and 1 Code of conduct) | 1 Workshop on code of conduct/ethics for cllrs facilitated | 0 | 1 Income Tax workshop facilitated | 1 Income Tax workshop facilitated | Exit report | 0 | Improved governance
To facilitate 2 training skills development programmes for Councillors by June 2017 | By identifying training course, issue invites to attending Cllrs | Human and financial resources | Trining facilitated | Skills development | Training of Councillors | 2 X training and development programmes attended | Number of training programmes facilitated | 2 training programmes facilitated | 1 Training programme for cllrs facilitated | 0 | 0 | 1 Training programmes for cllrs facilitated | Exit report | 0 | Improved governance
Facilitate 100% completion of declaration of interest returns by October 2016 | By facilitating workshop of declaration of interest return s | Human resources | Declaration of interest returns facilitated | Completed declaration of interest returns | Councillor declaration of interest returns | 100% of Councillors declared | Percentage of declaration of interest returns completed | 100% completion of declaration of interest returns | 100% completion of declaration of interest returns facilitated | 0 | 0 | 0 | Completed declarion of interest returns | 0 | Improved governance
To facilitate 100% resolution of Councillors queries within 30 days | *By recording Councillors queries *By submitting queries to relevant department for attention*By giving feedback to the relevant councillors | Human resources | Query register | Improved Councillor welfare | Councillors welfare | 5 X queries *12 X assistance on claims attended to | Percentage resolution of Cllrs queries facilitated | 100% Councillors queries facilitated.(Recording queries 10%, submission and attending to the queries 70%, Feedback 20%) | 100% cllrs queries facilitated (recording queriesv10%, submission and attending to queries 70%, feedback 20%) | 100% cllrs queries facilitated (recording queriesv10%, submission and attending to queries 70%, feedback 20%) | 100% cllrs queries facilitated (recording queriesv10%, submission and attending to queries 70%, feedback 20%) | 100% cllrs queries facilitated (recording queriesv10%, submission and attending to queries 70%, feedback 20%) | Occurance register | 0 | Improved governance
To facilitate 100% implementation of the approved schedule of Council activities by June 2017 | By compiling schedule of Council activities, service in Council meeting for approval and implement activities | Human and financial resources | Annual council calendar | Improved governance | Schedule of Council Activities | 22 Council and portfolio committee meetings held | Percentage facilitation of schedule of council activities | 100% facilitation of schedule of council activities. (Council meetings 40%, Portfolio meetings 40%, Standing committee meetings 20%) | 100% (2x council meetings, 10x portfolio committee meetings facilitated) | 100% (2x council meetings, 5x portfolio committee meetings facilitated) | 100% (2x council meetings, 10x portfolio committee meetings facilitated) | 100% (2x council meetings, 5x portfolio committee meetings facilitated) | attendance registers and exit report | R955 000.0 0 | Improved governance
To facilitate four oversight visits by June 2017 | By liaising with relevant department, identify the projects and draw oversight plan | Human and financial resources | Oversight reports | Effective oversight | Oversight visits | 4 oversights visits facilitated | Number of oversight visits facilitated | 4 oversight visits facilitated *pre-oversight visit *sessions with project managers *compile pre-oversight report | 1 oversight visit facilitated | 1 oversight visit facilitated | 1 oversight visit facilitated | 1 oversight visit facilitated | Oversight visit reports | 0 | Public accounctability
To conduct one induction of new councillors and facilitate one strategic planning session for Council Committees by September 2016 | By preparing strategic planning material, book venue, invite Cllrs and officials to attend the strategic planning | Human and financial resources | Induction workshop and strategic plan | knowledgeable Councillors and effective oversight | Section 79 Committees Strategic planning | 2 strategic planning sessions facilitated | Number of induction conducted and strategic planning sessions acilitated | 1 Induction of new Councillors conducted (1st Quarter - September). 1 Strategic planning session facilitated for Section 79 portfolio and standing committees (1st Quarter - September) | 1 induction of new councillors conducted | 1 strategic planning session facilitated | 0 | 0 | Exit report | 0 | Improved governance
To compile and coordinate 100% Council resolution register by June 2017 | By compiling council resolutions, submit to management and serve in the council meeting | Human resources | Quarterly resolution registers | Improved resolution implementation | Council Resolution register | 4 Resolution registers developed and implemented | % Council Resolution register compiled and coordinated | 100% Council Resolution register compiled and coordinated | 100% Council Resolution register compiled and coordinated | 100% Council Resolution register compiled and coordinated | 100% Council Resolution register compiled and coordinated | 100% Council Resolution register compiled and coordinated | Resolution Register | 0 | Improved governance
To facilitate two extra special council meetings - SODA and to outline budget priorities for 2017/2018 by May 2017 | By preparing the agenda and invites for extra special council meetings | Human and financial resources | SODA and Budget Speech | Improved accountability | Budget Speech | 1 Extra Special Council facilitated | Number of extra special council facilitated | 2 Extra Special Council meetings facilitated | 0 | 0 | 1 Extra Special Council meeting (SODA) facilitated | 1 Extra Special Council meeting (Budget Speech) facilitated | Attendance Register and minutes | 250000 | Public accounctability
To facilitate 2 study groups for councillors | By fostering relationship with provincial and national legislatures | Human and financial resources | Study groups | Implementation of best practice by Councillors | Councillors study groups | New | Number of study groups facilitated | 2 study groups for councillors facilitated | 0 | 1 Study group for councillors facilitated | 1 Study group for councillors facilitated | 0 | Exit reports | 0 | Improved governance
To coordinate training of ward committees in the district | By liaising with Coghsta and Local Municipalities | Human resources | Training of ward committees | Effective ward committees | Coordination of ward committees’ training | New | Number of ward committee s training coordinated | 1 training of ward committees coordinated | 0 | 1 Training of ward committees coordinated | 0 | 0 | Exit report | 0 | Improved governance
To facilitate 3 public awareness engagements on SDM petition policy | By conducting interviews with local, regional and national radio stations | Human resources | Involvement of the public on matters of governance in the District | Enhanced participatory democracy | Public Awareness on SDM Petition policy | New | Number of public awareness engagements facilitated | 3 public awareness engagements facilitated | 0 | 1 Public awareness engagements facilitated | 1 Public awareness engagements facilitated | 1 Public awareness engagements facilitated | Exit reports | 0 | Public accounctability
To convene 4 Secretariat Fora | By inviting local secretariat officials to form part of Secretariat Forum | Human and financial resources | Coordinated IGR Forums | Improved intergovernmental relations | Secretariat forum | New | Number of Secretariat Fora convened | 4 Secretariat Fora convened | 1 Secretariat Forum convened | 1 Secretariat For a convened | 1 Secretariat For a convened | 1 Secretariat For a convened | Attendance registers and minutes | 0 | Improved governance
To convene 4 public participation fora | By inviting local public participation officials to form part of Public Participation Forum | Human and financial resources | Coordinated IGR Forums | Improved intergovernmental relations | Public Participation Forum | New | Number of Pulbic Participation For a convened | 4 Public Participation For a convened | 1 Public Participation forum convened | 1 Public Participation fora convened | 1 Public Participation fora convened | 1 Public Participation fora convened | Attendance registers and minutes | R0.00 | Improved governance
To facilitate 8 multi-party Council & Portfolio Committees caucuses | By booking the venue, issue invitations, record proceedings | Human and financial resources | Caucuses facilitated | Effective engagements | Caucuses | New | Number of caucuses held | 8 caucuses facilitated | 2 Caucuses facilitated | 2 Caucuses facilitated | 2 Caucuses facilitated | 2 Caucuses facilitated | Exit reports | 0 | Improved governance
To facilitate multi-party Workshop on back to basics and other national programmes | By preparing training material, identify person to facilitate, book the venue, issue invitations, record proceedings | Human and financial resources | Workshop facilitated | Improved compliance | Back to basics workshop | New | Number of workshops held | 1 workshop facilitated | 0 | 1 workshop facilitated | 0 | 0 | Exit report | 0 | Improved governance
To facilitate 4 multi-party Council whippery meetings | By booking venue, issue invitations, record proceedings | Human resources | Council whippery meetings facilitated | Improved communication | Council Whippery | New | Number of meetings held | 4 council whippery meetings facilitated | 1 Councl whippery meeting facilitated | 1 Councl whippery meeting facilitated | 1 Councl whippery meeting facilitated | 1 Councl whippery meeting facilitated | Exit reports | 0 | Improved governance
To facilitate 4 caucus outreach | By identifying relevant stakeholders, book venue, record proceedings | Human and financial resources | Caucuses facilitated | Enhanced participatory democracy | Caucus outreach | New | Number of meetings held | 4 caucus outreaches facilitated | 1 Caucus outreach facilitated | 1 Caucus outreach facilitated | 1 Caucus outreach facilitated | 1 Caucus outreach facilitated | Exit reports | 0 | Public accounctability
To review 100% standing rules and orders of council annually | By identifying sections which need to be reviewed for purpose of amendment | Human resources | Standing rules and orders reviewed | Updated standing rules and orders of council | Council Standing Rules and Orders | New | Percentage Reviewed sections of standing rules and orders | 100% Recommended sections for amendment are packaged to council for considerations | 0 | Recommended sections for amendment are packaged to council for considerations | 0 | 0 | Exit report | 0 | Improved governance