## Sheet1
OFFICE OF THE EXECUTIVE MAYOR 2017/2018
2017/2018 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN:
GOOD GOVERNANCE AND PUBLIC PARTICIPATION
OBJECTIVE | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2016/2017 | INDICATORS | ANNUAL TARGET 2017/2018 | Q1 | Q2 | Q3 | Q4 | ACTION (Retained/Remove/ Adjust) | REASON FOR ACTION | BUDGET ADJUSTED | EVIDENCE | BUDGET 2017/18 | IMPACT
To facilitate campaigns for the elderly by June 2018. | Human and Financial resources | Integrated Aged Advocacy Programme | Promote Stakeholder Engagement In Public Service | Facilitation of Aged Care campaigns | 2 Campaigns for the elderly facilitated | Number of Aged Care campaigns facilitated | 2 Aged Care campaigns facilitated | Facilitate Mandela Day held | Facilitate a session for International Older Person's day. | No Activity | No Activity | Retain | None | 0 | *Aged Care Campaigns Reports * Attendance Registers | 90000 | Improved enviornment for elderly programs and development
To facilitate campaigns for the children by June 2018. | Human and Financial resources | Integrated Children Development | Promote Stakeholder Engagement In Public Service | Facilitation of Children's campaigns | 2 Children's campaigns facilitated | Number of children's campaigns facilitated | 2 children's campaigns facilitated | No Activity | Facilitate International children's day. | No Activity | Take A Girl Child To Work | Retain | None | 0 | *Childre's Campaigns Reports * Attendance Registers | 40000 | Improved enviornment ofr children development
To facilitate awareness campaigns for people with disability by June 2018. | Human and Financial resources | Integrated Programme for people living with disability | Promote Stakeholder Engagement In Public Service | Facilitation of awareness campaigns for People with Disability | 3 awareness campaigns for people with disability facilitated | Number of awareness campaigns for people with disability facilitated | 3 awareness campaigns for people with disability facilitated | Albinism awarenes compaign. | Facilitate International disability day | Facilitate Human rights day for people with disability | No Activity | Retain | None | 0 | *People with disability campaigns Reports * Attendance Registers | 90000 | Improved environment for people with disability.
To facilitate Youth development programmes by June 2018. | Human and Financial resources | Integrated Youth Develepment | Promote Stakeholder Engagement In Public Service | Facilitation of Youth Development Programmes | 3 Youth development programmes facilitated | Number of Youth development programmes facilitated | 4 Youth development programmes facilitated | Matriculants tertiary application awareness campaign | Launching of the Youth Council. . | 1. Facilitate Back to school Compaigns. 2.Facilitate Career Exhibition. | *Launching of the Youth Council. *Facilitate Youth Month Expo Celebration. | Adjust | Delay in adoption of youth policy. Q2 target moved to Q4. | 0 | *Reports on youth development programmes facilitated. *Attendance Registers | 400000 | Improved youth development environment
To facilitate Women Development programmes in the socio-economic mainstream by June 2018. | Human and Financial resources | Integrated Women and gender programme | Promote Stakeholder Engagement In Public Service | Facilitation of Women’s Development programmes | 3 Women Development Programmes facilitated violence | Number of Women Development Programmes facilitated | 4 Women Development Programmes facilitated | Launching of women's month and SDM Women Business Summit | Launching of 16 Days | 1. Observe Orange day: visit to 1 centre for abused women. 2.International womens day celebration | No Activity | Retain | None | 0 | *Reports on women development programmes facilitated. *Attendance Registers | 130000 | Improved envrionement for development of women
To facilitate Theatre workshops by June 2018 | Human and Financial resources | Integrated Theatre Promotion | Promote Stakeholder Engagement In Public Service | Facilitation of Theatre workshops | 2 Theatre programmes facilitated | Number of theatre workshops facilitated | 2 theatre workshops facilitated | No Activity | * Facilitate Drama Auditions * Facilitate theatre workshop | No Activity | No Activity | Retain | None | 0 | *Reports on theatre workshops and auditions facilitated. *Attendance Registers | 200000 | Knowledge transfer
To facilitate promotion of indigenous languages by June 2018 | Human and Financial resources | Integrated Indigenous Languages Promotion | Promote Stakeholder Engagement In Public Service | Facilitation of promotion of Indigenous languages | 3 promotions of indigenous languages facilitated | Number of promotions of indigenous languages facilitated | 2 promotions of indigenous languages facilitated | Facilitate Local Competitions on indigenous languages | Facilitate District Language Promotion District Competitions | No Activity | No Activity | Retain | None | 0 | *Reports on promotion of Indigenous languages facilitated. *Attendance Registers | 0 | Preserve langauge
To facilitate Sports activities by June 2018 | Human and Financial resources | Integrated Sports Activities | Promote Stakeholder Engagement In Public Service | Facilitation of Sport activities | 3 Sport Activities facilitated | Number of Sport activities facilitated | 2 Sport activities facilitated | Facilitate Indigenous sports games | Organise Executive Mayor's Cup sports games | Organise Executive Mayor's Cup sports games | No Activity | Adjust | Late finalisation of local municipalities Mayor's cup .Q2 target moved to Q3 | 0 | *Reports on sports activities facilitated. *Attendance Registers | 100000 | Healthy lifestyle
To coordinate health calendar activities by June 2018 | Human and Financial resources | Integrated HIV/AIDS, STIs & TB Programmes Mainstreaming | Promote Stakeholder Engagement In Public Service | Coordination of health calendar days activities. | 3 health calendar days activities conducted | Number of health calendar days activities coordinated | 4 Health calendar days activities coordinated | No Activity | Coordinate World AIDS Day Commemoration | * Coordinate STIs Condom Week Campaign * Coordinate TB Month Commemoration | Coordinate Candle Light Ceremony | Retain | None | 0 | *Reports on health calendar days activities facilitated. *Attendance Registers | 30000 | Healthy lifestyle
To coordinate District Health Council Programmes by June 2018 | Human and Financial resources | Integrated District Council Programmes | Promote Stakeholder Engagement In Public Service | Coordination of District Health Council Programmes | 3 Support Visits to health care facilities coordinated | Number of Support Visits to health care facilities coordinated | 4 Support Visits to health care facilities coordinated | 1 Support Visits to health care facilities coordinated | 2 Support Visits to health care facilities coordinated | 3 Support Visits to health care facilities coordinated | 4 Support Visits to health care facilities coordinated | Retain | None | 0 | *Reports on District Health Council programmes. *Attendance Registers | 20000 | Effective and Efficient Health Care Facilities
To facilitate programmes in harmonizing relationship with traditional leaders by June 2018. | Human and Financial resources | Integrated Traditional Leadership (Executive Support) | Promote Stakeholder Engagement In Public Service | Facilitation of Traditional Leadership (Executive support) | 8 programmes in harmonizing relationship with traditional leaders facilitated | All programmes facilitated in harmonizing relationship with traditional leaders | All programmes facilitated in harmonizing relationship with traditional leaders | All programmes facilitated in harmonizing relationship with traditional leaders | All programmes facilitated in harmonizing relationship with traditional leaders | All programmes facilitated in harmonizing relationship with traditional leaders | All programmes facilitated in harmonizing relationship with traditional leaders | Retain | None | 0 | Exit Report | 460000 | Political and governance stability
To provide support to Mayoral Committee meetings by June 2018. | Human and Financial resources | Integrated Executive Support (Mayoral Committee and Lekgotla) | Promote Stakeholder Engagement In Public Service | Executive Support to Mayoral Committee | 12 Mayoral Committee meetings | Number of Mayoral Committee meetings supported. | 12 Mayoral Committee meetings and supported. | * 3 Logistical support to the Mayoral Committee. * 1 Lekgotla supported | * 6 Logistical support to the Mayoral Committee. * 2 Lekgotla supported | * 9 Logistical support to the Mayoral Committee. supported | *12 Logistical support to the Mayoral Committee. supported | Adjust | Lekgotla is PMS function | 0 | * Mayoral Committee minutes * Attendance Registers | 0 | Political stability. Ehannced oversight
To organise 1 international relations trip by June 2018 | Human and Financial resources | Integrated International Relations | Promote Stakeholder Engagement In Public Service | International Relations | 0 international relations trip organised. | Number of international relations trip organised. | 1 international relations trip organised *MOU generated *Trip undertaken | No Activity | 1 International relations facilitated | No Activity | No Activity |  |  | 0 | * Mayoral Committee minutes * Attendance Registers | 20000 | Enhanced International relations.
To facilitate Moral Regeneration Movement (MRM) capacity building by June 2018. | Human and Financial resources | Integrated Society MRM | Promote Stakeholder Engagement In Public Service | Facilitation of Moral Regeneration Movement capacity building | MRM committee established | Number of workshops for MRM committee facilitated | 1 workshop for MRM committee facilitated | * Workshopping of the MRM Committee * Develop programmes for MRM committee | Implementation of MRM programmes | Implementation of MRM programmes | Implementation of MRM programmes | Retain | None | 0 | * Moral Regeneration Movement Committee reports * Attendance Registers | 20000 | Enhanced Social Cohesion and National Building
To conduct outreaches /Imbizos by June 2018. | Human and Financial resources | Engagement Stakeholder | Promote Stakeholder Engagement In Public Service | Conduct outreaches and Imbizos | 08 imbizos/outreaches conducted | Number of imbizos/outreaches conducted | 8 imbizos/outreaches conducted | 2 imbizos/outreaches conducted | 4 imbizos/outreaches conducted | 6 imbizos/outreaches conducted | 8 imbizos/outreaches conducted | Retain | None | 0 | * Imbizos/Outreaches reports * Attendance Registers | R2M | Improved relations
To facilitate strategic events by June 2018. | Human and Financial resources | Integrated Society and Improved Arts and culture | Promote Stakeholder Engagement In Public Service | Facilitation of Strategic Events | 5 strategic events facilitated | Number of strategic events facilitated. | 5 strategic events facilitated. | *King Sekhukhune I Commemoration facilitated * Heritage Day facilitated | Kgoshi Nyabela Commemoration Day facilitated | Kgoshi Mampuru Commemoration Day facilitated. Facilitate SODA | Bapedi Kings Commemoration Day facilitated | Adjust | SODA target added in Q3 | 0 | * Strategic Events Report * Attendance Registers | R1M | Informed communities
To update website by June 2018 | Human and Financial resources | Regular updated and functional website | Promote Stakeholder Engagement In Public Service | Update of Website | functional website | Number of website updates undertaken | 12 website updates undertaken | 3 updates undertaken | 6 updates undertaken | 9 updates undertaken | 12 updates undertaken | Retain | None | 0 | Print out website report | 100000 | Informed communities and stakeholders
To market and brand events by June 2018 | Human and Financial resources | Marketing events | Promote Stakeholder Engagement In Public Service | Marketing and branding of events | 10 marketing and branding events of the district done | Number of events marketed | 12 events marketed | 3 events marketed and branded | 6 events marketed and branded | 9 events marketed and branded | 12 events marketed and branded | Retain | None | 0 | Photos of the marketed events | R225 000.00 | Improved corporate identity and attract investors
To undertake media relations activities by June 2018 | Human and Financial resources | Regular adverts published | Promote Stakeholder Engagement In Public Service | Undertaking of media relations activities | 12 media relations activities undertaken | Number of media relations activities undertaken | 14 media relations activities undertaken | 5 media relations activities undertaken | 9 media relations activities undertaken | 11 media relations activities undertaken | 14 media relations activities undertaken | Retain | None | 0 | * Media clipse * Media statements * Adverts | 160000 | Imporved media relations
To produce internal, external and special news letters by June 2018 | Human and Financial resources | Regular copies of publications provided to communities | Promote Stakeholder Engagement In Public Service | Production of internal, external and special newsletters. | 3 Internal, 2 external and 1 special news letter produced | Number of internal, external and special Newsletters produced | 8 Newsletter produced | 1 internal newsletter produced | 1 external, 1 special and 1 internal newsletter produced | 1 Internal newsletter produced | 1 external, 1 Internal and 1 special newsletter produced | Retain | None | 0 | Copies of internal, external and special newsletters produced. | 850000 | Informed and engaged communities
To facilitate Batho Pele activities by June 2018 | Human and Financial resources | Implementation of Batho Pele principles | Promote Stakeholder Engagement In Public Service | Facilitation of Batho-Peel Activities | 4 Batho pele activities facilitated | Number of batho pele activities facilitated | 4 batho pele activities facilitated | No Activity | 4 batho pele activities facilitated | 3 batho pele activities facilitated | 4 batho pele activities facilitated | Adjust | Target corrected to cummulative | 0 | Batho Pele activities Report | 50000 | Improved Relations
To generate customer care reports by June 2018 | Human and Financial resources | Level of Customer satisfaction | Promote Stakeholder Engagement In Public Service | Generation of customer care reports. | 24 Reports on customer care generated. | Number of reports on customer care generated | 24 reports on customer care generated | 6 Reports on customer care generated *3 Presidential/Premier reports *3 SDM Call centre reports* | 12 Reports on customer care generated *6 Presidential/Premier reports *6 SDM Call centre reports* | 18 Reports on customer care generated *9 Presidential/Premier reports * 9 SDM Call centre reports* | 24 Reports on customer care generated *12 Presidential/Premier reports *12 SDM Call centre reports* | Retain | None | 0 | Report on Customer care generated+A26:N28A27:N28 | 0 | Improved Relations and Customer Care