## LOCAL ECONOMIN DEV
2015/2016 SERVICE DELICERY BUDGET AND IMPLEMENTATION
KPA 3: LOCAL ECONOMIC DEVELOPMENT
PLANNING AND ECONOMIC DEVELOPMENT
WEIGHTING | SUB-WEIGHTING | MEASURABLE OBJECTIVE | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2017/18 | INDICATORS | ANNUAL TARGET 2017/18 | Midterm targets | PROGRESS ACHIEVED/NOT ACHIEVED/ NOT APPLICABLE | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTION | EVIDENCE | BUDGET 2017/18 | IMPACT
2016/2017 SERVICE DELIVERY BUDGET IMPLEMENTATION PLAN: SDA
|  | To facilitate 100% implementation of Schuinsdraai, Potlake Nature reserves and De Hoop Dam business plans by June 2018 | human and financial resources | Precinct Plan | Improved local planing | Schuinsdraai, Potlake Nature reserve and De Hoop Dam | Business plans for Schuinsdraai, Potlake and De Hoop Dam | Percentage facilitation of implementation of Schuinsdraai, Potlake nature reserve and De Hoop Dam | 100% Appointment of Transational advisors to leverage funding for Schuinsdraai, Potlake reserve and De Hoop Dam business plans (Development of terms of reference * Securing of transaction adviser * Securing a strategic partner * Preparation and submission of close out report) | 10% Development of terms of reference and advertising | Achieved | TOR developed awaiting board approval for advert and commnets from Provincial Treasury | None | N/A | Draft TOR in place | 0 | Improved planning
|  | 100% monitoring and evaluation of Social Labour Plans implemetation by June 2018 | human resources | Implementation framework | Improved Tourism development | Monitoring and Evaluation of Social Labour Plans | Social and Labour Plans and Mining Charter | number of engagements held | 4 quarterly engagemnets held on monitoring and evaluation of Social Labour Plans implemetation ( Quarterly engagement on Social and Labour Plan facilitated) | 2 quartely reports on SLPs implementation | Monthly engagement with DMR and Mining houses | Achieved | 2 reports on the progress of the mines' SLP's has been generated | To continue engaging DMR and Mining Companiesto request SLP's of the other mines | Report and minutes | 0
|  | To undertake 4 engagements with department of rural development and land reform by June 2018 | human resources | Coordinating structure | Improved coordination | Agripark | Agripark business plan | Number of engagements held department of rural development and land reform (DRDLR) | 4 Engagements held department of rural development and land reform (DRDLR) | 2 Engagements held department of rural development and land reform (DRDLR) | Achieved | *2 engageements held with stakeholders.* Tender for fencing of Groblersdal Agri-Hub advertised and on evaluation stage with a budget of R 2million -R3 million set aside for Vleisboom FPSU -In terms of 1 household 1 hacter project- 10 projects are supported covering 855 hactares with a udget of R 13,9 million creating 855 job opportunities | None | N/A | Munites and register | 0 | Local economic development
|  | To finalise Agri SETA accreditation and MOU by June 2018 | human resources | Support package for village retailers | Increased entrepreneurship | Agri SETA Accreditation licence and MOU | Application fo licence submitted | % finalisation of Agri SETA accreditation and MOU | 100 % accreditation certificate and MOU (finalisation of Agri SETA and MOU *Identification of Training facilities*Assesment of training facilities by SETA*Final submission to Agri SETA for accreditation*signing of MOU) | 20% finalisation of Agri SETA and MOU (Identification of Training facilities) | Achieved | *Tranining centre identified and secured at SEDA.* QMS Asssement done and awaing site verification | None | N/A | Letters of confirmation | 0 | Increased entrepreneurship
|  | To implement 100% MOU with MINTEK by June 2018 | human and financial resources | Engagement meetings | Improved coordination | MINTEK Partnership | Draft MOU | % implementation of MOU with MINTEK | 100% implementation of MOU with MINTEK (High level draft research report* Final reasearch report* Feasibilty studies) | 20%High level draft research report | Not Achieved | High level engagements held and MOU signed | Lack of funding to finance R1,3 million for the study | MINTEK to engage Mines for possible funding. * Application in progress with IDC for funding | Report and minutes | 0 | Agricultural development
|  | To implement 100% MOU with TVET colleges and mining houses by June 2018 |  |  |  | Mining Skills development | TVET colleges and Mining Houses taining centres | % facilitation of MOU with Mining Houses and TVET Colleges on for Technical skills development | 100% facilitation of MOU with Mining Houses, TVET Colleges and Universities on for Technical skills development ( Conducting of skills assesment*Engagement with institutions* Draft MOU*Final MOU) | 25% Conducting of skills assesment needs with the Mining Houses |  |  |  |  | Close out report | 0
|  | To facilitate 100% International and local manufacturing excursions |  |  |  | International and local manufacturing excursions | None | Percentage facilitation of International and local manufacturing excursions | 100% facilitation of International and local manufacturing excursions | [5 empty] | Close out report | 0
ACTING: CEO: SDA
DATE